## Sheet5 (hidden)
Row Labels | Count of NEW METER INSTALLED AT DT
ADERALPH | 8
ALL SOLUTION | 18
MAYFAK | 9
QUINTEC | 14
SYSFIX | 11
TEE N BEE | 10
VICBONNY | 10
(blank)
Grand Total | 80

## Sheet1
Row Labels | Count of NEW METER INSTALLED AT DT
ADERALPH | 8
ALL SOLUTION | 18
MAYFAK | 9
QUINTEC | 14
SYSFIX | 11
TEE N BEE | 10
VICBONNY | 10
(blank)
Grand Total | 80

## wc
S/N | SBC NAME | WC METER INSTALLED | S/N | SBC NAME | WC | LVMD | TOTAL | TOTAL AMOUNT
1 | ADERALPH | 17 | 1 | ADERALPH | 17 | 21 | 38 | 760000
2 | ALL SOLUTION | 19 | 2 | ALL SOLUTION | 19 | 18 | 37 | 740000
3 | MAYFAK | 19 | 3 | MAYFAK | 19 | 25 | 44 | 880000
4 | QUINTEC | 15 | 4 | QUINTEC | 15 | 8 | 23 | 460000
5 | SYSFIX | 11 | 5 | SYSFIX | 11 | 0 | 11 | 220000
6 | TEE N BEE | 14 | 6 | TEE N BEE | 14 | 20 | 34 | 680000
7 | VICBONNY | 10 | 7 | VICBONNY | 10 | 13 | 23 | 460000
8 | DEMOL | 3 | 8 | DEMOL | 3 | 15 | 18 | 360000
TOTAL |  | 108 | 9 | WELLDONE | 0 | 2 | 2 | 40000
|  |  | 10 | DEMOL/TEE N BEE | 0 | 1 | 1 | 20000
S/N | SBC NAME | LVMD INSTALLATION | 11 | DEMOL/MAYFAK | 0 | 6 | 6 | 120000
1 | ADERALPH | 21 | TOTAL |  | 108 | 129 | 237 | 4740000
2 | All solution | 18
3 | DEMOL | 15
4 | DEMOL/TEE N BEE | 1
5 | mayfak | 25
6 | mayfak/demol | 6
7 | QUINTEC | 8
8 | REALLOCATED vicbonny | 5
9 | TEE N BEE | 20
10 | vicbonny | 8
11 | welldone | 2
TOTAL |  | 129

## lvmd
S/N | CIS DT Number | New Unique DT Nomenclature | BAND | BU | UT | New UT Name | Feeder Name | Ownership | Installation Position | Metering Status | OLD Meter Number | Meter Functionality Status | Meter Type | Capacity | Connection Status | Commissioning Status | Maintenance Status | Disconnection Status | Coordinates (LAT) | Coordinates (LONG) | Addresses | Identified Issue(s) | Required Materials | Remark by EM Engineer | SBC SCHEDULED FOR INSTALLATION | NEW METER INSTALLED AT DT | STATUS | DATE OF INSTALLATION
1 | 1000280385 | 11-Oke IraINJ-T1-Ayo Alabi-MODUPE ERINOSHO 3 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508007161 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6554 | 3.3491 | MODUPE ERINOSO STREET OKEIRA OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | VICBONNY | 060021050490 | METER INSTALLED | 2023-12-15
2 | 1000280379 | 11-Oke IraINJ-T1-Ayo Alabi-MODUPE ERINOSHO 2 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508007162 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6553 | 3.3491 | MODUPE ERINOSO STREET OKEIRA OGBA | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | VICBONNY | 060021050482 | METER INSTALLED | 2023-12-15
3 | 1000265943 | 11-Oke IraINJ-T1-Ayo Alabi-AYO ALABI 51 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508006182 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6496 | 3.3457 | 51 AYO ALABI ROAD OKEIRA OGBA | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | VICBONNY | 060021050033 | METER INSTALLED | 2023-12-15
4 | 1000274431 | 11-Oke IraINJ-T1-Ayo Alabi-AYO ALABI 56 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 60020122220 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6508 | 3.3475 | AYO ALABI ROAD OKEIRA OGBA | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | VICBONNY | 060021050423 | METER INSTALLED | 2023-12-15
5 | 1000281939 | 11-Oke IraINJ-T1-Ayo Alabi-AYO ALABI 13 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508007349 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.646 | 3.3443 | NO 13,AYO-ALABI STREET OGBA. | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | VICBONNY | 060021050798 | METER INSTALLED | 2023-12-15
6 | 1000281941 | 11-Oke IraINJ-T1-Ayo Alabi-AYO ALABI 22 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 60020122089 | FAULTY | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6476 | 3.3447 | NO 22, AYO-ALABI STREET OGBA. | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | VICBONNY | 060021052181 | METER INSTALLED | 2023-12-15
7 | 1000273099 | 11-Oke IraINJ-T1-Ayo Alabi-AYO ALABI 27 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 60020122403 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6473 | 3.3446 | NO 27,AYO-ALABI STREET OGBA. | BURNT METER | WC meter to be installed | WC meter to be installed | VICBONNY | 060021051515 | METER INSTALLED | 2023-12-15
8 | 1000281433 | 11-Oke IraINJ-T1-Ayo Alabi-AYO ALABI 41 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 60020122175 | FAULTY | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6485 | 3.3449 | NO 41,AYO-ALABI STREET OGBA. | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | VICBONNY | 060021052476 | METER INSTALLED | 2023-12-15
9 | 1000280459 | 11-Oke IraINJ-T1-Ayo Alabi-AYO ALABI 52 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508006728 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6503 | 3.3467 | NO 57,AYO-ALABI STREET OGBA. | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | VICBONNY | 060021051593 | METER INSTALLED | 2023-12-15
10 | 1000273367 | 11-Oke IraINJ-T1-Ayo Alabi-AYO ALABI 9B HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 60020122384 | FAULTY | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6458 | 3.3439 | NO 9,AYO-ALABI STREET OGBA. | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | VICBONNY | 060021051547 | METER INSTALLED | 2023-12-15
11 | 1000280648 | 11-Oke IraINJ-T1-Ayo Alabi-CELESTIAL AVENUE 7 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508007359 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6543 | 3.35 | CELESTIAL AVENUE OKEIRA OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 060021050497 | METER INSTALLED | 2023-12-18
12 | 1000280107 | 11-Oke IraINJ-T1-Ayo Alabi-CELESTIAL AVENUE 22 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 60019030606 | FAULTY | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6561 | 3.3498 | CELESTIAL AVENUE OKEIRA OGBA | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 060021051612 | METER INSTALLED | 2023-12-18
13 | 1000280113 | 11-Oke IraINJ-T1-Ayo Alabi-CELESTIAL AVENUE 25 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508006254 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6557 | 3.3498 | CELESTIAL AVENUE OKEIRA OGBA | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 060021051597 | METER INSTALLED | 2023-12-18
14 | 1000281922 | 11-Oke IraINJ-T1-Ayo Alabi-YUSUF STR 22 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508007594 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.649 | 3.3424 | 22YUSUF STREET OKEIRA OGBA | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 060021052768 | METER INSTALLED | 2023-12-18
15 | 1000267819 | 11-Oke IraINJ-T1-Ayo Alabi-YUSUF STR 8 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508004996 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6488 | 3.3433 | NO 10,YUSUF STREET OFF AYO-ALABI STREET OGBA. | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 060021051964 | METER INSTALLED | 2023-12-18
16 | 1001612546 | 11-Oke IraINJ-T1-Ayo Alabi-SAMUEL ABEGUNDE HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 60020122349 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6562 | 3.3506 | ABEGUNDE STREET, OKEIRA OGBA | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 060021050656 | METER INSTALLED | 2023-12-18
17 | 1000280936 | 11-Oke IraINJ-T1-Ayo Alabi-DELE AYEDUN HVDS 4 | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508004371 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6512 | 3.3451 | DELE AYEDUN CLOSE OKEIRA OGBA | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 060021052432 | METER INSTALLED | 2023-12-18
18 | 1000280873 | 11-Oke IraINJ-T1-Ayo Alabi-ALADESHE 8 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508004480 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6546 | 3.3487 | FUNSO ALADESE STREET OKEIRA OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 060021050930 | METER INSTALLED | 2023-12-18
19 | 1000280544 | 11-ObawoleINJ-T1-Youdeowei-3 JOSEPH DEMURIN HVDS | Band B | ABULE EGBA | IJU | IJU | 11-ObawoleINJ-T1-Youdeowei | PUBLIC | POLE MOUNTED | Metered | 201508007082 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6619 | 3.329 | 3 JOSEPH DEMURIN STR OFF BABATUNDE HASSAN | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021052389 | METER INSTALLED | 2024-01-10
20 | 1001663406 | 11-ObawoleINJ-T1-Youdeowei-14 ALHAJI AJISAFE HVDS | Band B | ABULE EGBA | IJU | IJU | 11-ObawoleINJ-T1-Youdeowei | PUBLIC | POLE MOUNTED | Metered | 60017052350 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6672 | 3.3274 | 14 ALHAJI AJISAFE STR OFF RAFTEC WAY | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050484 | METER INSTALLED | 2024-01-10
21 | 1000282142 | 11-ObawoleINJ-T1-Youdeowei-13 ALHAJI MUSTAPHA HVDS | Band B | ABULE EGBA | IJU | IJU | 11-ObawoleINJ-T1-Youdeowei | PUBLIC | POLE MOUNTED | Metered | 201508006798 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.665 | 3.3267 | 13 ALHAJI MUSTAPHA STR | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050839 | METER INSTALLED | 2024-01-10
22 | 1000281366 | 11-ObawoleINJ-T1-Youdeowei-9 AINA STR HVDS | Band B | ABULE EGBA | IJU | IJU | 11-ObawoleINJ-T1-Youdeowei | PUBLIC | POLE MOUNTED | Metered | 201508006352 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6633 | 3.3315 | 9 AINA STREET, UNITY ESTATE | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021052639 | METER INSTALLED | 2024-01-10
23 | 1000281106 | 11-ObawoleINJ-T1-Youdeowei-5 TAIWO SHITTA STR HVDS | Band B | ABULE EGBA | IJU | IJU | 11-ObawoleINJ-T1-Youdeowei | PUBLIC | POLE MOUNTED | Metered | 201508006222 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6609 | 3.3295 | 5 TAIWO SHITTA STR OFF OLD AKUTE ROAD | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050219 | METER INSTALLED | 2024-01-10
24 | 1001660910 | 11-AgegeINJ-T1-Iju Road-18 FAGBA STR HVDS | Band C | ABULE EGBA | IJU | IJU | 11-AgegeINJ-T1-Iju Road | PUBLIC | POLE MOUNTED | Metered | 60017070356 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6576 | 3.3249 | 18 FAGBA STREET OFF IJU ROAD | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021050667 | METER INSTALLED | 2024-01-11
25 | 1000281465 | 11-AgegeINJ-T1-Iju Road-17 PA ALAO HVDS | Band C | ABULE EGBA | IJU | IJU | 11-AgegeINJ-T1-Iju Road | PUBLIC | POLE MOUNTED | Metered | 201508007427 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6535 | 3.3257 | 17 PA ALAO STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021050021 | METER INSTALLED | 2024-01-11
26 | 1004362422 | 11-AgegeINJ-T1-Iju Road-11 AKINFEMI SAVAGE HVDS | Band C | ABULE EGBA | IJU | IJU | 11-AgegeINJ-T1-Iju Road | PUBLIC | POLE MOUNTED | Metered | 60020122063 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6539 | 3.3241 | 11 AKINFEMI SAVAGE OFF TUNJI ADEBAYO STR | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021050246 | METER INSTALLED | 2024-01-11
27 | 1001661410 | 11-AgegeINJ-T1-Iju Road-3 PRINCE DUROTOYE HVDS | Band C | ABULE EGBA | IJU | IJU | 11-AgegeINJ-T1-Iju Road | PUBLIC | POLE MOUNTED | Metered | 60017070050 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6409 | 3.3228 | 3 PRINCE DUROTOYE OFF IJU ROAD | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021050052 | METER INSTALLED | 2024-01-11
28 | 1000260832 | 11-AgegeINJ-T1-Iju Road-30 DADDY SAVAGE HVDS | Band C | ABULE EGBA | IJU | IJU | 11-AgegeINJ-T1-Iju Road | PUBLIC | POLE MOUNTED | Metered | 60019030479 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6552 | 3.328 | 30 DADDY SAVAGE STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021052399 | METER INSTALLED | 2024-01-11
29 | 1003580532 | 11-IjegunINJ-T2-Pipeline-228 & 229 ISAAC ALABI STREET | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Pipeline | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.516 | 3.2611 | ISAAC ALABI STREET | New service | WC meter to be installed | WC meter to be installed | MAYFAK | 060021050670 | METER INSTALLED | 2024-01-15
30 | 1003580534 | 11-IjegunINJ-T2-Pipeline-222 & 223 IJEGUN B/STOP | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Pipeline | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5163 | 3.2602 | IJEGUN B/STOP | New service | WC meter to be installed | WC meter to be installed | QUINTEC | 060021050481 | METER INSTALLED | 2024-01-15
31 | 1002258458 | 11-IjegunINJ-T1-Ikotun-230 & 231 MAJOR BUS STOP | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T1-Ikotun | PUBLIC | POLE MOUNTED | Metered | 60019060423 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5236 | 3.2578 | MAJOR BUS STOP IKOTUN ROAD | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 060021050671 | METER INSTALLED | 2024-01-15
32 | 1002090448 | 11-IjegunINJ-T1-Ikotun-339&462 AYANWALE STREET | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T1-Ikotun | PUBLIC | POLE MOUNTED | Metered | 60019060487 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5351 | 3.2622 | PIPELINE ROAD, IJEGUN | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 060021050444 | METER INSTALLED | 2024-01-15
33 | 1002641892 | 11-IjegunINJ-T2-Pipeline-CSP 401 & 402-KUDEBU ST OFF ISOLO RD | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Pipeline | PUBLIC | POLE MOUNTED | Metered | 60019060800 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5134 | 3.2648 | KUDEBU ST OFF ISOLO RD | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 060021050950 | METER INSTALLED | 2024-01-17
34 | 1000269367 | 11-BeckleyINJ-T1-Agbe road-ILE OGBO HVDS 11 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 60020122187 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6612 | 3.308 | 50B ILE OGBO | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 060021051100 | METER INSTALLED | 2024-01-18
35 | 1000269373 | 11-BeckleyINJ-T1-Agbe road-ILE OGBO HVDS 14 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 60020122457 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6624 | 3.3077 | 57B ILE OGBO | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 060021050466 | METER INSTALLED | 2024-01-18
36 | 1000273499 | 11-BeckleyINJ-T1-Agbe road-TOFEK HVDS 1 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 60019060611 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6571 | 3.309 | 4 TOFEK STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 060021050662 | METER INSTALLED | 2024-01-18
37 | NA | Nathan (11kV) New meter | NA | AKOKA TS | AKOKA TS | AKOKA TS | Nathan (Interphase meter) | PUBLIC | POLE MOUNTED | Metered | 60019060568 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | NA | NA | AKOKA TS | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 060021051963 | METER INSTALLED | 2024-01-16
38 | 1000273488 | 11-BeckleyINJ-T1-Agbe road-OLANIYI HVDS 6 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201508005951 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.658 | 3.3094 | 28 OLANIYI STR | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021050436 | METER INSTALLED | 2024-01-18
39 | 1000273745 | 11-BeckleyINJ-T1-Agbe road-OLANIYI HVDS 11 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201505001147 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6605 | 3.3088 | 45 OLANIYI STR | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021050838 | METER INSTALLED | 2024-01-18
40 | 1002994484 | 11-BeckleyINJ-T1-Agbe road-AKERELE 5 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201508004002 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6505 | 3.3072 | 5 AKERELE OKO OBA | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021051968 | METER INSTALLED | 2024-01-18
41 | 1000266992 | 11-BeckleyINJ-T1-Agbe road-WAMON TAOFEEK HVDS 7 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 60020122413 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6521 | 3.3069 | 18B WAMON TAOFEEK | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021050703 | METER INSTALLED | 2024-01-18
42 | 1000266952 | 11-BeckleyINJ-T1-Agbe road-WAMON TAOFEEK HVDS 9 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201508005576 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6525 | 3.3072 | 18 WAMON TAOFEEK | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021050954 | METER INSTALLED | 2024-01-18
43 | 1000274821 | 11-BeckleyINJ-T1-Agbe road-OWODE HVDS 4 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201508005178 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6528 | 3.3083 | NO 22 OWODE STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021051967 | METER INSTALLED | 2024-01-18
44 | 1000274818 | 11-BeckleyINJ-T1-Agbe road-OWODE HVDS 2 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201508005185 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6513 | 3.3074 | 32 OWODE STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021050874 | METER INSTALLED | 2024-01-18
45 | 1000269376 | 11-BeckleyINJ-T1-Agbe road-OLUSHOLA ADESHINA HVDS 2 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201508006139 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6588 | 3.3071 | 9 OLUSHOLA ADESHINA | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021051344 | METER INSTALLED | 2024-01-30
46 | 1000273854 | 11-BeckleyINJ-T1-Agbe road-OLUDEGUN HVDS 1 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 60020122164 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6575 | 3.3067 | 2 OLUDEGUN | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021051162 | METER INSTALLED | 2024-01-30
47 | 1000274404 | 11-BeckleyINJ-T1-Agbe road-MOSES EMEYA HVDS 4 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201512008307 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6509 | 3.3081 | 9 MOSES EMEYA STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021052331 | METER INSTALLED | 2024-01-30
48 | 1000274606 | 11-BeckleyINJ-T1-Agbe road-SANTOS HVDS 10 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201508003746 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6511 | 3.3043 | 7 SANTOS | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021052987 | METER INSTALLED | 2024-01-30
49 | 1000274407 | 11-BeckleyINJ-T1-Agbe road-MOSES EMEYA HVDS 2 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 60021052447 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6523 | 3.3091 | 12 MOSES EMEYA STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021051966 | METER INSTALLED | 2024-01-30
50 | 1000976030 | 11-OgbaINJ-T1-Ijaye-HVDS (KEKE)-BLK 87 SSS | Band B | IKEJA | OGBA | OGBA | 11-OgbaINJ-T1-Ijaye | PUBLIC | POLE MOUNTED | Metered | 201505002492 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6293 | 3.3281 | IJAYE HOUSING ESTATE AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021050478 | METER INSTALLED | 2024-01-30
51 | 1000288050 | 11-OgbaINJ-T1-Ijaye-PYTHAGORAS HVDS OBA OGUNJI | Band B | IKEJA | OGBA | OGBA | 11-OgbaINJ-T1-Ijaye | PUBLIC | POLE MOUNTED | Metered | 201508006351 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6275 | 3.3338 | OBA OGUNJI ROAD, AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021051744 | METER INSTALLED | 2024-01-30
52 | 1000281749 | 11-Oke IraINJ-T2-Kayode-31 ALH SARU HVDS 25KVA | Band B | IKEJA | OGBA | OGBA | 11-Oke IraINJ-T2-Kayode | PUBLIC | POLE MOUNTED | Metered | 201508006824 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6297 | 3.3408 | ALH. UMAR SARO ST. IFAKO IJAIYE ROAD. | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021052320 | METER INSTALLED | 2024-01-26
53 | 1000281334 | 11-Oke IraINJ-T2-Kayode-NO 6 IJAIYE ROAD HVDS BY MANSARD | Band B | IKEJA | OGBA | OGBA | 11-Oke IraINJ-T2-Kayode | PUBLIC | POLE MOUNTED | Metered | 60020122256 | FAULTY | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6292 | 3.3377 | IJAIYE ROAD, BY AXA MANSARD, OGBA LAGOS | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021052087 | METER INSTALLED | 2024-01-26
54 | 1000260709 | 11-Oke IraINJ-T2-Kayode-BLK 22 HVDS (OPP AY HOTEL) | Band B | IKEJA | OGBA | OGBA | 11-Oke IraINJ-T2-Kayode | PUBLIC | POLE MOUNTED | Metered | 60020122246 | FAULTY | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6311 | 3.3458 | BLK 22 LAGOS STATE STAFF QUARTERS, OPP AY HOTEL, OFF WEMCO ROAD | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021052137 | METER INSTALLED | 2024-01-26
55 | 1002527924 | 11-Oke IraINJ-T2-Kayode-4 GABOL-HVDS(IJAIYE ROAD) | Band B | IKEJA | OGBA | OGBA | 11-Oke IraINJ-T2-Kayode | PUBLIC | POLE MOUNTED | Metered | 60019060896 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6274 | 3.3367 | GABOL SHOPPING PLAZA, 2 IJAIYE ROAD, OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021050543 | METER INSTALLED | 2024-01-26
56 | 1000283462 | 11-Oke IraINJ-T2-Kayode-BLK 14 OLADELE KADIRI | Band B | IKEJA | OGBA | OGBA | 11-Oke IraINJ-T2-Kayode | PUBLIC | POLE MOUNTED | Metered | 201508005846 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6305 | 3.3446 | 14 OLADELE KADIRI CLOSE, OFF NOB OLUWA STREET. LSDPC ESTATE (PHAZE 2) | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021052341 | METER INSTALLED | 2024-01-26
57 | 1000975599 | 11-AgegeINJ-T3-Oyemekun-2A OWONIKOKO CLOSE | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508007465 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6435 | 3.3295 | OSHUNKEYE STREET OFF OWONIKOKO STREET OFF COLLEGE ROAD, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021052956 | METER INSTALLED | 2024-01-31
58 | 1000281557 | 11-AgegeINJ-T3-Oyemekun-BILEWU OSHOFA CRESCENT | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 60020122488 | FAULTY | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6367 | 3.3275 | BILEWU OSHOFA STREET, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021050303 | METER INSTALLED | 2024-01-31
59 | 1000281479 | 11-AgegeINJ-T3-Oyemekun-4 PRATT ATANDA CLOSE | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508006423 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6418 | 3.3282 | ATANDA PRATT CLOSE, OFF ADEKOYA STREET, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021052480 | METER INSTALLED | 2024-01-31
60 | 1000262756 | 11-AgegeINJ-T3-Oyemekun-6 OGUNBORE STREET | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508005709 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6369 | 3.327 | OGUNBORE STREET, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021051535 | METER INSTALLED | 2024-01-31
61 | 1000262309 | 11-AgegeINJ-T3-Oyemekun-8 AYEDOGBON CLOSE | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508007459 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6431 | 3.3297 | AYEDOGBON CLOSE OFF COLLEGE ROAD, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021051365 | METER INSTALLED | 2024-01-31
62 | 1001602044 | 11-AgegeINJ-T3-Oyemekun-11 OMOAKIN STREET | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 60016111989 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6385 | 3.3304 | OMOAKIN STREET, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021050432 | METER INSTALLED | 2024-01-31
63 | 1000281564 | 11-AgegeINJ-T3-Oyemekun-29 GBAGBA CRESCENT | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508006286 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6377 | 3.3305 | GBAGBA CRESENT IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021051609 | METER INSTALLED | 2024-01-31
64 | 1002995492 | 11-AgegeINJ-T3-Oyemekun-38 AJIBODU | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 60012110009 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.647 | 3.33 | AJIBODU STREET OFF COLLEGE ROAD, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021050477 | METER INSTALLED | 2024-01-31
65 | 1000255414 | 11-AgegeINJ-T3-Oyemekun-11 AJIBODU STREET | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508005589 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6456 | 3.3288 | AJIBODU STREET OFF COLLEGE ROAD, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021052896 | METER INSTALLED | 2024-01-31
66 | 1000254378 | 11-AgegeINJ-T3-Oyemekun-32 HDVS ADEKOYE STREET | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508005271 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6397 | 3.3249 | ADEKOYA STREET OFF COLLEGE ROAD, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021050341 | METER INSTALLED | 2024-01-31
67 | 1000260446 | 11-AgegeINJ-T3-Oyemekun-6 ADEOLA AVENUE | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508004578 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6442 | 3.3288 | 10B,ADEOLA AVENUE OFF COLLEGE ROAD, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021052826 | METER INSTALLED | 2024-01-31
68 | 1002057055 | 11-AgegeINJ-T3-Oyemekun-15 HARMONY CLOSE | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508007405 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.65 | 3.329 | HARMONY CLOSE, HARMONY ESTATE, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021050384 | METER INSTALLED | 2024-01-31
69 | 1000280388 | 11-AgegeINJ-T3-Oyemekun-2, BELLO ADOGIE STREET | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508006152 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.65 | 3.3313 | BELLO ADOGIE CLOSE, HARMONY ESTATE, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021051375 | METER INSTALLED | 2024-01-31
70 | 1000255451 | 11-AgegeINJ-T3-Oyemekun-4 ADELEKE ODUNUGA CLOSE | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508005587 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6489 | 3.3298 | ADELEKE ODUNUGA CLOSE, HARMONY ESTATE, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021050185 | METER INSTALLED | 2024-01-31
71 | 1003580530 | 11-IjegunINJ-T2-Isheri Oshun-212 & 213 TAYLOR JUNCTION | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Isheri Oshun | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5149 | 3.2655 | TAYLOR JUNCTION | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021051441 | METER INSTALLED | 2024-02-12
72 | 1003580968 | 11-IjegunINJ-T1-Okerube-319 & 310 MOMODU DADA STREET | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T1-Okerube | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5197 | 3.257 | MOMODU DADA STREET IJEGUN | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050547 | METER INSTALLED | 2024-02-12
73 | 1003580804 | 11-IjegunINJ-T1-Okerube-186 & 187 OLU AKINBO STREET | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T1-Okerube | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5192 | 3.2541 | OLU AKINBO STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050689 | METER INSTALLED | 2024-02-12
74 | 1003580802 | 11-IjegunINJ-T1-Okerube-161 & 162 MOJISOLA ALARAPINNI STREET | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T1-Okerube | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5193 | 3.2533 | MOJISOLA ALARAPINNI STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050550 | METER INSTALLED | 2024-02-12
75 | 1003580994 | 11-IjegunINJ-T1-Okerube-69 & 70 ALABATA STREET | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T1-Okerube | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5177 | 3.2494 | ALABATA STREET IJEGUN | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050953 | METER INSTALLED | 2024-02-12
76 | 1003580536 | 11-IjegunINJ-T2-Pipeline-319 & 310 ANTHONY ABUBA | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Pipeline | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5169 | 3.2591 | ANTHONY ABUBA | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050426 | METER INSTALLED | 2024-02-12
77 | 1003808402 | 11-Ilupeju BypassINJ-T1-Industrial-AGBOLAHAN KEHINDE | Band A | SHOMOLU | ILUPEJU | ILUPEJU MEGA | 11-Ilupeju BypassINJ-T1-Industrial | PUBLIC | POLE MOUNTED | Metered | 60008400274 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5464 | 3.3594 | 11, TAIWO KOYA STREET, ILUPEJU | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021050083 | METER INSTALLED | 2024-02-12
78 | 1001616902 | 11-OguduINJ-T3-Kola Adeshina-​ALHAJA ABASS 1 A | Band B | SHOMOLU | OGUDU | ANTHONY MEGA | 11-OguduINJ-T3-Kola Adeshina | PUBLIC | POLE MOUNTED | Metered | 60016111682 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5712 | 3.3928 | 31 ABUDU STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021052068 | METER INSTALLED | 2024-02-12
79 | 1001959902 | 11-OguduINJ-T3-Kola Adeshina-ALHAJI ABASS 1C | Band B | SHOMOLU | OGUDU | ANTHONY MEGA | 11-OguduINJ-T3-Kola Adeshina | PUBLIC | POLE MOUNTED | Metered | 60019060822 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5733 | 3.3928 | 16 T RAMAT CRESCENT | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021050103 | METER INSTALLED | 2024-02-12
80 | 1002112445 | 11-OguduINJ-T2-Alapere-1 TONY OMOREGIE CSP | Band B | SHOMOLU | OGUDU | ANTHONY MEGA | 11-OguduINJ-T2-Alapere | PUBLIC | POLE MOUNTED | Metered | 60019060726 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5742 | 3.4044 | TONY OMOREGIE CLOSE | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021050461 | METER INSTALLED | 2024-02-12
81 | 1003072572 | 11-OguduINJ-T3-Balogun-5 CHURCH STREET CSP | Band C | SHOMOLU | OWORO | OWOROSHONKI MEGA | 11-OguduINJ-T3-Balogun | PUBLIC | POLE MOUNTED | Metered | 60015052441 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.546 | 3.402 | 5 CHURCH STREET , OWORO, LAGOS | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021050545 | METER INSTALLED | 2024-02-24
82 | 1000265920 | 11-Oke IraINJ-T1-Ayo Alabi-OLA STREET 11 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508006483 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.651 | 3.3435 | OLA STREET OKEIRA OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021051879 | METER INSTALLED | 2024-03-04
83 | 1000265931 | 11-Oke IraINJ-T1-Ayo Alabi-DAPSON 1 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 60020122183 | FAULTY | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6516 | 3.3472 | NO 1,DAPSON STREET OFF AYO-ALABI STREET. | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021050251 | METER INSTALLED | 2024-03-04
84 | 1000266493 | 11-Oke IraINJ-T1-Ayo Alabi-AKINTOYE CL 9 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508007195 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6512 | 3.3441 | NO 7,AKINTOYE CLOSE OFF AYO-ALABI STREET OGBA. | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021051286 | METER INSTALLED | 2024-03-04
85 | 1000268243 | 11-Oke IraINJ-T1-Ayo Alabi-WAHAB FOLORUNSHO HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508004479 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6496 | 3.3472 | NO 6,WAHAB FOLORUSHO STREET OFF AYO-ALABI STREET OGBA. | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021051924 | METER INSTALLED | 2024-03-04
86 | 1000268247 | 11-Oke IraINJ-T1-Ayo Alabi-SHOFIDIYA CL 1 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508006893 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6505 | 3.3463 | NO 1,SHOFIDIYA CLOSE OFF AYO-ALABI STREET OGBA. | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021051618 | METER INSTALLED | 2024-03-04
87 | 1000270973 | 11-Oke IraINJ-T1-Ayo Alabi-J SHONOLA 18 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508004373 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6474 | 3.3434 | NO 18,JACOB SONOLA STREET OFF AYO-ALABI STREET OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021051428 | METER INSTALLED | 2024-03-04
88 | 1000280399 | 11-Oke IraINJ-T1-Ayo Alabi-SUNMONU 11 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508006382 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6468 | 3.3481 | NO 11,SUMONU STREET OFF AYO-ALABI STREET OGBA. | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021050494 | METER INSTALLED | 2024-03-04
89 | 1000280634 | 11-Oke IraINJ-T1-Ayo Alabi-KAYODE JOSEPH 13 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508005752 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6552 | 3.3507 | KAYODE JOSEPH STREET OKEIRA OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021052701 | METER INSTALLED | 2024-03-04
90 | 1000280939 | 11-Oke IraINJ-T1-Ayo Alabi-DELE AYEDUN HVDS 3 | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508004379 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.651 | 3.3449 | NO 14,DELEAYEDU CLOSE OFF AYO-ALABI STREET OGBA. | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021050664 | METER INSTALLED | 2024-03-04
91 | 1003019078 | 11-Oke IraINJ-T1-Ayo Alabi-OLADIPO BANJO 21 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508006291 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6501 | 3.3424 | OLADIPO BANJO STREET OKEIRA OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021051141 | METER INSTALLED | 2024-03-04
92 | 1000280619 | 11-Oke IraINJ-T1-Ayo Alabi-POWERLINE 15A HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508005667 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6535 | 3.3494 | POWERLINE STREET, OKEIRA OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021050840 | METER INSTALLED | 2024-03-04
93 | 1000267831 | 11-Oke IraINJ-T1-Ayo Alabi-OLANIPEKUN 5 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508004482 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6486 | 3.3464 | NO 11,OLANIPEKU AVENUE OFF AYO-ALABI STREET OGBA. | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021052605 | METER INSTALLED | 2024-03-04
94 | 1000280644 | 11-Oke IraINJ-T1-Ayo Alabi-CELESTIAL AVENUE 5 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 60020122446 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6537 | 3.3499 | CELESTIAL AVENUE OKEIRA OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021050302 | METER INSTALLED | 2024-03-04
95 | 1000262351 | 11-AgegeINJ-T3-Oyemekun-17 ADEEKO STREET | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | METERED | 201508004698 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6435 | 3.3303 | 17,ADEEKO STREET OFF COLLEGE ROAD, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021052017 | METER INSTALLED | 2024-05-02
96 | 1000281897 | 11-AgegeINJ-T3-Oyemekun-10 OGUNBORE STR | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | METERED EST. | 201508006279 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6372 | 3.3272 | OGUNBORE STREET, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021052744 | METER INSTALLED | 2024-05-02
97 | 1000255876 | 11-AgegeINJ-T3-Oyemekun-15 ADEOLA AVENUE | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | METERED | 201508004576 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.645 | 3.3297 | 15,ADEOLA AVENUE OFF COLLEGE ROAD, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021052268 | METER INSTALLED | 2024-05-02
98 | 1000975590 | 11-ObawoleINJ-T1-Youdeowei-26 FELIX CR HVDS | Band A | ABULE EGBA | IJU | IJU | 11-ObawoleINJ-T1-Youdeowei | PUBLIC | POLE MOUNTED | METERED EST. | 201508007041 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6588 | 3.3299 | 26 FELIX CRESCENT OFF OLD AKUTE ROAD | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021052506 | METER INSTALLED | 2024-07-02
99 | 1003143924 | 11-ObawoleINJ-T1-Youdeowei-11 AWOBONA HVDS | Band A | ABULE EGBA | IJU | IJU | 11-ObawoleINJ-T1-Youdeowei | PUBLIC | POLE MOUNTED | METERED EST. | 60019060835 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6651 | 3.3274 | 11,AWOBONA STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021052054 | METER INSTALLED | 2024-07-02
100 | 1003797028 | 11-AlimoshoINJ-T8-Alimosho-6, BOUNDARY ROAD | Band A | AKOWONJO | EGBEDA | EGBEDA | 11-AlimoshoINJ-T8-Alimosho | PUBLIC | POLE MOUNTED | METERED | 60020122410 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5994 | 3.31 | LAJO KROAD | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021052400 | METER INSTALLED | 2024-07-04
101 | 1002527415 | 11-AlimoshoINJ-T8-Alimosho-4 OLAIYA CLOSE WILLIAM ESTATE | Band A | AKOWONJO | EGBEDA | EGBEDA | 11-AlimoshoINJ-T8-Alimosho | PUBLIC | POLE MOUNTED | METERED | 60019060567 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6072 | 3.3089 | OLAIYA CLOSE WILLIAM LAYOUT | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021051643 | METER INSTALLED | 2024-07-04
102 | 0101346682 | JAWURA ENVIROMENTAL SERVICE |  | IKEJA | PTC | PTC | 11-New AlausaINJ-T6-Awolowo |  |  |  | Complete Installation |  |  | 50 |  | Whole current meter |  |  |  |  | 130, AWOLOWO WAY BALOGUN BUS STOP, IKEJA |  | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050797 | METER INSTALLED | 2024-07-16
103 | 0102776194 | LAGOS STATE STREET LIGHT |  | SHOMOLU | OWOROSHONKI MEGA | OWOROSHONKI MEGA | 11-OguduINJ-T3-Soluyi |  |  |  | Complete Installation |  |  | 50 |  | Whole current meter |  |  | 6.5639 | 3.3847 | ESTAPORT AVENUE, SOLUYI ROAD GBAGADA LAGOS |  | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021052779 | METER INSTALLED | 2024-07-16
104 | 0100070739 | ILUPEJU INJECTION STATION |  | SHOMOLU | ILUPEJU | ILUPEJU | 33-IlupejuTCN-ILUPEJU BY-PASS |  | #NAME? | #NAME? | Complete Installation |  |  | 50 | [6 empty] | P H C N OFFICE |  | WC meter to be installed | WC meter to be installed | All solution | 60021051071 | METER INSTALLED | 2024-07-16
105 | 1004048968 | 11-OjoduINJ-T2-River Valley-ABASIAKARA |  | IKEJA | OJODU | OJODU | 11-OjoduINJ-T2-River Valley |  | POLE MOUNTED | METERED | 60020122191 | FUNCTIONAL | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6408 | 3.372 | OJODU ISS, ISHERI ROAD OJODU BERGER |  | WC meter to be installed | WC meter to be installed | DEMOL | 60021052328 | METER INSTALLED
106 | 1001888404 | 11-OdogunyanINJ-T2-Odokekere-POLE 351A/351B KENNY JULIUS STR |  | IKORODU | ODOGUNYAN | ODOGUNYAN | 11-OdogunyanINJ-T2-Odokekere |  | POLE MOUNTED | METERED | 60019060777 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6876 | 3.5222 | OMO ONILE AREA AREA HVDS POLE MOUNTED |  | WC meter to be installed | WC meter to be installed | DEMOL | 60021052670 | METER INSTALLED
107 | 1001596985 | 11-IjedeINJ-T1-Gberibe-NIPP HVDS POLE 598 A&B | Band D | IKORODU | IJEDE | IJEDE | 11-IjedeINJ-T1-Gberibe-NIPP HVDS | [6 empty] | 50 |  |  |  |  | 6.594 | 3.5879 | OLUFUNMILAYO FADUGBAGBE STREET, OKE-ELETU IJEDE ROAD IKORODU |  | WC meter to be installed | WC meter to be installed | MAYFAK | 60021051745 | METER INSTALLED | 2024-07-26
Note on C38: Energy Management: The feeder is Nathan but the DT feeding EKO is Oke Suna DT 500

## LVMD DATA ANALYSIS (hidden)
Row Labels | Count of METER NO
ADERALPH | 9
All solution | 3
DEMOL | 7
mayfak | 5
TEE N BEE | 3
(blank)
Grand Total | 27

## PROJECT 643 LVMD REPORT
S/N | CIS DT Numbers | New Unique DT Nomenclature | BU | UT | New UT Name | Feeder Name | Ownership | Installation Position | Acc Platform | Acc TYPE (PRE-PAID/POST-PAID) | Metering Status | Meter Number | Meter Functionality Status | Meter Type | Capacity | Meter Ratings | Connection Status | Commissioning Status | Maintenance Status | Disconnection Status | Coordinates (LAT) | Coordinates (LONG) | Addresses | Project | SBC | SBC PHONE NO | METER NO | INSTALLATION STATUS | INSTALLATION DATE | REMARK
1 | 1006025016 | 11-Oke AfaINJ-T2-Ilamose-TUNDE GANIYU | OSHODI | OKE-AFA | OKE-AFA | 11-Oke AfaINJ-T2-Ilamose | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.536318 | 3.310691 | ALH GANIYU STREET OKE AFA | PROJECT 643 | ADERALPH | 8151528316 | 60022033785 | INSTALLED | 2023-11-15
2 | 1006025201 | 11-IgandoINJ-T1-Egan-BENSON ADU 2 | OSHODI | IGANDO | IGANDO | 11-IgandoINJ-T1-Egan | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.546 | 3.2189 | ADEOLA OLAWALE ST. ISUTI RD, IGANDO. | PROJECT 643 | ADERALPH | 8151528316 | 60022032978 | INSTALLED | 2023-11-15
3 | 1006025202 | 33-EjigboTCN-IJEGUN-CHURCH GATE | OSHODI | IJEGUN | IJEGUN | 33-EjigboTCN-IJEGUN | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5022 | 3.2578 | ALONG IJE-ODODO IJEGUN. | PROJECT 643 | ADERALPH | 8151528316 | 60022033350 | INSTALLED | 2023-11-15 | REPLACEMENT OF BURNT METER UNDER PROJECT 843 060022031296
4 | 1003953410 | 33-EgbinTCN-OKE ELETU-ABATA CDA | IKORODU | IJEDE | IJEDE | 33-EgbinTCN-OKE ELETU | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | Gap | 60021080305 | N/A | MOJEC | 500 | 800/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.604 | 3.6395 | OKE ELETU, IJEDE | PROJECT 643 | DEMOL | 09021887242 | 60022033502 | INSTALLED | 2023-11-21
5 | 1006025018 | 11-AgegeINJ-T1-Oko Oba-BAMGBOYE 2 | ABULE EGBA | FAGBA | FAGBA | 11-AgegeINJ--T1-Oko-Oba | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6595 | 3.319836 | AMUSAN JUNCTION, OFF OLABODE STREET, BAMGBOYE AREA | PROJECT 643 | TEE N BEE | 8074952106 | 60022033824 | INSTALLED | 2023-11-26
6 | 1006024201 | 11-EpeINJ-T1-Township-OBA ANIMASHAUN DT | IKORODU | EPE | EPE | 11-EpeINJ-T1-Township | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5848 | 3.9546 | Along Oba Animashaun way, Epe | PROJECT 643 | DEMOL | 09021887242 | 60022031679 | INSTALLED | 2023-11-25
7 | 1006025021 | 33-IkoroduTCN-AGBOWA-HILLTOP NEWTOWN CDA | IKORODU | EPE | EPE | 33-IkoroduTCN-AGBOWA | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6031 | 3.9776 | KULANLA ROAD, OFF ADERIBIGBE STREET, OFF EPE ITOKIN ROAD, EPE | PROJECT 643 | DEMOL | 09021887242 | 60022033712 | INSTALLED | 2023-11-25
8 | 1001605934 | 11-PTCINJ-T2-Medical-OSUNDAIRO | IKEJA | PTC | PTC | 11-PTCINJ-T2-Medical | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5948 | 3.3394 | SOMOYE ST. OFF MEDICAL ROAD ROAD COMPUTER VILLAGE IKEJA | PROJECT 643 | All solution | 9098079569 | 60022033611 | INSTALLED | 2023-12-01
9 | 1006025601 | 11-IgandoINJ-T1-New Igando-IGANDO NEW TOWN CDA | OSHODI | IGANDO | IGANDO | 11-IgandoINJ-T1-New Igando | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | UNMETERED | NA | N/A | N/A | 300 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.57 | 3.2486 | AT ADESOLARIN STREET NEW IGANDO TOWN IGANDO. | PROJECT 643 | All solution | 9098079569 | 60022033396 | INSTALLED | 2023-12-16
10 | 1006025017 | 11-BolorunpeluINJ-T1-Idimu-AGBOGUNLERI 2 | OSHODI | IDIMU | IDIMU | 11-BolorunpeluINJ-T1-Idimu | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5718 | 3.287 | AGBOGUNLERI STREET IDIMU BUS-STOP | PROJECT 643 | All solution | 9098079569 | 60022033501 | INSTALLED | 2023-12-16
11 | 1006026401 | 11-AbesanINJ-T1-Ipaja-IFESOWAPO IKOLA ILUMO | AKOWONJO | IPAJA | IPAJA | 11-AbesanINJ-T1-Ipaja | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6211 | 3.254 | At Ifesowapo community off Ikola Road, Akowonjo | PROJECT 643 | ADERALPH | 8151528316 | 60022031176 | INSTALLED | 2023-12-18
12 | 1006025404 | 33-OdogunyanTCN-AGBEDE-GOD FIRST CDA | IKORODU | ODOGUNYAN | ODOGUNYAN | 33-OdogunyanTCN-AGBEDE | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | UNMETERED | NA | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6975 | 3.4605 | At Elepete, off Agric, Ikorodu | PROJECT 643 | DEMOL | 09021887242 | 60022033622 | INSTALLED | 2023-12-26
13 | 1006025403 | 11-IgbogboINJ-T1-Ofin-AyangaAdeIgbopa CDA | IKORODU | IGBOGBO | IGBOGBO | 11-IgbogboINJ-T1-Ofin | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | UNMETERED | NA | N/A | N/A | 300 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.546 | 3.5206 | At Igbopa Community, off Oreta road, Igbogbo Ikorodu | PROJECT 643 | DEMOL | 09021887242 | 60022032521 | INSTALLED | 2023-12-26
14 | 1006010401 | 33-IkoroduTCN-AGBOWA-GOD IS LOVE CDA | IKORODU | EPE | EPE | 33-IkoroduTCN-AGBOWA | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6636 | 3.6292 | At Majodo Phase II along Emuren, Ikorodu | PROJECT 643 | DEMOL | 09021887242 | 60022032842 | INSTALLED | 2023-12-26
15 | 1006026601 | 11-OgbaINJ-T1-Ijaye-LSDPC CASTLE ESTATE | IKEJA | OGBA | OGBA | 11-OgbaINJ-T1-Ijaye | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6272 | 3.3302 | LSDPC MEDIUM HOUSING ESTATE, PHASE 1, AGEGE STADIUM ROAD. | PROJECT 643 | ADERALPH | 8151528316 | 60022033029 | INSTALLED | 2024-01-19
16 | 1006027001 | 33-IkoroduTCN-IGBOGBO-MUSAMOT ABENI FKC CDA | IKORODU | IJEDE | IJEDE | 33-IkoroduTCN-IGBOGBO | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6081 | 3.5732 | MUSAMOT ABENI STREET, GINTI, FKC, ELEPE, IKORODU | PROJECT 643 | mayfak | 9050329971 | 60022033795 | INSTALLED | 2024-01-23
17 | 1006028401 | 33-IkoroduTCN-IJEDE-PROGRESSIVE CDA 2 | IKORODU | IJEDE | IJEDE | 33-IkoroduTCN-IJEDE | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6299 | 3.5819 | PROGRESSIVE CDA 2 | PROJECT 643 | mayfak | 9050329971 | 60022033238 | INSTALLED | 2024-01-23
18 | 1006025823 | 11-ShashaINJ-T1-Foursquare-IMALA ONA ARA | AKOWONJO | ABULE-ODU | ABULE-ODU | 11-ShashaINJ-T1-Foursquare | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5747 | 3.2906 | Located at 8, Yusuf Adeoye street, Idimu Lagos, | PROJECT 643 | mayfak | 9050329971 | 60022032979 | INSTALLED | 2024-01-24
19 | 1006025824 | 11-EkoroINJ--T2-Agbele-AINA AJAYI PHASE2 | AKOWONJO | ABORU | ABORU | 11-EkoroINJ--T2-Agbele | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6365 | 3.2762 | Located at off Meiran Lagos, Resident Association | PROJECT 643 | mayfak | 9050329971 | 60022033079 | INSTALLED | 2024-01-24
20 | 1000279710 | 11-BolorunpeluINJ-T1-Idimu-MADARIKAN | OSHODI | IDIMU | IDIMU | 11-BolorunpeluINJ-T1-Idimu | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | METERED | 60017112008 | FUNCTIONAL | MOJEC | 500 | 800/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5649 | 3.2719 | MADARIKAN STREET IDIMU IKOTUN | PROJECT 643 | MAYFAK | 9050329971 | 60022031719 | INSTALLED | 2024-01-29
21 | 1002486411 | 11-WasimiINJ-T2-Wasimi-S0HUKURA YAM MARKET | SHOMOLU | IKOSI | MAGODO MEGA | 11-WasimiINJ-T2-Wasimi | PRIVATE | GROUND MOUNTED | CIS | N/A | METERED | N/A | N/A | N/A | 500 | 800/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6088 | 3.3908 | AT MILE 12, KETU, LAGOS | PROJECT 643 | TEE N BEE | 8074952106 | 60022032427 | INSTALLED | 2024-01-25
22 | 1005118902 | 33-OdogunyanTCN-FAKALE MAYA-IFESOWAPO AJEBO | IKORODU | EPE | EPE | 33-OdogunyanTCN-FAKALE MAYA | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.7087 | 3.5651 | AJEBO JUNCTION FAKALE, OGUN STATE | PROJECT 643 | TEE N BEE | 8074952106 | 60022032604 | INSTALLED | 2024-01-28
23 | 1006025822 | 11-New AlausaINJ-T4-Allen-SOJI ADEPEGBA RESIDENCE | IKEJA | PTC | PTC | 11-New AlausaINJ-T4-Allen | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6041 | 3.3504 | NO. 1 SOJI ADEPEGAB CLOSE, OFF ALLEN AVENUE, IKEJA | PROJECT 643 | ADERALPH | 8151528316 | 60022031841 | INSTALLED | 2024-02-12
24 | 1006028601 | 11-PTCNJ-T8-Olowu-SEIDU DT | IKEJA | PTC | PTC | 11-PTCNJ-T8-Olowu | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5975 | 3.3447 | OFF OLOWU STREET 19 SEIDU AJIPOWU ST ALLEN IKEJA | PROJECT 643 | ADERALPH | 8151528316 | 60022033888 | INSTALLED | 2024-02-12
25 | 1006028001 | 11-OjoduINJ-T1-Ojodu-AKIODE CDA | IKEJA | OBA AKRAN | OBA AKRAN | 11-OjoduINJ-T1-Ojodu | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6383 | 3.3561 | 18 OGUNNUSI RD OJODU LAGOS 101233 LAGOS NIGERIA | PROJECT 643 | ADERALPH | 8151528316 | 60022032529 | INSTALLED | 2024-02-12
26 | 1006029001 | 11-AlajaINJ-T1-Fadayomi-IFELODUN OWODINA | AKOWONJO | AYOBO | AYOBO | 11-AlajaINJ-T1-Fadayomi | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5791 | 3.2427 | 16 Lawan Ode st idimu lagos | PROJECT 643 | ADERALPH | 8151528316 | 60022032913 | INSTALLED | 2024-02-12
27 | 1000257534 | 11-OdogunyanINJ-T1-Centex-ODOGUNYAN INJECTION | IKORODU | ODOGUNYAN | ODOGUNYAN | 11-OdogunyanINJ-T1-Centex | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | METERED | 60017111781 | FUNCTIONAL | MOJEC | 500 | 800/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6797 | 3.5248 | AGODO ALARA | PROJECT 643 | DEMOL | 09021887242 | 060022091220 | INSTALLED | 2024-02-07 | N:B METER INITIALLY INSTALLED IS '060022031725 AND WAS REPLACED WHEN IT DEVELOPED FAULTY WITH NEW METER 060022091220
28 | 1006028801 | 33-OdogunyanTCN-FAKALE MAYA-ITAPARA CDA DT | IKORODU | EPE | EPE | 33-OdogunyanTCN-FAKALE MAYA | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.7021 | 3.5638 |  | PROJECT 643 | TEE N BEE | 09021887242 | 60022032483 | INSTALLED | 2024-02-09
29 | 1006025401 | 11-SaboINJ-T2-Eyita-ALHAJA KADIJA MORAYO CDA | IKORODU | LASUNWON | LASUNWON | 11-SaboINJ-T2-Eyita | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | UNMETERED | NA | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.628 | 3.5003 | At Alhaja Morayo street, Olori Powerline CDA, Eyita Powerline, Ikorodu | PROJECT 643 | DEMOL | 09021887242 | 060022033814 | INSTALLED | 2024-02-24
30 | 1000259268 | 11-SaboINJ-T2-Lagos Road-LOWA | IKORODU | AYANGBUREN | AYANGBUREN | 11-SaboINJ-T2-Lagos Road | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | METERED | 201508003507 | FAULTY | CLOU | 500 | 800/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6233 | 3.4941 | LOWA ST | PROJECT 643 | QUINTEC | 07065706955 | 60022032439 | INSTALLED | 2024-05-17 | PREVIOUSLY INSTALLED BY DEMOL WITH PROJECT 843 METER WITH METER NO 60022031297 on 11/03/2024
31 | 1006030001 | 33-IkoroduTCN-AGBOWA-ALEKE PHASE2 ESTATE | IKORODU | EPE | EPE | 33-IkoroduTCN-AGBOWA | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6631 | 3.6067 |  | PROJECT 643 | TEE N BEE | 09021887242 | 60022033476 | INSTALLED | 2024-03-11
32 | 1000237900 | 11-IjegunINJ-T1-Obalagbe-OKERUBE | OSHODI | IKOTUN | IKOTUN | 11-IjegunINJ-T1-Obalagbe | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | Gap | 201505000761 | N/A | CLOU | 500 | 800/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5279 | 3.2363 | OKERUBE BUSTOP, ABARANJE ROAD IKOTUN | PROJECT 643 | TEE N BEE | 09021887242 | 60022032719 | INSTALLED | 2024-03-11
33 | 1006019602 | 33-OtaTCN-AMJE-AYINLA ADAMS 2 | ABULE EGBA | IJAIYE | IJAIYE | 33-OtaTCN-AMJE | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.675 | 3.2822 | Sherifat Banire, off Taibat Banire street, Ojokoro LCDA, Ifako LGA, Abule Egba BU | PROJECT 643 | MAYFAK | 9050329971 | 60022033104 | INSTALLED | 2024-03-11
34 | 1006029401 | 11-IgbogboINJ-T1-Ofin-UPS STAFF COOPERATIVE ESTATE CDA DT | IKORODU | IGBOGBO | IGBOGBO | 11-IgbogboINJ-T1-Ofin | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.564 | 3.5224 |  | PROJECT 643 | QUINTEC | 07065706955 | 60022033894 | INSTALLED | 2024-05-17 | PREVIOUSLY INSTALLED BY DEMOL WITH PROJECT 843 METER WITH METER NO 60022033796 on 14/03/2024
35 | 1003370522 | 33-EgbinTCN-OKE ELETU-IREAKARI CDA | IKORODU | IJEDE | IJEDE | 33-EgbinTCN-OKE ELETU | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6223 | 3.6509 | IMOTA, IKORODU | PROJECT 643 | DEMOL | 09021887242 | 60022033954 | INSTALLED | 2024-03-24
36 | 1006030201 | 11-OdogunyanINJ-T2-Ita Oluwo-Upright CDA | IKORODU | ODOGUNYAN | ODOGUNYAN | 11-OdogunyanINJ-T2-Ita Oluwo | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.683 | 3.4767 |  | PROJECT 643 | DEMOL | 09021887242 | 60022031664 | INSTALLED | 2024-03-15
37 | 1006030401 | 33-IkoroduTCN-IJEDE-Peace CDA | IKORODU | IJEDE | IJEDE | 33-IkoroduTCN-IJEDE | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5676 | 3.5739 |  | PROJECT 643 | DEMOL | 09021887242 | 60022032843 | INSTALLED | 2024-03-15
38 | 1003953406 | 33-EgbinTCN-OKE ELETU-IGBOPA LONDON PHASE 2 | IKORODU | IJEDE | IJEDE | 33-EgbinTCN-OKE ELETU | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5817 | 3.6081 | IGBOPA LONDON PHASE 2, OKE ELETU, IJEDE | PROJECT 643 | DEMOL | 09021887242 | 60022032924 | INSTALLED | 2024-03-14
39 | 1004872022 | 33-Oke-AroTCN-AKUTE-BEACHLAND | SHOMOLU | OLOWORA | MAGODO MEGA | 33-Oke-AroTCN-AKUTE | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.698 | 3.4365 | GBAYIDE SOMUYIWA | PROJECT 643 | TEE N BEE | 09021887242 | 60022033806 | INSTALLED | 2024-03-16
40 | 1006028201 | 11-BolorunpeluINJ-T3-Governor- PEACE EST IV CDA | OSHODI | IDIMU | IDIMU | 11-BolorunpeluINJ-T3-Governor | PUBLIC | GROUND | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.570989 | 3.257583 | SALVATION ARMY STREET, OFF GOVERNOR ROAD , IKOTUN | PROJECT 643 | TEE N BEE | 09021887242 | 60022032610 | INSTALLED | 2024-03-13
41 | 1006027801 | 11-Ago OkotaINJ-T2-Oke Ogbere-OLANREWAJU 2 | OSHODI | AGO | AGO | 11-Ago OkotaINJ-T2-Oke Ogbere | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5015 | 3.2969 | OLANREWAJU STREET DIVINE ESTATE AGO | PROJECT 643 | TEE N BEE | 09021887242 | 60022033176 | INSTALLED | 2024-03-14
42 | 1006025802 | 33-Oke-AroTCN-AKUTE-IBOKO 2 | ABULE EGBA | AKUTE | AKUTE | 33-Oke-AroTCN-AKUTE | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.663 | 3.3807 | SALAMI STREET, IBOKO, OGUN STATE | PROJECT 643 | MAYFAK | 9050329971 | 60022032426 | INSTALLED | 2024-03-13
43 | 1006019603 | 11-MongoroINJ-T1-New Dopemu-OREMEJI RELIEF DT | AKOWONJO | EGBEDA | EGBEDA | 11-MongoroINJ-T1-New Dopemu | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6046 | 3.3255 | Oremeji, off Onipetesi, Idi Mangoro Ikeja LGA | PROJECT 643 | MAYFAK | 9050329971 | 60022032987 | INSTALLED | 2024-03-12
44 | 1006030601 | 33-EgbinTCN-OKE ELETU-OKEAGBO DT | IKORODU | IJEDE | IJEDE | 33-EgbinTCN-OKE ELETU | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6072 | 3.649 | NA | PROJECT 643 | TEE N BEE | 09021887242 | 60022033584 | INSTALLED | 2024-03-25
45 | 1006025402 | 11-BolorunpeluINJ-T1-Isijola-IREPO 3 | OSHODI | IKOTUN | IKOTUN | 11-BolorunpeluINJ-T1-Isijola | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5495 | 3.2539 | AT 62 OSUMBA STREET IKOTUN | PROJECT 643 | MAYFAK | 9050329971 | 60022033906 | INSTALLED | 2024-03-25
46 | 1006030801 | 33-IkoroduTCN-IPAKODO-LAGOON VIEW ESTATE CDA | IKORODU | IGBOGBO | IGBOGBO | 33-IkoroduTCN-IPAKODO | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5855 | 3.4875 | IPAKODO-LAGOON VIEW ESTATE CDA | PROJECT 643 | DEMOL | 09021887242 | 60022033068 | INSTALLED | 2024-04-08
47 | 1001598531 | 33-IkoroduTCN-AGBOWA-ERERUFU | IKORODU | EPE | EPE | 33-IkoroduTCN-AGBOWA | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | FAULTY | INACTIVE | 6.6453 | 3.8481 | ITOIKIN EPE ROAD ERERUFU | PROJECT 643 | TEE N BEE | 09021887242 | 60022031887 | INSTALLED | 2024-03-27
48 | 1000208427 | 11-ObawoleINJ-T1-Youdeowei-MEDOVILLA | ABULE EGBA | IJU | IJU | 11-ObawoleINJ-T1-Youdeowei | PUBLIC | GROUND | CIS | POST-PAID | Gap | 60016110241 | FAULTY | MOJEC | 100 | 200/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6631 | 3.323 | 215/217 IJU ROAD | LIGHT UP LAGOS | MAYFAK | 9050329971 | 60021080958 | INSTALLED | 2024-04-26
49 | 1006032604 | 11-IlupejuINJ-T4-Ikorodu-OLOLADE BENSON CDA | IKEJA | PTC | PTC | 11-IlupejuINJ-T4-Ikorodu | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5695 | 3.3658 | OLADE BENSON ELEKO, ONIGBOGBO, MARYLAND | PROJECT 643 | ADERALPH | 8151528316 | 60022033522 | INSTALLED | 2024-05-10
50 | 1006032801 | 11-OjoduINJ-T1-Ojodu-OJODU CDA | IKEJA | OJODU | OJODU | 11-OjoduINJ-T1-Ojodu | PUBLIC | GROUND | CIS | POST PAID | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6449 | 3.3652 | ZINSOU OFF AINA STREET, OJODU B/STOP, OJODU | PROJECT 643 | ADERALPH | 8151528316 | 60022032517 | INSTALLED | 2024-05-10
51 | 1006032603 | 11-SecretariatINJ-T1-Lateef Jakande-AKIODE 2 CDA | IKEJA | OJODU | OJODU | 11-SecretariatINJ-T1-Lateef Jakande | PUBLIC | GROUND | CIS | POST PAID | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6373 | 3.3553 | OPPOSITE ZENITH BANK OGUNUSI ROAD OJODU | PROJECT 643 | ADERALPH | 8151528316 | 60022033149 | INSTALLED | 2024-05-10
52 | 1006034001 | 33-AlausaTCN-OPIC-PALMS HAVEN CDA | SHOMOLU | MAGODO MEGA | MAGODO MEGA | 33-AlausaTCN-OPIC | PUBLIC | GROUND | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6426 | 3.398 | PALM HAVEN CDA OPIC | PROJECT 643 | ADERALPH | 8151528316 | 60022032761 | INSTALLED | 2024-05-10
53 | 1006032002 | 33-OdogunyanTCN-AGBEDE-Gloryland Omolaiye CDA | IKORODU | IJEDE | IJEDE | 33-OdogunyanTCN-AGBEDE | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6799 | 3.4862 | At Progressive street, Agbede Transformer, Ikorodu Lagos State | PROJECT 643 | TEE N BEE | 09021887242 | 60022033166 | INSTALLED | 2024-05-15
54 | 1006032001 | 33-EgbinTCN-OKELETU-Igbangbe Phase ll CDA | IKORODU | ODOGUNYAN | ODOGUNYAN | 33-EgbinTCN-OKE ELETU | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5899 | 3.6373 | At Agura Gberigbe Road C/P Bus-stop, Agura Ikorodu Lagos State | PROJECT 643 | TEE N BEE | 09021887242 | 60022031901 | INSTALLED | 2024-05-21
55 | 1006032201 | 33-IkoroduTCN-AGBOWA- OKE SABO CDA | IKORODU | EPE | EPE | 33-IkoroduTCN-AGBOWA | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6711 | 3.6632 |  | PROJECT 643 | TEE N BEE | 09021887242 | 60022033662 | INSTALLED | 2024-05-22
56 | 1006032202 | 33-IkoroduTCN-IJEDE-Igbe-Ogunro Joint CDA | IKORODU | IJEDE | IJEDE | 33-IkoroduTCN-IJEDE | PUBLIC | GROUND | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5702 | 3.5725 |  | PROJECT 643 | TEE N BEE | 09021887242 | 60022033548 | INSTALLED | 2024-05-15
57 | 1006032401 | 33-IkoroduTCN-AGBOWA-Sacred Heart Estate | IKORODU | EPE | EPE | 33-IkoroduTCN-AGBOWA | PUBLIC | GROUND | CIS | N/A | UNMETERED | N/A | N/A | N/A | 200 | 300/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6857 | 3.7115 | Odo Onasa Agbowa Ikosi Epe Ikorodu, Lagos | PROJECT 643 | TEE N BEE | 09021887242 | 60022033730 | INSTALLED | 2024-05-22
58 | 1000005002 | 33-Oke-AroTCN-AKUTE-NANSO AKPAN | SHOMOLU | OLOWORA | MAGODO MEGA | 33-Oke-AroTCN-AKUTE | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6375 | 3.4108 | NANSOAKPAN STREET, ISHERI NORTH ESTATE | PROJECT 643 | QUINTEC | 07065706955 | 60022032909 | INSTALLED | 2024-05-17
59 | 1004499976 | 11-OworoINJ-T1-Ifako-ABUBAKAR ODUTAN LASISI | SHOMOLU | OWORO | OWOROSHONKI MEGA | 11-OworoINJ-T1-Ifako | PUBLIC | POLE MOUNTED | CIS | POST-PAID | Gap | 60012064611 | HEALTHY | MOJEC | 100 | 200/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5549 | 3.3913 | 1 BABALOLA STREET, GBAGADA, OWORO | LIGHT UP LAGOS | MAYFAK | 9050329971 | 60020123655 | INSTALLED | 2024-05-14
60 | 1006032601 | 11-IjegunINJ-T2-Pipeline-HARMONY 2 | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Pipeline | PUBLIC | GROUND MOUNTED | CIS | POST PAID | UNMETERED | N/A | N/A | N/A | 300 | 500/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.4984 | 3.2709 | OFF EKENE UDEH ASIWAJU STRT,FAGBILE PHASE 3 IJEGUN | PROJECT 643 | TEE N BEE | 09021887242 | 60022032713 | INSTALLED | 2024-05-29
61 | 1000229080 | 11-IjegunINJ-T1-Ikotun-WILLIAMS SHOTUNDE | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T1-Ikotun | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | Gap | 201505001838 | N/A | CLOU | 500 | 800/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.542 | 3.2633 | IJEGUN IKOTUN ROAD | PROJECT 643 | QUINTEC | 07065706955 | 60022032782 | INSTALLED | 2024-05-28
62 | 1000254484 | 11-Ilupeju BypassINJ-T1-Bypass-TOWN PLANNING III | SHOMOLU | ILUPEJU | ILUPEJU MEGA | 11-Ilupeju BypassINJ-T1-Bypass | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | METERED | 60016111854 | FUNCTIONAL | MOJEC | 300 | 500/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5567 | 3.3573 | 40/42 TOWN PLANNING | PROJECT 643 | ADERALPH | 8151528316 | 60022033812 | INSTALLED | 2024-05-20
63 | 1006036801 | 11-AmuwoINJ-T2-Jakande 2-AGBEDE 2 | OSHODI | AMUWO | AMUWO | 11-AmuwoINJ-T2-Jakande 2 | PUBLIC | GROUND | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.468 | 3.3011 | PLOT 133 AMUWO ODOFIN BY FESTAC LINK BRIDGE, AMUWO | PROJECT 643 | All solution | 9098079569 | 60022033794 | INSTALLED | 2024-06-23
64 | 1000256860 | 11-IgbobiINJ-T3-Railway-IDERA | SHOMOLU | ILUPEJU | ILUPEJU MEGA | 11-IgbobiINJ-T3-Railway | PUBLIC | GROUND | CIS | POST-PAID | METERED | 201508004228 | FUNCTIONAL | CLOU | 500 | 800/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5356 | 3.3606 | IDERA STREET | PROJECT 643 | All solution | 9098079569 | 60022032420 | INSTALLED | 2024-06-28
65 | 1001612442 | 11-Ilupeju BypassINJ-T1-Industrial-BYE-PASS | SHOMOLU | ILUPEJU | ILUPEJU MEGA | 11-Ilupeju BypassINJ-T1-Industrial | PUBLIC | GROUND | CIS | POST-PAID | METERED | 60016111867 | FUNCTIONAL | MOJEC | 500 | 800/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5455 | 3.3592 | CREATIVE HOUSE ILUPEJU BYPASS | PROJECT 643 | All solution | 9098079569 | 60022032812 | INSTALLED | 2024-06-28
66 | 1006034002 | 11-OjoduINJ-T2-Express-MUYIBAT OYEFUSI 2 | IKEJA | OBA AKRAN | OBA AKRAN | 11-OjoduINJ-T2-Express | PUBLIC | GROUND | CIS | POST-PAID | UNMETERED | #N/A | N/A | N/A | 300 | 500/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6355 | 3.3641 | 15, MUYIBAT OYEFUSI STREET, OMOLE ESTATE PHASE 1 | PROJECT 643 | All solution | 9098079569 | 60022031749 | INSTALLED | 2024-07-04
67 | 1006025801 | 11-OdogunyanINJ-T1-Agodo-ANNEX 2 | IKORODU | LASUNWON | LASUNWON | 11-OdogunyanINJ-T1-Agodo | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | FAULTY | INACTIVE | 6.6501 | 3.5162 | OFF ADEOWO STREET, LASUNWON | PROJECT 643 | All solution | 9098079569 | 60022031706 | INSTALLED | 2024-07-04 | Replacement and Retrieval of Old Meter/'060022031897
68 | 1006034801 | 11-IgbogboINJ-T2-Agunfoye-Union Homes Garden Estate CDA | IKORODU | IGBOGBO | IGBOGBO | 11-IgbogboINJ-T2-Agunfoye | PUBLIC | GROUND | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5762 | 3.5493 | No. 25, Alhaji Semiu White Okunola Street, Ire 1, Igbogbo Baiyeku LCDA. Lagos | PROJECT 643 | MAYFAK | 9050329971 | 60022031798 | INSTALLED | 2024-07-04
69 | 0101315348 | GEORGE TEMITOPE | IKEJA | IKEJA | IKEJA | 11-Adekunle FajuyiINJ-T1-Oduduwa | PUBLIC | N/A | N/A | N/A | Complete Installation | N/A | N/A | N/A | 100 | 200/5A | N/A | N/A | N/A | N/A |  |  | 29D, REMI FANKAYODE STREET, GRA ,IKEJA | PROJECT 643 | vicbonny | +234 806 797 3395 | 060022033356 | INSTALLED | 2024-07-09
70 | 0100348387 | OGUNDERO MAJOR GENERAL | IKEJA | IKEJA | IKEJA | 11-Adekunle FajuyiINJ-T1-Oduduwa | PUBLIC | N/A | N/A | N/A | Complete Installation | N/A | N/A | N/A | 100 | 200/5A | N/A | N/A | N/A | N/A |  |  | 25 ADEKUNLE FAJUYI C 84/P25/25490 G R A IKEJA | PROJECT 643 | vicbonny | +234 806 797 3395 | 060022033857 | INSTALLED | 2024-07-09
71 | 0100928167 | CHIEF OKORONKWO GEOR | IKEJA | IKEJA | IKEJA | 11-Adekunle FajuyiINJ-T1-Isaac John | 300 | N/A | N/A | N/A | Complete Installation | N/A | N/A | N/A | 300 | 500/5A | N/A | N/A | N/A | N/A | 6.5826 | 3.3487 | 1A LADOKE AKINTOLA STREET GRA IKEJA LAGOS | PROJECT 643 | vicbonny | +234 806 797 3395 | 060022032720 | INSTALLED | 2024-07-09
72 | 0100068892 | SMRIDU HOTEL | IKEJA | IKEJA | IKEJA | 11-Adekunle FajuyiINJ-T1-Oduduwa | 200 | N/A | N/A | N/A | Complete Installation | N/A | N/A | N/A | 200 | 500/5A | N/A | N/A | N/A | N/A | 6.5708 | 3.3487 | 39. ADEKUNLE FAJUYI WAY. IKEJA. | PROJECT 643 | vicbonny | +234 806 797 3395 | 060022031672 | INSTALLED | 2024-07-09
73 | 0100068986 | FIDELIS AYEBAE | IKEJA | IKEJA | IKEJA | 11-IlupejuINJ-T4-Ikorodu | 100 | N/A | N/A | N/A | Complete Installation | N/A | N/A | N/A | 100 | 200/5A | N/A | N/A | N/A | N/A | 6.5678 | 3.3654 | 11 IYA OLOYE CRES. ONIGBONGBO MARYLAND LAGOS | PROJECT 643 | vicbonny | +234 806 797 3395 | 060022033456 | INSTALLED | 2024-07-09
74 | 0100068949 | MESSRS.E.I OJEI HOLDING | IKEJA | IKEJA | IKEJA | 11-Adekunle FajuyiINJ-T1-Oduduwa | 200 | N/A | N/A | N/A | Complete Installation | N/A | N/A | N/A | 200 | 500/5A | N/A | N/A | N/A | N/A | 6.5755 | 3.3564 | 11A+11B SASEGBON STR IKEJA G R A | PROJECT 643 | vicbonny | +234 806 797 3395 | 060022033618 | INSTALLED | 2024-07-10
75 | 0102380538 | SEGUN OJU BRIGHT | IKEJA | PTC | PTC | 11-PTCINJ-T1-Opebi | PUBLIC | N/A | N/A | N/A | Complete Installation | N/A | N/A | N/A | 100 | 200/5A | N/A | N/A | N/A | N/A |  |  | 40 TOYIN STREET IKEJA | PROJECT 643 | QUINTEC | 07065706955 | 060022031142 | INSTALLED | 2024-07-11
76 | 0102649326 | IKEJA ELECTRIC - MAGODO MEGA UNDERTAKING | SHOMOLU | MAGODO MEGA | MAGODO MEGA | 11-MagodoINJ-T2-Bashiru | PUBLIC |  |  | N/A | Complete Installation | N/A | N/A | N/A | 100 | 200/5A | N/A | N/A | N/A | N/A |  |  | PLOT 5B JUBILEE ROAD, CMD ROAD, MAGODO, LAGOS. | PROJECT 643 | ADERALPH | 8151528316 | 060022033263 | INSTALLED | 2024-07-11
77 | 0100070101 | YAKUBU A R ALHAJI | SHOMOLU | MAGODO | MAGODO | 11-MagodoINJ-T1-Shangisha | PUBLIC |  |  |  | Complete Installation | N/A | N/A | N/A | 100 | 200/5A | N/A | N/A | N/A | N/A |  |  | 1 JAIYE OYEDOTUN STR | PROJECT 643 | ADERALPH | 8151528316 | 060022031881 | INSTALLED | 2024-07-11
78 | 0101296742 | CONELE ADEBOLA OGUNSOWO | IKEJA | OREGUN | OREGUN | 11-New AlausaINJ-T5-Alausa | PUBLIC |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | Batch 1 | [5 empty] | 6A, KAFI STREET, ALAUSA,OREGUN. | PROJECT 643 | mayfak | 9050329971 | 060022031878 | INSTALLED | 2024-07-13
79 | 0100346185 | ISMAIL ABIODUN OLALEMI | IKEJA | OREGUN | OREGUN | 11-New AlausaINJ-T5-Alausa | PUBLIC |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | Batch 1 | [5 empty] | ISHOLA BELLO STREET ISHOLA BEL | PROJECT 643 | mayfak | 9050329971 | 060022031689 | INSTALLED | 2024-07-13
80 | 0101309234 | KENETH | IKEJA | OREGUN | OREGUN | 11-New AlausaINJ-T6-Ogundana | PUBLIC |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | Batch 1 | [5 empty] | 23, OGUNDANA STREET OFF ALLEN AVENUE | PROJECT 643 | mayfak | 9050329971 | 060022033355 | INSTALLED | 2024-07-13
81 | 0102796155 | KENSIGNTON & KENSGNTON NIG. LT | IKEJA | OREGUN | OREGUN | 11-New AlausaINJ-T6-Ogundana | 200 |  |  |  | Complete Installation |  |  |  | 300 | 500/5A LVMD | Batch 1 | [5 empty] | 35 OGUNDANA STREET OFF ALLEN AVENUE, IKEJA | PROJECT 643 | mayfak | 9050329971 | 060022033601 | INSTALLED | 2024-07-13
82 | 0100068881 | ADNA HOTEL | IKEJA | PTC | PTC | 11-PTCINJ-T3-General Hospital | 200 |  |  |  | Complete Installation |  |  |  | 300 | 500/5A LVMD | Batch 1 |  |  |  | 6.5761 | 3.3454 | 28. BADIPO BATEYE STREET. G R A - IKEJA. LAGOS. | PROJECT 643 | REALLOCATED vicbonny | +234 806 797 3395 | 60022033314 | INSTALLED | 2024-07-13
83 | 0100069019 | VIRGIN ATLANTIC | IKEJA | PTC | PTC | 11-PTCINJ-T3-General Hospital | 500 |  |  |  | Complete Installation |  |  |  | 500 | 800/5A LVMD | Batch 1 |  |  |  | 6.5799 | 3.3426 | 10. MOBOLAJI BANK ANTHONY WAY. IKEJA. LAGOS. | PROJECT 643 | REALLOCATED vicbonny | +234 806 797 3395 | 060022032946 | INSTALLED | 2024-07-13
84 | 0100348793 | EKITI STATE LIASON OFFICE | IKEJA | PTC | PTC | 11-PTCINJ-T3-General Hospital | 100 |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | Batch 1 |  |  |  | 6.5754 | 3.3469 | 81A ODUDUWA CRESCENT GRA IKEJA LAGOS. | PROJECT 643 | REALLOCATED vicbonny | +234 806 797 3395 | 060022031844 | INSTALLED | 2024-07-13
85 | 0101536732 | ADEMIDUN FEMI-MAPADERUN | IKEJA | PTC | PTC | 11-PTCINJ-T3-General Hospital | PUBLIC |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | Batch 1 | [5 empty] | 45,ODUDUWA CRESCENT,IKEJA GRA | PROJECT 643 | REALLOCATED vicbonny | +234 806 797 3395 | 060022033430 | INSTALLED | 2024-07-13
86 | 0102261457 | FEDERAL MIN INTERNAL AFFAI | IKEJA | PTC | PTC | 11-PTCINJ-T3-General Hospital | PUBLIC |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | Batch 1 | [5 empty] | IMMIGRATION DEPT 68/51777 IKEJA | PROJECT 643 | REALLOCATED vicbonny | +234 806 797 3395 | 060022033369 | INSTALLED | 2024-07-13
87 | 0100925854 | BEIJ INN AND SUITES | SHOMOLU | OGUDU | OGUDU | 11-OguduINJ-T1-CAC | 200 |  |  |  | Complete Installation |  |  |  | 300 | 500/5A LVMD | Batch 1 |  |  |  | 6.5787 | 3.3808 | 26 EMMANUEL HIGH STREET | PROJECT 643 | ADERALPH | 8151528316 | 060022033597 | INSTALLED | 2024-07-16
88 | 0101028661 | CHIEF ADEKUNLE ABDUL | SHOMOLU | OGUDU | OGUDU | 11-OguduINJ-T1-Express | 300 |  |  |  | Complete Installation |  |  |  | 300 | 500/5A LVMD | Batch 1 |  |  |  | 6.5755 | 3.3898 | PLT 3 BLK M OGUDU GRA LAGOS | PROJECT 643 | ADERALPH | 8151528316 | 060022032747 | INSTALLED | 2024-07-16
89 | 0100070508 | U A C FOOD (MR BIGGS) | SHOMOLU | OGUDU | OGUDU | 11-OguduINJ-T1-Express | 200 |  |  |  | Complete Installation |  |  |  | 300 | 500/5A LVMD | Batch 1 |  |  |  | 6.577 | 3.3895 | 117 OGUDU ROAD | PROJECT 643 | ADERALPH | 8151528316 | 060022032450 | INSTALLED | 2024-07-16
90 | 0100350372 | JUDE EKWUNIFE | IKEJA | PTC | PTC | 11-New AlausaINJ-T6-Awolowo | 200 |  |  |  | Complete Installation |  |  |  | 300 | 500/5A LVMD | Batch 1 |  |  |  | 6.6023 | 3.3457 | 4. FADEYI ALADURA STREET. OFF ORISHE STREET. IKEJA. | PROJECT 643 | QUINTEC | 07065706955 | 060022032817 | INSTALLED | 2024-07-16
91 | 0100068771 | DOWN TOWN ROYAL HOTEL | IKEJA | PTC | PTC | 11-New AlausaINJ-T6-Awolowo | 100 |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | Batch 1 |  |  |  | 6.605 | 3.3493 | 22. DIPEOLU ST. OFF AWOLOWO WA AIRPORT HOTEL. IKEJA LAGOS. | PROJECT 643 | QUINTEC | 07065706955 | 060020123679 | INSTALLED | 2024-07-16
92 | 0100068953 | DR ABAYOMI FINNIH OLUYO | IKEJA | PTC | PUBLIC | 11-PTCINJ-T3-General Hospital | 100 |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | [6 empty] | 34 ODUDUWA CRESCENT M/NO 80/P200/5/196 G R A IKEJA | PROJECT 643 | welldone |  | 060022032582 | INSTALLED | 2024-07-16
93 | 0100348273 | DANIEL KEHINDE OLABISI | IKEJA | PTC | PUBLIC | 11-PTCINJ-T3-General Hospital | 100 |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | [6 empty] | 91 ODUDUWA CRESCENT 98/P50/000039 GRA | PROJECT 643 | welldone |  | 060022033180 | INSTALLED | 2024-07-16
94 | 1003442556 | 11-OguduINJ-T3-Soluyi-ESTAPORT | SHOMOLU | OWORO | OWOROSHONKI MEGA | 11-OguduINJ-T3-Soluyi | PUBLIC | GROUND | CIS | POST-PAID |  | 60020120209 | FUNCTIONAL | MOJEC | 200 | 300/5a |  |  |  |  | 6.56 | 3.3862 | DOGO MAJEKODUNMI STREET, SOLUYI | PROJECT 643 | mayfak/demol | 09021887242 | 060022031760 | INSTALLED | 2024-07-17
95 | 1000240761 | 11-Adekunle FajuyiINJ-T1-Oduduwa-ODUDUWA WAY III | IKEJA | PTC | PTC | 11-Adekunle FajuyiINJ-T1-Oduduwa | PUBLIC | GROUND | CIS | POST-PAID |  | 201505001066 | FUNCTIONAL | CLOU | 500 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE |  | 6.5714 | 3.3531 | ODUDUWA WAY, IKEJA GRA | PROJECT 643 | All solution | 9098079569 | 60022031661 | INSTALLED | 2024-07-16
96 | 0100702082 | Z FATOKU ESQ | SHOMOLU | ILUPEJU MEGA | ILUPEJU MEGA | 11-IlupejuINJ-T3-Coker | PUBLIC |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | [6 empty] | 1 SERE ST | PROJECT 643 | All solution | 9098079569 | 60022033955 | INSTALLED | 2024-07-17
97 | 1003970428 | 11-New GowonINJ-T1-Olorunadaba-MOBOLAJI AKINSHILO | AKOWONJO | EGBEDA | EGBEDA | 11-New GowonINJ-T1-Olorunadaba | PUBLIC | POLE MOUNTED | CIS | POST-PAID | METERED | 60020120127 | FAULTY | MOJEC | 100 | 200/5 | COMMISSIONED | HEALTHY | ACTIVE |  | 6.6081 | 3.2962 | 2 ONIYIDE CLOSE RANTI ALABI RAJI OBA ALIMOSHO LAGOS STATE | PROJECT 643 | mayfak/demol |  | 060022032670 | INSTALLED | 2024-07-13
98 | 1000163154 | 11-New GowonINJ-T1-Olorunadaba-ADEBUNMI EDUN | AKOWONJO | EGBEDA | EGBEDA | 11-New GowonINJ-T1-Olorunadaba | PUBLIC | GROUND | CIS | POST-PAID | METERED | 60017052599 | FUNCTIONAL | MOJEC | 500 | 800/5 | COMMISSIONED | HEALTHY | ACTIVE |  | 6.6084 | 3.2998 | ADEBUNMI STREET ALIMOSHO LAGOS STATE | PROJECT 643 | mayfak/demol |  | 060022032766 | INSTALLED | 2024-07-13
99 | 1006038005 | 33-OdogunyanTCN-FAKALE MAYA-PROMISED LAND CDA 2 | IKORODU | ODOGUNYAN | ODOGUNYAN | 33-OdogunyanTCN-FAKALE MAYA | PUBLIC | GROUND | CIS | POST-PAID | UNMETERED | N/A | N/A | N/A | 500 | 800/5 | NOT COMMISSIONED | HEALTHY | INACTIVE |  | 6.7237 | 3.5393 | EVERLASTING AREA CDC, OGIJO SAGAMU SOUTH, OGUN STATE | PROJECT 643 | DEMOL |  | 60022032409 | INSTALLED | 2024-07-16
100 | 1006038004 | 33-IkoroduTCN-IPAKODO- ELEPE ROYAL ESTATE CDA | IKORODU | IGBOGBO | IGBOGBO | 33-IkoroduTCN-IPAKODO | PUBLIC | GROUND | CIS | POST-PAID | UNMETERED | N/A | N/A | N/A | 500 | 800/5 | NOT COMMISSIONED | HEALTHY | INACTIVE |  | 6.6061 | 3.4998 | NO. 1, SHIFAD SHITTA STREET, ELEPE ROYAL ESTATE, AGA, IKORODU, LAGOS STATE | PROJECT 643 | DEMOL |  | 60022032945 | INSTALLED | 2024-07-16
101 | 0100346373 | BOLA OGUNSANWO | IKEJA | OREGUN | OREGUN | 11-New AlausaINJ-T5-Alausa | PUBLIC |  |  |  | Complete Installation | N/A | Batch 1 | mayfak | 100 | 200/5A LVMD | [6 empty] | 6 KAFFI STR | PROJECT 643 | mayfak |  | 060022032669 | INSTALLED | 2024-07-17
102 | 1000238330 | 11-ShashaINJ-T1-Coker Estate-KINGS COURT 2 | AKOWONJO | ABULE-ODU | ABULE-ODU | 11-ShashaINJ-T1-Coker Estate | PUBLIC | GROUND | CIS | POST-PAID | METERED | 201505001278 | FUNCTIONAL | CLOU | 500 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE |  | 6.5822 | 3.3076 | KINGS COURT OFF JAIYE OBA ROAD SHASHA LAGOS STATE | PROJECT 643 | mayfak/demol |  | 060022033161 | INSTALLED | 2024-07-17 | meter was collected from aderalph / meter installed
103 | 1002050818 | 11-PTCINJ-T3-Oba Akinjobi-BCI GLOBAL PROPERTIE | IKEJA | PTC | PTC | 11-PTCINJ-T3-Oba Akinjobi | PUBLIC | GROUND | CIS | POST-PAID | METERED | 60017111280 | FUNCTIONAL | MOJEC | 200 | 300/5 | COMMISSIONED | HEALTHY | ACTIVE |  | 6.5809 | 3.3543 | OBA DOSUNMU STREET GRA IKEJA | PROJECT 643 | All solution |  | 60022032523 | INSTALLED | 2024-07-19
104 | 1000189155 | 11-New AlausaINJ-T6-Awolowo-OBOKUN | IKEJA | PTC | PTC | 11-New AlausaINJ-T6-Awolowo | PUBLIC | GROUND | CIS | POST-PAID | METERED | 201505000842 | FUNCTIONAL | CLOU | 300 | 500/5 | COMMISSIONED | HEALTHY | ACTIVE |  | 6.6055 | 3.3485 | OBOKUN CLOSE IKEJA | PROJECT 643 | All solution |  | 60022033240 | INSTALLED | 2024-07-19
105 | 1000975518 | 11-OjoduINJ-T1-Ojodu-OJODU ESTATE 1 | IKEJA | OJODU | OJODU | 11-OjoduINJ-T1-Ojodu | PUBLIC | GROUND | CIS | POST-PAID | METERED | 201505000850 | FUNCTIONAL | CLOU | 500 | 800/5 | COMMISSIONED | HEALTHY | ACTIVE |  | 6.646 | 3.365 | SOFOLA STREET OFF OGUNLUSI ROAD OJODU BERGER | PROJECT 643 | All solution |  | 60022032636 | INSTALLED | 2024-07-19
106 | 1000247282 | 11-New AlausaINJ-T6-Ogundana-OLARIBIRO | IKEJA | OREGUN | OREGUN | 11-New AlausaINJ-T6-Ogundana | PUBLIC | GROUND | CIS | POST-PAID | METERED | 60019030581 | FUNCTIONAL | MOJEC | 500 | 800/5 | COMMISSIONED | HEALTHY | ACTIVE |  | 6.6046 | 3.3531 | ALLEN AVENUE IKEJA LAGOS OFF ADEBOYE SOLANKE STREET | PROJECT 643 | All solution |  | 60022032434 | INSTALLED | 2024-07-19
107 | 0100070680 | INTERIOR OPTION LIMITED | SHOMOLU | ILUPEJU | ILUPEJU | 11-Ilupeju BypassINJ-T1-Industrial |  |  |  |  | Complete Installation |  | Batch 1 |  | 100 | 200/5A LVMD | [6 empty] | BURNUN IND LTD | PROJECT 643 | All solution |  | 60022033327 | INSTALLED | 2024-07-19
108 | 0100709356 | CITY HALL - OJOTA | SHOMOLU | ANTHONY MEGA | ANTHONY MEGA | 11-OguduINJ-T1-CAC |  |  |  |  | Complete Installation |  | Batch 1 |  | 100 | 200/5A LVMD |  |  |  |  | 6.5807 | 3.3822 | EMMANUEL HIGH STR OGUDU LAGOS | PROJECT 643 | All solution |  | 60020123623 | INSTALLED | 2024-07-22
109 | 0100070167 | OMOTAYO OJO CAB CONST WK L | SHOMOLU | IKOSI | IKOSI | 11-MarylandINJ-T3-Demurin |  |  |  |  | Complete Installation |  | Batch 1 |  | 300 | 500/5A LVMD |  |  |  |  | 6.607 | 3.3817 | 23 LOVEALL ST | PROJECT 643 | All solution |  | 60022033816 | INSTALLED | 2024-07-22
110 | 0100070771 | KAMSON KEHINDE | SHOMOLU | OLOWORA | OLOWORA | 11-MagodoINJ-T2-Bashiru | PUBLIC |  |  |  | Complete Installation |  | Batch 1 | tee n bee | 100 | 200/5A LVMD | [6 empty] | P.793 SOMIDE ODUNJIR | PROJECT 643 | TEE N BEE |  | 60022033311 | INSTALLED | 2024-07-18
111 | 0100070132 | RAPEEAT TEMITAYO LAWAL | SHOMOLU | OLOWORA | OLOWORA | 33-AlausaTCN-OPIC | 100 | #NAME? | #NAME? |  | Complete Installation |  | Batch 1 | tee n bee | 100 | 200/5A LVMD | [6 empty] | PLT 10 ISHERI NORTH OPIC | PROJECT 643 | TEE N BEE |  | 60022033272 | INSTALLED | 2024-07-18
112 | 0100070502 | EHKAY CORRUGATED CARTONS LTD | SHOMOLU | OGUDU | OGUDU | 11-OguduINJ-T1-Ogudu | 500 | #NAME? | #NAME? |  | Complete Installation |  | Batch 1 | aderalph | 300 | 500/5A LVMD |  |  |  |  | 6.5877 | 3.3836 | 2-10 TAIWO STREET | PROJECT 643 | ADERALPH |  | 060022033013 | INSTALLED | 2024-07-18
113 | 1002049767 | 33-OgbaTCN-IJU WATER WORKS-GENERAL HOSPITAL | IKEJA | IFAKO | IFAKO | 33-OgbaTCN-IJU WATER WORKS-GENERAL HOSPITAL |  |  |  |  | Complete Installation | 800/5A LVMD |  | aderalph | 500 | 800/5A LVMD |  |  |  |  | 6.6439 | 3.3255 | COLLEGE ROAD, AGEGE | PROJECT 643 | ADERALPH |  | 060022033026 | INSTALLED | 2024-07-19
114 | 0100069024 | G L O B A C O M OFFICE | IKEJA | PTC | PTC | 11-PTCINJ-T1-Opebi | 200 |  |  |  | Complete Installation | 500/5A LVMD | Batch 1 | quintec | 1900-07-18 | 500/5A LVMD | INSTALLED |  |  |  | 6.5957 | 3.3549 | 2. OPEBI ROAD. IKEJA. | PROJECT 643 | QUINTEC |  | 060022032662 | INSTALLED | 2024-07-18
115 | 0100922296 | OLUMIRIN VENTURES LIMITED | IKEJA | OGBA | OGBA | 11-OgbaINJ-T2-Mangoro | 3NP07304 |  |  |  | Complete Installation | 500/5A LVMD | [10 empty] | 1, OGBA ROAD | PROJECT 643 | vicbonny |  | 060022032771 | INSTALLED | 2024-07-18
116 | 0100068353 | POWER LINE NIGERIA LTD | IKEJA | OGBA | OGBA | 11-OgbaINJ-T3-Oba Akran | 0 |  |  |  | Complete Installation | 200/5A LVMD | [10 empty] | SAPARA STR MD/IKEJA/1/2/29 M/N 65/23457 IKEJA | PROJECT 643 | vicbonny |  | 060022033330 | INSTALLED | 2024-07-18
117 | 1003016404 | 11-MagodoINJ-T1-Owulade-AUSTIN AGBOLAHAN | SHOMOLU | MAGODO | MAGODO MEGA | 11-MagodoINJ-T1-Owulade | PUBLIC | GROUND | CIS | POST-PAID | METERED | 60011010673 | FUNCTIONAL | MOJEC | 100 | 200/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6188 | 3.3847 | AUSTIN AGBONLAHOR CLOSE, OFF ADETORO ADELAJA STREET, MAGODO PHASE 2, LAGOS | PROJECT 643 | mayfak |  | 60022033273 | INSTALLED | 2024-07-24
118 | 0100068144 | GS MICROFINANCE BANK | IKEJA | OREGUN | OREGUN | 11-New AlausaINJ-T5-Alausa |  |  |  |  | Complete Installation | 500/5A LVMD | Batch 1 | mayfak | [6 empty] | 6.6096 | 3.3535 | 1. KUDIRAT ABIOLA WAY. OREGUN LAGOS. | PROJECT 643 | mayfak |  | 060022033567 | INSTALLED | 2024-07-23
119 | 1006038401 | 11-Ipakodo (Ebute)INJ-T1-WAEC-OLU ODO II | IKORODU | IGBOGBO | IGBOGBO | 11-Ipakodo (Ebute)INJ-T1-WAEC | PUBLIC | GROUND | CIS | POST-PAID | UNMETERED | N/A | N/A | 500 | NOT CONNECTED | NOT COMMISSIONED |  | HEALTHY |  |  | 6.5908 | 3.5004 | OLU ODO , EBUTE, IGBOGBO, IKORODU | PROJECT 643 | mayfak |  | 60022033747 | INSTALLED | 2024-07-25
120 | 1006038201 | 11-SaboINJ-T2-Erunwen-Awofusi CDA | IKORODU | AYANGBUREN | AYANGBUREN | 11-SaboINJ-T2-Erunwen |  | GROUND MOUNTED | UNMETERED | 500 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | NOT CONNECTED | NOT COMMISSIONED |  |  |  |  | 6.6121 | 3.544 | Awofusi Community Area. Ikorodu Lagos State | PROJECT 643 | mayfak |  | 60022033474 | INSTALLED | 2024-07-26
121 | 1000253993 | 11-OgbaINJ-T1-Isokoko-ADEYEMI 500KVA | IKEJA | OGBA | OGBA | 11-OgbaINJ-T1-Isokoko | PUBLIC | GROUND | CIS | POST-PAID | METERED | 201508004053 | FUNCTIONAL | CLOU | 500 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE |  | 6.6202 | 3.328 | ADEYEMI STREET OGBA | PROJECT 643 | ALL SOLUTION |  | 60022032443 | INSTALLED | 2024-07-30
122 | 1003212906 | 11-AlimoshoINJ-T8-Alimosho-OBICHERE UGOCHUKWU | AKOWONJO | EGBEDA | EGBEDA | 11-AlimoshoINJ-T8-Alimosho | PUBLIC | POLE MOUNTED | CIS | POST-PAID | METERED | 60013090435 | FUNCTIONAL | MOJEC | 100 | 200/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6066 | 3.307 | ADISA OGUNWEMIMO STREET | PROJECT 643 | TEE N BEE |  | 060022031880 | INSTALLED | 2024-07-30
123 | 1000535965 | 33-AyoboTCN-ABULE TAYLOR-OPEYEMI 1 | AKOWONJO | ABULE-TAYLOR | ABULE-TAYLOR | 33-AyoboTCN-ABULE TAYLOR | PUBLIC | GROUND | CIS | POST-PAID | METERED | 201508005684 | FUNCTIONAL | CLOU | 500 | 800/5 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6621 | 3.2868 | OPEYEMI STREET, OBADEYI. | PROJECT 643 | DEMOL/TEE N BEE |  | 060022033792 | INSTALLED | 2024-07-29
124 | 1006038402 | 33-Oke-AroTCN-AKUTE-FEYSDAM RESIDENTIAL ESTATE | SHOMOLU | MAGODO MEGA | MAGODO MEGA | 33-Oke-AroTCN-AKUTE | PUBLIC | GROUND MOUNTED |  |  | UNMETERED |  |  |  | 500 |  | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.686832 | 3.432806 | AT BLOCK E-F, PLOT 2, VOERA ESTATE, AREPO, OFF LAGOS IBADAN EXPRESSWAY | PROJECT 643 | mayfak |  | 060022032792 | INSTALLED | 2024-07-29
125 | 1005118908 | 11-AbesanINJ-T1-Ipaja-GLORYFIELD | AKOWONJO | IPAJA | IPAJA | 11-AbesanINJ-T1-Ipaja | GROUND MOUNTED | UNMETERED | [6 empty] | 500 | NOT CONNECTED | NOT COMMISSIONED |  | HEALTHY | INACTIVE | 6.6278 | 3.2509 | peace estate road off command road,ipaja Akowonjo | PROJECT 643 | mayfak |  | 60022032406 | INSTALLED | 2024-07-30
126 | 0100068665 | MAZIN ENGINEERING CO LTD | IKEJA | OREGUN | OREGUN | 11-SecretariatINJ-T2-UAC |  |  |  |  | Complete Installation | 800/5A LVMD | Batch 1 | mayfak | 500 | [5 empty] | 6.6046 | 3.3645 | PLT 20 OLAYIWOLA STR M/NO 85/56 OREGUN | PROJECT 643 | mayfak |  | 060022032476 | INSTALLED | 2024-07-29
127 | 1002050712 | 11-OgbaINJ-T3-Oba Akran-DEMILLER GENERAL SERVICES | IKEJA | ANIFOWOSHE | ANIFOWOSHE | 11-OgbaINJ-T3-Oba Akran | PUBLIC | POLE MOUNTED | CIS | POST-PAID | METERED | 201606010644 | FAULTY | CLOU | 100 | CONNECTED | COMMISSIONED |  | HEALTHY | ACTIVE | 6.598 | 3.3406 | 6,OBA AKRAN AVENUE | PROJECT 643 | mayfak/demol |  | 060022033851 | INSTALLED | 2024-07-29
128 | 0100068632 | CHRIST EMBASSY CHURCH | IKEJA | OREGUN | OREGUN | 11-New AlausaINJ-T5-Alausa |  |  |  |  | Complete Installation | 800/5A LVMD | Batch 1 | mayfak | 500 | [5 empty] | 6.6067 | 3.3628 | BILLINGS WAY ALAUSA IKEJA. LAGOS. | PROJECT 643 | mayfak |  | 060022032425 | INSTALLED | 2024-07-23
129 | 1001603434 | 11-New GowonINJ-T1-Olorunadaba-I.E. DISTRICT OFFICE EGBEDA | AKOWONJO | EGBEDA | EGBEDA | 11-New GowonINJ-T1-Olorunadaba | PUBLIC | 60013090645 | [12 empty] | * | 3.2937 | AKOWONJO BU OFFICE | PROJECT 643 | mayfak/demol | FUNCTIONAL | 060022032908 | INSTALLED | 3107/2024

## ISSUE LIST
S/N | CIS Account No. | NAME | BU | UT | Transformer Capacity | Meter No | Feeder | Coordinates (LAT) | Coordinates (LONG) | ADDRESS | Meter current condition | Requirement | Remark | Installer | METER NO ASSIGNED FOR LOCATION | INSTALLATION STATUS/ISSUES | DAY OUTAGE WAS SCHEDULE
1 | 0100068893 | THE ROZIZZIO | IKEJA | PTC | PUBLIC | #NAME? | 11-Adekunle FajuyiINJ-T1-Isaac John |  |  | 29 ISAAC JOHN GRA. IKEJA LAGOS. | Complete Installation | 200/5A LVMD | Batch 1 | vicbonny | 060022033346 | BURNT CABLE /CUSTOMER NOT AROUND/PROMISE TO CHANGE CABLE | 2024-07-09
2 | 0101846534 | O'SHEY | IKEJA | PTC | PUBLIC | #NAME? | 11-Adekunle FajuyiINJ-T1-Isaac John |  |  | 29 ISAAC JOHN GRA. IKEJA LAGOS. | Complete Installation | 200/5A LVMD | Batch 1 | vicbonny | 060022033205 | ALREADY METERED/AWAIT NEW LOCATION FROM IE | 2024-07-09
3 | 0100349046 | YOUNG TITILOLA | IKEJA | PTC | PUBLIC | #NAME? | 11-Adekunle FajuyiINJ-T1-Isaac John |  |  | 58A, ISAAC JOHN STREET, GRA , IKEJA , LAGOS | Complete Installation | 500/5A LVMD | Batch 1 | vicbonny | 060022032818 | ALREADY METERED/AWAIT NEW LOCATION FROM IE | 2024-07-09
4 | 0100070089 | LAGOS STATE HOUSE ANNEX | SHOMOLU | MAGODO | 200 | #NAME? | 11-MagodoINJ-T1-Shangisha | 6.614 | 3.3678 | 1 SHANGISHA | Complete Installation | 500/5A LVMD | Batch 1 | aderalph | 060022033714 | FACILITY STAKEHOLDERS DELAYING INSTALLATION
5 | 0102229993 | SIMON PETER OPARA | SHOMOLU | MAGODO MEGA | PUBLIC | #NAME? | 11-MagodoINJ-T1-Shangisha |  |  | 2, EMMANUEL KESHI STR, MAGODO PHASE II LAGOS | Complete Installation | 200/5A LVMD | Batch 1 | aderalph | 060022031687 | ALREADY METERED
6 | 0102071186 | AMBIENCE HOTEL & RESORT | SHOMOLU | MAGODO MEGA | PUBLIC | #NAME? | 11-MagodoINJ-T1-Shangisha |  |  | 23 ADEKUNLE BANJO AVENUE | Complete Installation | 200/5A LVMD | Batch 1 | aderalph | 060022031685 | ALREADY PAID FOR NEW METER AND EXPECTING IT
7 | 0102173664 | SADELA SAMUEL | SHOMOLU | OWOROSHONKI MEGA | PUBLIC | #NAME? | 11-OguduINJ-T3-Soluyi |  |  | SHOLUYI VILL OFF AMOELE | Complete Installation | 500/5A LVMD | Batch 1 | tee n bee | 060022032745 | ALREADY METERED
8 | 0102403987 | BAPTIST COMPOUND | SHOMOLU | OWOROSHONKI MEGA | PUBLIC | #NAME? | 11-Ilupeju BypassINJ-T1-Obanikoro |  |  | BAPTIST ACADEMY OBANIKORO LAGOS | Complete Installation | 500/5A LVMD | Batch 1 | tee n bee | 060022033445 | ALREADY METERED
9 | 0100098726 | POWER HOLDING COMPANY OF NIG., | IKEJA | PTC | 300 | #NAME? | 33-OgbaTCN-PTC EXP. | #NAME? | #NAME? | 1. GENERAL HOSPITAL ROAD. IKEJ PTC UNDERTAKING OFFICE LAGOS STATE | Complete Installation | 500/5A LVMD | Batch 1 | demol | 060022033729 | VOLTAGE CABLE CASTED /UNDERGROUND | 2024-07-11
10 | 0100069057 | GOODISS SUPERSTORES LTD | IKEJA | PTC | 300 | #NAME? | 11-PTCINJ-T2-Awuse | 6.587 | 3.3576 | 21/22, MOBOLAJI BANK ANTHONY WAY, MARYLAND , IKEJA , LAGOS | Complete Installation | 500/5A LVMD | Batch 1 | demol | 060022033000 | SHORT CABLE AT SITE | 2024-07-10
11 | 0101477190 | NPF MICROFINANCCE BANK PLC | IKEJA | PTC | PUBLIC | #NAME? | 11-PTCINJ-T2-Awuse |  |  | OBA AKINJOBI WAY, GRA, IKEJA | Complete Installation | 200/5A LVMD | Batch 1 | demol | 060022033563 | CUSTOMER DOESN’T WANT METER TO BE CHANGE | 2024-07-10
12 | 1001603434 | 11-New GowonINJ-T1-Olorunadaba-I.E. DISTRICT OFFICE EGBEDA | AKOWONJO | EGBEDA | PUBLIC | 60013090645 | 11-New GowonINJ-T1-Olorunadaba | 6.6043 | 3.2937 | AKOWONJO BU OFFICE | METERED | 800/5A LVMD | FUNCTIONAL | DEMOL | 060022033792 | SHORT CABLES (YELLOW AND BLUE PHASE)
13 | 0101394974 | DR ADEBOLA SULAIMON | IKEJA | PTC | PTC |  | 11-PTCINJ-T3-General Hospital | 6.575 | 3.347 | 90 ODUDUWA CRESCENT | Faulty Electronic component | 200/5A LVMD | Faulty meter | welldone/meter with vicbonny | 060022033364 | Requires 2m cable of 150mm X 4 core
14 | 0100068948 | AYOOLA ABIDOYE | IKEJA | PTC | PTC |  | 11-PTCINJ-T3-General Hospital | 6.5804 | 3.3437 | 54 OLADIPO BATEYE ST IKEJA G R A | Complete Installation | 200/5A LVMD | Faulty meter | welldone/meter with vicbonny | 060022033365 | customer refused access to location
15 | NEW ACCOUNT | ARAROMI COMMUNITY | IKEJA | OJODU | PUBLIC |  | 11-OjoduINJ-T1-Ojodu |  |  | ADENIYI OKE STREET | Complete Installation | 500/5A LVMD | Batch 1 | tee n bee | 60022031858 | require 1 concrete po;e and 150mmx 4core
16 | 0100062889 | THE APOSTOLIC FAITH MISSION | SHOMOLU | MENDE | MENDE | #NAME? | 11-MarylandINJ-T3-Sylvia | 6.5626 | 3.3772 | 1, APOSTOLIC FAITH COMP | Complete Installation | 800/5A LVMD | Batch 1 | aderalph | 060022033161 | need cable/ short cable
17 | 0100098734 | ELIZADE NIGERIA LIMITED | IKEJA | PTC | PTC | #NAME? | 11-MarylandINJ-T2-GRA | 6.5793 | 3.3607 | 14 MOBOLAJI BANK ANTHONY WAY IKEJA LAGOS | Complete Installation | 800/5A LVMD | Batch 1 | quintec | 060022032413 | customer doesn’t want meter
18 | 0100098717 | ALHAJI KAREEM YUSUF | IKEJA | PTC | PTC | #NAME? | 11-PTCINJ-T1-Opebi | 6.5941 | 3.3516 | 7A ABIODUN CLOSE OFF TOYIN STREET LAGOS | Complete Installation | 500/5A LVMD | Batch 1 | quintec | 060022033659 | customer doesn’t want meter said they have case with IE IN COURT
19 | 0101451596 | GLOBACOM LTD - LAG 309 | IKEJA | PTC | PTC | #NAME? | 11-MarylandINJ-T2-GRA |  |  | BEHIND BRISCOE MOTORS OFF MOBOLAJI BANK ANTHONY WAY, IKEJA | Complete Installation | 200/5A LVMD | Batch 1 | quintec | 060020123680 | NEED CABLE
20 | 100070201 | REX CHARLES AND PATRICK LTD | SHOMOLU | OLATEJU | OLATEJU | #NAME? | 11-Ilupeju BypassINJ-T1-Industrial | 6.5417 | 3.3571 | AGEGE MOTOR RD | Complete Installation | 500/5A LVMD | Batch 1 | tee n bee | 60022032581 | ALREADY METERED
21 | 0102290575 | MEGAVONS C.P.E.D | SHOMOLU | IGBOBI MEGA | IGBOBI MEGA | #NAME? | 11-IgbobiINJ-T2-Market |  |  | 134 IKORODU ROAD ONIPANU | Complete Installation | 200/5A LVMD | Batch 1 | All solution | 60022301677 | ALREADY METERED
22 | 0102726053 | ATC WILESS 403132 LG0778 | SHOMOLU | ILUPEJU MEGA | ILUPEJU MEGA | #NAME? | 11-Ilupeju BypassINJ-T1-Industrial |  |  | 15 TAIWO KOYA STREET OFF MOGAJI STREET ILUPEJU, LAGOS | Complete Installation | Whole current meter | Batch 1 | All solution | 060021051084 | ALREADY METERED
23 | 0102122637 | JIDE AGABE | IKEJA | OREGUN | OREGUN | #NAME? | 11-New AlausaINJ-T4-Oregun |  |  | 3B,OLUFUNKE ATITEBI JULI ESTATE,IKEJA,LAGOS | Complete Installation | 200/5A LVMD | Batch 1 | mayfak | 060022033722 | short cable
24 | 0102731129 | PIUS KOLAWOLE EDDO | IKEJA | OREGUN | OREGUN | #NAME? | 11-New AlausaINJ-T5-Alausa |  |  | 24 IYALLA STREET OFF KAFFI ALAUSA IKEJA | Complete Installation | 200/5A LVMD | Batch 1 | mayfak | 060022031870 | short cable
25 | 0101309240 | KUNLE | IKEJA | OREGUN | OREGUN | #NAME? | 11-New AlausaINJ-T6-Ogundana |  |  | 31B, OGUNDANA STREET OFF ALLEN AVENUE | Complete Installation | 200/5A LVMD | Batch 1 | mayfak | 060022032494 | short cable

## OUTSTANDING WC LVMD (hidden)
S/N | CIS DT Number | New Unique DT Nomenclature | BAND | BU | UT | New UT Name | Feeder Name | Ownership | Installation Position | Metering Status | OLD Meter Number | Meter Functionality Status | Meter Type | Capacity | Connection Status | Commissioning Status | Maintenance Status | Disconnection Status | Coordinates (LAT) | Coordinates (LONG) | Addresses | Identified Issue(s) | Required Materials | Remark by EM Engineer | SBC SCHEDULED FOR INSTALLATION | NEW METER INSTALLED AT DT | STATUS | DATE OF INSTALLATION

## OUTSTANDING WC (2) (hidden)
S/N | CIS DT Number | New Unique DT Nomenclature | BAND | BU | UT | New UT Name | Feeder Name | Ownership | Installation Position | Metering Status | OLD Meter Number | Meter Functionality Status | Meter Type | Capacity | Connection Status | Commissioning Status | Maintenance Status | Disconnection Status | Coordinates (LAT) | Coordinates (LONG) | Addresses | Identified Issue(s) | Required Materials | Remark by EM Engineer | SBC SCHEDULED FOR INSTALLATION | NEW METER INSTALLED AT DT | STATUS | DATE OF INSTALLATION

## WC TO DEPLOY (hidden)
S/N | CIS DT Number | New Unique DT Nomenclature | BAND | BU | UT | New UT Name | Feeder Name | Ownership | Installation Position | Metering Status | OLD Meter Number | Meter Functionality Status | Meter Type | Capacity | Connection Status | Commissioning Status | Maintenance Status | Disconnection Status | Coordinates (LAT) | Coordinates (LONG) | Addresses | STATUS | DATE OF INSTALLATION

## PRIVATE
S/N | METER NO | RATING | SBC | PROJECT
2 | 60021080524 | 200/5A | MAYFAK | LIGHT UP LAGOS METER WITH MAYFAK