## Sheet5 (hidden)
Row Labels | Count of NEW METER INSTALLED AT DT
ADERALPH | 8
ALL SOLUTION | 18
MAYFAK | 9
QUINTEC | 14
SYSFIX | 11
TEE N BEE | 10
VICBONNY | 10
(blank)
Grand Total | 80

## PROJECT 200 WC REPORT
S/N | CIS DT Number | New Unique DT Nomenclature | BAND | BU | UT | New UT Name | Feeder Name | Ownership | Installation Position | Metering Status | OLD Meter Number | Meter Functionality Status | Meter Type | Capacity | Connection Status | Commissioning Status | Maintenance Status | Disconnection Status | Coordinates (LAT) | Coordinates (LONG) | Addresses | Identified Issue(s) | Required Materials | Remark by EM Engineer | SBC SCHEDULED FOR INSTALLATION | NEW METER INSTALLED AT DT | STATUS | DATE OF INSTALLATION | REMARK
1 | 1000280385 | 11-Oke IraINJ-T1-Ayo Alabi-MODUPE ERINOSHO 3 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508007161 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6554 | 3.3491 | MODUPE ERINOSO STREET OKEIRA OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | VICBONNY | 060021050490 | METER INSTALLED | 2023-12-15
2 | 1000280379 | 11-Oke IraINJ-T1-Ayo Alabi-MODUPE ERINOSHO 2 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508007162 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6553 | 3.3491 | MODUPE ERINOSO STREET OKEIRA OGBA | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | VICBONNY | 060021050482 | METER INSTALLED | 2023-12-15
3 | 1000265943 | 11-Oke IraINJ-T1-Ayo Alabi-AYO ALABI 51 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508006182 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6496 | 3.3457 | 51 AYO ALABI ROAD OKEIRA OGBA | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | VICBONNY | 060021050033 | METER INSTALLED | 2023-12-15
4 | 1000274431 | 11-Oke IraINJ-T1-Ayo Alabi-AYO ALABI 56 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 60020122220 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6508 | 3.3475 | AYO ALABI ROAD OKEIRA OGBA | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | VICBONNY | 060021050423 | METER INSTALLED | 2023-12-15
5 | 1000281939 | 11-Oke IraINJ-T1-Ayo Alabi-AYO ALABI 13 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508007349 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.646 | 3.3443 | NO 13,AYO-ALABI STREET OGBA. | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | VICBONNY | 060021050798 | METER INSTALLED | 2023-12-15
6 | 1000281941 | 11-Oke IraINJ-T1-Ayo Alabi-AYO ALABI 22 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 60020122089 | FAULTY | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6476 | 3.3447 | NO 22, AYO-ALABI STREET OGBA. | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | VICBONNY | 060021052181 | METER INSTALLED | 2023-12-15
7 | 1000273099 | 11-Oke IraINJ-T1-Ayo Alabi-AYO ALABI 27 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 60020122403 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6473 | 3.3446 | NO 27,AYO-ALABI STREET OGBA. | BURNT METER | WC meter to be installed | WC meter to be installed | VICBONNY | 060021051515 | METER INSTALLED | 2023-12-15
8 | 1000281433 | 11-Oke IraINJ-T1-Ayo Alabi-AYO ALABI 41 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 60020122175 | FAULTY | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6485 | 3.3449 | NO 41,AYO-ALABI STREET OGBA. | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | VICBONNY | 060021052476 | METER INSTALLED | 2023-12-15
9 | 1000280459 | 11-Oke IraINJ-T1-Ayo Alabi-AYO ALABI 52 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508006728 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6503 | 3.3467 | NO 57,AYO-ALABI STREET OGBA. | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | VICBONNY | 060021051593 | METER INSTALLED | 2023-12-15
10 | 1000273367 | 11-Oke IraINJ-T1-Ayo Alabi-AYO ALABI 9B HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 60020122384 | FAULTY | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6458 | 3.3439 | NO 9,AYO-ALABI STREET OGBA. | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | VICBONNY | 060021051547 | METER INSTALLED | 2023-12-15
11 | 1000280648 | 11-Oke IraINJ-T1-Ayo Alabi-CELESTIAL AVENUE 7 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508007359 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6543 | 3.35 | CELESTIAL AVENUE OKEIRA OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 060021050497 | METER INSTALLED | 2023-12-18
12 | 1000280107 | 11-Oke IraINJ-T1-Ayo Alabi-CELESTIAL AVENUE 22 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 60019030606 | FAULTY | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6561 | 3.3498 | CELESTIAL AVENUE OKEIRA OGBA | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 060021051612 | METER INSTALLED | 2023-12-18
13 | 1000280113 | 11-Oke IraINJ-T1-Ayo Alabi-CELESTIAL AVENUE 25 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508006254 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6557 | 3.3498 | CELESTIAL AVENUE OKEIRA OGBA | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 060021051597 | METER INSTALLED | 2023-12-18
14 | 1000281922 | 11-Oke IraINJ-T1-Ayo Alabi-YUSUF STR 22 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508007594 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.649 | 3.3424 | 22YUSUF STREET OKEIRA OGBA | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 060021052768 | METER INSTALLED | 2023-12-18
15 | 1000267819 | 11-Oke IraINJ-T1-Ayo Alabi-YUSUF STR 8 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508004996 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6488 | 3.3433 | NO 10,YUSUF STREET OFF AYO-ALABI STREET OGBA. | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 060021051964 | METER INSTALLED | 2023-12-18
16 | 1001612546 | 11-Oke IraINJ-T1-Ayo Alabi-SAMUEL ABEGUNDE HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 60020122349 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6562 | 3.3506 | ABEGUNDE STREET, OKEIRA OGBA | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 060021050656 | METER INSTALLED | 2023-12-18
17 | 1000280936 | 11-Oke IraINJ-T1-Ayo Alabi-DELE AYEDUN HVDS 4 | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508004371 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6512 | 3.3451 | DELE AYEDUN CLOSE OKEIRA OGBA | Meter Confirmed Faulty | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 060021052432 | METER INSTALLED | 2023-12-18
18 | 1000280873 | 11-Oke IraINJ-T1-Ayo Alabi-ALADESHE 8 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | Metered | 201508004480 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6546 | 3.3487 | FUNSO ALADESE STREET OKEIRA OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 060021050930 | METER INSTALLED | 2023-12-18
19 | 1000280544 | 11-ObawoleINJ-T1-Youdeowei-3 JOSEPH DEMURIN HVDS | Band B | ABULE EGBA | IJU | IJU | 11-ObawoleINJ-T1-Youdeowei | PUBLIC | POLE MOUNTED | Metered | 201508007082 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6619 | 3.329 | 3 JOSEPH DEMURIN STR OFF BABATUNDE HASSAN | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021052389 | METER INSTALLED | 2024-01-10
20 | 1001663406 | 11-ObawoleINJ-T1-Youdeowei-14 ALHAJI AJISAFE HVDS | Band B | ABULE EGBA | IJU | IJU | 11-ObawoleINJ-T1-Youdeowei | PUBLIC | POLE MOUNTED | Metered | 60017052350 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6672 | 3.3274 | 14 ALHAJI AJISAFE STR OFF RAFTEC WAY | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050484 | METER INSTALLED | 2024-01-10
21 | 1000282142 | 11-ObawoleINJ-T1-Youdeowei-13 ALHAJI MUSTAPHA HVDS | Band B | ABULE EGBA | IJU | IJU | 11-ObawoleINJ-T1-Youdeowei | PUBLIC | POLE MOUNTED | Metered | 201508006798 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.665 | 3.3267 | 13 ALHAJI MUSTAPHA STR | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050839 | METER INSTALLED | 2024-01-10
22 | 1000281366 | 11-ObawoleINJ-T1-Youdeowei-9 AINA STR HVDS | Band B | ABULE EGBA | IJU | IJU | 11-ObawoleINJ-T1-Youdeowei | PUBLIC | POLE MOUNTED | Metered | 201508006352 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6633 | 3.3315 | 9 AINA STREET, UNITY ESTATE | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021052639 | METER INSTALLED | 2024-01-10
23 | 1000281106 | 11-ObawoleINJ-T1-Youdeowei-5 TAIWO SHITTA STR HVDS | Band B | ABULE EGBA | IJU | IJU | 11-ObawoleINJ-T1-Youdeowei | PUBLIC | POLE MOUNTED | Metered | 201508006222 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6609 | 3.3295 | 5 TAIWO SHITTA STR OFF OLD AKUTE ROAD | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050219 | METER INSTALLED | 2024-01-10
24 | 1001660910 | 11-AgegeINJ-T1-Iju Road-18 FAGBA STR HVDS | Band C | ABULE EGBA | IJU | IJU | 11-AgegeINJ-T1-Iju Road | PUBLIC | POLE MOUNTED | Metered | 60017070356 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6576 | 3.3249 | 18 FAGBA STREET OFF IJU ROAD | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021050667 | METER INSTALLED | 2024-01-11
25 | 1000281465 | 11-AgegeINJ-T1-Iju Road-17 PA ALAO HVDS | Band C | ABULE EGBA | IJU | IJU | 11-AgegeINJ-T1-Iju Road | PUBLIC | POLE MOUNTED | Metered | 201508007427 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6535 | 3.3257 | 17 PA ALAO STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021050021 | METER INSTALLED | 2024-01-11
26 | 1004362422 | 11-AgegeINJ-T1-Iju Road-11 AKINFEMI SAVAGE HVDS | Band C | ABULE EGBA | IJU | IJU | 11-AgegeINJ-T1-Iju Road | PUBLIC | POLE MOUNTED | Metered | 60020122063 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6539 | 3.3241 | 11 AKINFEMI SAVAGE OFF TUNJI ADEBAYO STR | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021050246 | METER INSTALLED | 2024-01-11
27 | 1001661410 | 11-AgegeINJ-T1-Iju Road-3 PRINCE DUROTOYE HVDS | Band C | ABULE EGBA | IJU | IJU | 11-AgegeINJ-T1-Iju Road | PUBLIC | POLE MOUNTED | Metered | 60017070050 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6409 | 3.3228 | 3 PRINCE DUROTOYE OFF IJU ROAD | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021050052 | METER INSTALLED | 2024-01-11
28 | 1000260832 | 11-AgegeINJ-T1-Iju Road-30 DADDY SAVAGE HVDS | Band C | ABULE EGBA | IJU | IJU | 11-AgegeINJ-T1-Iju Road | PUBLIC | POLE MOUNTED | Metered | 60019030479 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6552 | 3.328 | 30 DADDY SAVAGE STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021052399 | METER INSTALLED | 2024-01-11
29 | 1003580532 | 11-IjegunINJ-T2-Pipeline-228 & 229 ISAAC ALABI STREET | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Pipeline | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.516 | 3.2611 | ISAAC ALABI STREET | New service | WC meter to be installed | WC meter to be installed | MAYFAK | 060021050670 | METER INSTALLED | 2024-01-15
30 | 1003580534 | 11-IjegunINJ-T2-Pipeline-222 & 223 IJEGUN B/STOP | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Pipeline | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5163 | 3.2602 | IJEGUN B/STOP | New service | WC meter to be installed | WC meter to be installed | QUINTEC | 060021050481 | METER INSTALLED | 2024-01-15
31 | 1002258458 | 11-IjegunINJ-T1-Ikotun-230 & 231 MAJOR BUS STOP | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T1-Ikotun | PUBLIC | POLE MOUNTED | Metered | 60019060423 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5236 | 3.2578 | MAJOR BUS STOP IKOTUN ROAD | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 060021050671 | METER INSTALLED | 2024-01-15
32 | 1002090448 | 11-IjegunINJ-T1-Ikotun-339&462 AYANWALE STREET | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T1-Ikotun | PUBLIC | POLE MOUNTED | Metered | 60019060487 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5351 | 3.2622 | PIPELINE ROAD, IJEGUN | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 060021050444 | METER INSTALLED | 2024-01-15
33 | 1002641892 | 11-IjegunINJ-T2-Pipeline-CSP 401 & 402-KUDEBU ST OFF ISOLO RD | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Pipeline | PUBLIC | POLE MOUNTED | Metered | 60019060800 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5134 | 3.2648 | KUDEBU ST OFF ISOLO RD | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 060021050950 | METER INSTALLED | 2024-01-17
34 | 1000269367 | 11-BeckleyINJ-T1-Agbe road-ILE OGBO HVDS 11 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 60020122187 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6612 | 3.308 | 50B ILE OGBO | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 060021051100 | METER INSTALLED | 2024-01-18
35 | 1000269373 | 11-BeckleyINJ-T1-Agbe road-ILE OGBO HVDS 14 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 60020122457 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6624 | 3.3077 | 57B ILE OGBO | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 060021050466 | METER INSTALLED | 2024-01-18
36 | 1000273499 | 11-BeckleyINJ-T1-Agbe road-TOFEK HVDS 1 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 60019060611 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6571 | 3.309 | 4 TOFEK STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 060021050662 | METER INSTALLED | 2024-01-18
37 | NA | Nathan (11kV) New meter | NA | AKOKA TS | AKOKA TS | AKOKA TS | Nathan (Interphase meter) | PUBLIC | POLE MOUNTED | Metered | 60019060568 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | NA | NA | AKOKA TS | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 060021051963 | METER INSTALLED | 2024-01-16
38 | 1000273488 | 11-BeckleyINJ-T1-Agbe road-OLANIYI HVDS 6 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201508005951 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.658 | 3.3094 | 28 OLANIYI STR | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021050436 | METER INSTALLED | 2024-01-18
39 | 1000273745 | 11-BeckleyINJ-T1-Agbe road-OLANIYI HVDS 11 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201505001147 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6605 | 3.3088 | 45 OLANIYI STR | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021050838 | METER INSTALLED | 2024-01-18
40 | 1002994484 | 11-BeckleyINJ-T1-Agbe road-AKERELE 5 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201508004002 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6505 | 3.3072 | 5 AKERELE OKO OBA | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021051968 | METER INSTALLED | 2024-01-18
41 | 1000266992 | 11-BeckleyINJ-T1-Agbe road-WAMON TAOFEEK HVDS 7 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 60020122413 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6521 | 3.3069 | 18B WAMON TAOFEEK | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021050703 | METER INSTALLED | 2024-01-18
42 | 1000266952 | 11-BeckleyINJ-T1-Agbe road-WAMON TAOFEEK HVDS 9 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201508005576 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6525 | 3.3072 | 18 WAMON TAOFEEK | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021050954 | METER INSTALLED | 2024-01-18
43 | 1000274821 | 11-BeckleyINJ-T1-Agbe road-OWODE HVDS 4 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201508005178 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6528 | 3.3083 | NO 22 OWODE STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021051967 | METER INSTALLED | 2024-01-18
44 | 1000274818 | 11-BeckleyINJ-T1-Agbe road-OWODE HVDS 2 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201508005185 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6513 | 3.3074 | 32 OWODE STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021050874 | METER INSTALLED | 2024-01-18
45 | 1000269376 | 11-BeckleyINJ-T1-Agbe road-OLUSHOLA ADESHINA HVDS 2 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201508006139 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6588 | 3.3071 | 9 OLUSHOLA ADESHINA | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021051344 | METER INSTALLED | 2024-01-30
46 | 1000273854 | 11-BeckleyINJ-T1-Agbe road-OLUDEGUN HVDS 1 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 60020122164 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6575 | 3.3067 | 2 OLUDEGUN | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021051162 | METER INSTALLED | 2024-01-30
47 | 1000274404 | 11-BeckleyINJ-T1-Agbe road-MOSES EMEYA HVDS 4 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201512008307 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6509 | 3.3081 | 9 MOSES EMEYA STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021052331 | METER INSTALLED | 2024-01-30
48 | 1000274606 | 11-BeckleyINJ-T1-Agbe road-SANTOS HVDS 10 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 201508003746 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6511 | 3.3043 | 7 SANTOS | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021052987 | METER INSTALLED | 2024-01-30
49 | 1000274407 | 11-BeckleyINJ-T1-Agbe road-MOSES EMEYA HVDS 2 | Band C | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | Metered | 60021052447 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6523 | 3.3091 | 12 MOSES EMEYA STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021051966 | METER INSTALLED | 2024-01-30
50 | 1000976030 | 11-OgbaINJ-T1-Ijaye-HVDS (KEKE)-BLK 87 SSS | Band B | IKEJA | OGBA | OGBA | 11-OgbaINJ-T1-Ijaye | PUBLIC | POLE MOUNTED | Metered | 201505002492 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6293 | 3.3281 | IJAYE HOUSING ESTATE AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021050478 | METER INSTALLED | 2024-01-30
51 | 1000288050 | 11-OgbaINJ-T1-Ijaye-PYTHAGORAS HVDS OBA OGUNJI | Band B | IKEJA | OGBA | OGBA | 11-OgbaINJ-T1-Ijaye | PUBLIC | POLE MOUNTED | Metered | 201508006351 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6275 | 3.3338 | OBA OGUNJI ROAD, AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021051744 | METER INSTALLED | 2024-01-30
52 | 1000281749 | 11-Oke IraINJ-T2-Kayode-31 ALH SARU HVDS 25KVA | Band B | IKEJA | OGBA | OGBA | 11-Oke IraINJ-T2-Kayode | PUBLIC | POLE MOUNTED | Metered | 201508006824 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6297 | 3.3408 | ALH. UMAR SARO ST. IFAKO IJAIYE ROAD. | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021052320 | METER INSTALLED | 2024-01-26
53 | 1000281334 | 11-Oke IraINJ-T2-Kayode-NO 6 IJAIYE ROAD HVDS BY MANSARD | Band B | IKEJA | OGBA | OGBA | 11-Oke IraINJ-T2-Kayode | PUBLIC | POLE MOUNTED | Metered | 60020122256 | FAULTY | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6292 | 3.3377 | IJAIYE ROAD, BY AXA MANSARD, OGBA LAGOS | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021052087 | METER INSTALLED | 2024-01-26
54 | 1000260709 | 11-Oke IraINJ-T2-Kayode-BLK 22 HVDS (OPP AY HOTEL) | Band B | IKEJA | OGBA | OGBA | 11-Oke IraINJ-T2-Kayode | PUBLIC | POLE MOUNTED | Metered | 60020122246 | FAULTY | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6311 | 3.3458 | BLK 22 LAGOS STATE STAFF QUARTERS, OPP AY HOTEL, OFF WEMCO ROAD | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021052137 | METER INSTALLED | 2024-01-26
55 | 1002527924 | 11-Oke IraINJ-T2-Kayode-4 GABOL-HVDS(IJAIYE ROAD) | Band B | IKEJA | OGBA | OGBA | 11-Oke IraINJ-T2-Kayode | PUBLIC | POLE MOUNTED | Metered | 60019060896 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6274 | 3.3367 | GABOL SHOPPING PLAZA, 2 IJAIYE ROAD, OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021050543 | METER INSTALLED | 2024-01-26
56 | 1000283462 | 11-Oke IraINJ-T2-Kayode-BLK 14 OLADELE KADIRI | Band B | IKEJA | OGBA | OGBA | 11-Oke IraINJ-T2-Kayode | PUBLIC | POLE MOUNTED | Metered | 201508005846 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6305 | 3.3446 | 14 OLADELE KADIRI CLOSE, OFF NOB OLUWA STREET. LSDPC ESTATE (PHAZE 2) | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021052341 | METER INSTALLED | 2024-01-26
57 | 1000975599 | 11-AgegeINJ-T3-Oyemekun-2A OWONIKOKO CLOSE | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508007465 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6435 | 3.3295 | OSHUNKEYE STREET OFF OWONIKOKO STREET OFF COLLEGE ROAD, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021052956 | METER INSTALLED | 2024-01-31
58 | 1000281557 | 11-AgegeINJ-T3-Oyemekun-BILEWU OSHOFA CRESCENT | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 60020122488 | FAULTY | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6367 | 3.3275 | BILEWU OSHOFA STREET, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021050303 | METER INSTALLED | 2024-01-31
59 | 1000281479 | 11-AgegeINJ-T3-Oyemekun-4 PRATT ATANDA CLOSE | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508006423 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6418 | 3.3282 | ATANDA PRATT CLOSE, OFF ADEKOYA STREET, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021052480 | METER INSTALLED | 2024-01-31
60 | 1000262756 | 11-AgegeINJ-T3-Oyemekun-6 OGUNBORE STREET | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508005709 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6369 | 3.327 | OGUNBORE STREET, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021051535 | METER INSTALLED | 2024-01-31
61 | 1000262309 | 11-AgegeINJ-T3-Oyemekun-8 AYEDOGBON CLOSE | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508007459 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6431 | 3.3297 | AYEDOGBON CLOSE OFF COLLEGE ROAD, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ALL SOLUTION | 60021051365 | METER INSTALLED | 2024-01-31
62 | 1001602044 | 11-AgegeINJ-T3-Oyemekun-11 OMOAKIN STREET | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 60016111989 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6385 | 3.3304 | OMOAKIN STREET, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021050432 | METER INSTALLED | 2024-01-31
63 | 1000281564 | 11-AgegeINJ-T3-Oyemekun-29 GBAGBA CRESCENT | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508006286 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6377 | 3.3305 | GBAGBA CRESENT IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021051609 | METER INSTALLED | 2024-01-31
64 | 1002995492 | 11-AgegeINJ-T3-Oyemekun-38 AJIBODU | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 60012110009 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.647 | 3.33 | AJIBODU STREET OFF COLLEGE ROAD, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021050477 | METER INSTALLED | 2024-01-31
65 | 1000255414 | 11-AgegeINJ-T3-Oyemekun-11 AJIBODU STREET | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508005589 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6456 | 3.3288 | AJIBODU STREET OFF COLLEGE ROAD, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021052896 | METER INSTALLED | 2024-01-31
66 | 1000254378 | 11-AgegeINJ-T3-Oyemekun-32 HDVS ADEKOYE STREET | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508005271 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6397 | 3.3249 | ADEKOYA STREET OFF COLLEGE ROAD, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021050341 | METER INSTALLED | 2024-01-31
67 | 1000260446 | 11-AgegeINJ-T3-Oyemekun-6 ADEOLA AVENUE | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508004578 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6442 | 3.3288 | 10B,ADEOLA AVENUE OFF COLLEGE ROAD, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021052826 | METER INSTALLED | 2024-01-31
68 | 1002057055 | 11-AgegeINJ-T3-Oyemekun-15 HARMONY CLOSE | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508007405 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.65 | 3.329 | HARMONY CLOSE, HARMONY ESTATE, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021050384 | METER INSTALLED | 2024-01-31
69 | 1000280388 | 11-AgegeINJ-T3-Oyemekun-2, BELLO ADOGIE STREET | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508006152 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.65 | 3.3313 | BELLO ADOGIE CLOSE, HARMONY ESTATE, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021051375 | METER INSTALLED | 2024-01-31
70 | 1000255451 | 11-AgegeINJ-T3-Oyemekun-4 ADELEKE ODUNUGA CLOSE | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | Metered | 201508005587 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6489 | 3.3298 | ADELEKE ODUNUGA CLOSE, HARMONY ESTATE, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021050185 | METER INSTALLED | 2024-01-31
71 | 1003580530 | 11-IjegunINJ-T2-Isheri Oshun-212 & 213 TAYLOR JUNCTION | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Isheri Oshun | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5149 | 3.2655 | TAYLOR JUNCTION | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021051441 | METER INSTALLED | 2024-02-12
72 | 1003580968 | 11-IjegunINJ-T1-Okerube-319 & 310 MOMODU DADA STREET | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T1-Okerube | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5197 | 3.257 | MOMODU DADA STREET IJEGUN | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050547 | METER INSTALLED | 2024-02-12
73 | 1003580804 | 11-IjegunINJ-T1-Okerube-186 & 187 OLU AKINBO STREET | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T1-Okerube | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5192 | 3.2541 | OLU AKINBO STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050689 | METER INSTALLED | 2024-02-12
74 | 1003580802 | 11-IjegunINJ-T1-Okerube-161 & 162 MOJISOLA ALARAPINNI STREET | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T1-Okerube | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5193 | 3.2533 | MOJISOLA ALARAPINNI STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050550 | METER INSTALLED | 2024-02-12
75 | 1003580994 | 11-IjegunINJ-T1-Okerube-69 & 70 ALABATA STREET | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T1-Okerube | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5177 | 3.2494 | ALABATA STREET IJEGUN | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050953 | METER INSTALLED | 2024-02-12
76 | 1003580536 | 11-IjegunINJ-T2-Pipeline-319 & 310 ANTHONY ABUBA | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Pipeline | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5169 | 3.2591 | ANTHONY ABUBA | Faulty Meter | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050426 | METER INSTALLED | 2024-02-12
77 | 1003808402 | 11-Ilupeju BypassINJ-T1-Industrial-AGBOLAHAN KEHINDE | Band A | SHOMOLU | ILUPEJU | ILUPEJU MEGA | 11-Ilupeju BypassINJ-T1-Industrial | PUBLIC | POLE MOUNTED | Metered | 60008400274 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5464 | 3.3594 | 11, TAIWO KOYA STREET, ILUPEJU | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021050083 | METER INSTALLED | 2024-02-12
78 | 1001616902 | 11-OguduINJ-T3-Kola Adeshina-​ALHAJA ABASS 1 A | Band B | SHOMOLU | OGUDU | ANTHONY MEGA | 11-OguduINJ-T3-Kola Adeshina | PUBLIC | POLE MOUNTED | Metered | 60016111682 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5712 | 3.3928 | 31 ABUDU STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021052068 | METER INSTALLED | 2024-02-12
79 | 1001959902 | 11-OguduINJ-T3-Kola Adeshina-ALHAJI ABASS 1C | Band B | SHOMOLU | OGUDU | ANTHONY MEGA | 11-OguduINJ-T3-Kola Adeshina | PUBLIC | POLE MOUNTED | Metered | 60019060822 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5733 | 3.3928 | 16 T RAMAT CRESCENT | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021050103 | METER INSTALLED | 2024-02-12
80 | 1002112445 | 11-OguduINJ-T2-Alapere-1 TONY OMOREGIE CSP | Band B | SHOMOLU | OGUDU | ANTHONY MEGA | 11-OguduINJ-T2-Alapere | PUBLIC | POLE MOUNTED | Metered | 60019060726 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5742 | 3.4044 | TONY OMOREGIE CLOSE | Faulty Meter | WC meter to be installed | WC meter to be installed | SYSFIX | 60021050461 | METER INSTALLED | 2024-02-12
81 | 1003072572 | 11-OguduINJ-T3-Balogun-5 CHURCH STREET CSP | Band C | SHOMOLU | OWORO | OWOROSHONKI MEGA | 11-OguduINJ-T3-Balogun | PUBLIC | POLE MOUNTED | Metered | 60015052441 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.546 | 3.402 | 5 CHURCH STREET , OWORO, LAGOS | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021050545 | METER INSTALLED | 2024-02-24
82 | 1000265920 | 11-Oke IraINJ-T1-Ayo Alabi-OLA STREET 11 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508006483 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.651 | 3.3435 | OLA STREET OKEIRA OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021051879 | METER INSTALLED | 2024-03-04
83 | 1000265931 | 11-Oke IraINJ-T1-Ayo Alabi-DAPSON 1 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 60020122183 | FAULTY | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6516 | 3.3472 | NO 1,DAPSON STREET OFF AYO-ALABI STREET. | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021050251 | METER INSTALLED | 2024-03-04
84 | 1000266493 | 11-Oke IraINJ-T1-Ayo Alabi-AKINTOYE CL 9 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508007195 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6512 | 3.3441 | NO 7,AKINTOYE CLOSE OFF AYO-ALABI STREET OGBA. | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021051286 | METER INSTALLED | 2024-03-04
85 | 1000268243 | 11-Oke IraINJ-T1-Ayo Alabi-WAHAB FOLORUNSHO HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508004479 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6496 | 3.3472 | NO 6,WAHAB FOLORUSHO STREET OFF AYO-ALABI STREET OGBA. | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021051924 | METER INSTALLED | 2024-03-04
86 | 1000268247 | 11-Oke IraINJ-T1-Ayo Alabi-SHOFIDIYA CL 1 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508006893 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6505 | 3.3463 | NO 1,SHOFIDIYA CLOSE OFF AYO-ALABI STREET OGBA. | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021051618 | METER INSTALLED | 2024-03-04
87 | 1000270973 | 11-Oke IraINJ-T1-Ayo Alabi-J SHONOLA 18 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508004373 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6474 | 3.3434 | NO 18,JACOB SONOLA STREET OFF AYO-ALABI STREET OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021051428 | METER INSTALLED | 2024-03-04
88 | 1000280399 | 11-Oke IraINJ-T1-Ayo Alabi-SUNMONU 11 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508006382 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6468 | 3.3481 | NO 11,SUMONU STREET OFF AYO-ALABI STREET OGBA. | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021050494 | METER INSTALLED | 2024-03-04
89 | 1000280634 | 11-Oke IraINJ-T1-Ayo Alabi-KAYODE JOSEPH 13 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508005752 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6552 | 3.3507 | KAYODE JOSEPH STREET OKEIRA OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021052701 | METER INSTALLED | 2024-03-04
90 | 1000280939 | 11-Oke IraINJ-T1-Ayo Alabi-DELE AYEDUN HVDS 3 | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508004379 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.651 | 3.3449 | NO 14,DELEAYEDU CLOSE OFF AYO-ALABI STREET OGBA. | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021050664 | METER INSTALLED | 2024-03-04
91 | 1003019078 | 11-Oke IraINJ-T1-Ayo Alabi-OLADIPO BANJO 21 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508006291 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6501 | 3.3424 | OLADIPO BANJO STREET OKEIRA OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021051141 | METER INSTALLED | 2024-03-04
92 | 1000280619 | 11-Oke IraINJ-T1-Ayo Alabi-POWERLINE 15A HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508005667 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6535 | 3.3494 | POWERLINE STREET, OKEIRA OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021050840 | METER INSTALLED | 2024-03-04
93 | 1000267831 | 11-Oke IraINJ-T1-Ayo Alabi-OLANIPEKUN 5 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 201508004482 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6486 | 3.3464 | NO 11,OLANIPEKU AVENUE OFF AYO-ALABI STREET OGBA. | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021052605 | METER INSTALLED | 2024-03-04
94 | 1000280644 | 11-Oke IraINJ-T1-Ayo Alabi-CELESTIAL AVENUE 5 HVDS | Band C | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Ayo Alabi | PUBLIC | POLE MOUNTED | METERED | 60020122446 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6537 | 3.3499 | CELESTIAL AVENUE OKEIRA OGBA | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021050302 | METER INSTALLED | 2024-03-04
95 | 1000262351 | 11-AgegeINJ-T3-Oyemekun-17 ADEEKO STREET | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | METERED | 201508004698 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6435 | 3.3303 | 17,ADEEKO STREET OFF COLLEGE ROAD, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021052017 | METER INSTALLED | 2024-05-02
96 | 1000281897 | 11-AgegeINJ-T3-Oyemekun-10 OGUNBORE STR | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | METERED EST. | 201508006279 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6372 | 3.3272 | OGUNBORE STREET, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021052744 | METER INSTALLED | 2024-05-02
97 | 1000255876 | 11-AgegeINJ-T3-Oyemekun-15 ADEOLA AVENUE | Band B | IKEJA | IFAKO | IFAKO | 11-AgegeINJ-T3-Oyemekun | PUBLIC | POLE MOUNTED | METERED | 201508004576 | FAULTY | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.645 | 3.3297 | 15,ADEOLA AVENUE OFF COLLEGE ROAD, IFAKO AGEGE | Faulty Meter | WC meter to be installed | WC meter to be installed | ADERALPH | 60021052268 | METER INSTALLED | 2024-05-02
98 | 1000975590 | 11-ObawoleINJ-T1-Youdeowei-26 FELIX CR HVDS | Band A | ABULE EGBA | IJU | IJU | 11-ObawoleINJ-T1-Youdeowei | PUBLIC | POLE MOUNTED | METERED EST. | 201508007041 | FAULTY | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6588 | 3.3299 | 26 FELIX CRESCENT OFF OLD AKUTE ROAD | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021052506 | METER INSTALLED | 2024-07-02
99 | 1003143924 | 11-ObawoleINJ-T1-Youdeowei-11 AWOBONA HVDS | Band A | ABULE EGBA | IJU | IJU | 11-ObawoleINJ-T1-Youdeowei | PUBLIC | POLE MOUNTED | METERED EST. | 60019060835 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6651 | 3.3274 | 11,AWOBONA STREET | Faulty Meter | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021052054 | METER INSTALLED | 2024-07-02
100 | 1003797028 | 11-AlimoshoINJ-T8-Alimosho-6, BOUNDARY ROAD | Band A | AKOWONJO | EGBEDA | EGBEDA | 11-AlimoshoINJ-T8-Alimosho | PUBLIC | POLE MOUNTED | METERED | 60020122410 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5994 | 3.31 | LAJO KROAD | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021052400 | METER INSTALLED | 2024-07-04
101 | 1002527415 | 11-AlimoshoINJ-T8-Alimosho-4 OLAIYA CLOSE WILLIAM ESTATE | Band A | AKOWONJO | EGBEDA | EGBEDA | 11-AlimoshoINJ-T8-Alimosho | PUBLIC | POLE MOUNTED | METERED | 60019060567 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6072 | 3.3089 | OLAIYA CLOSE WILLIAM LAYOUT | Faulty Meter | WC meter to be installed | WC meter to be installed | MAYFAK | 60021051643 | METER INSTALLED | 2024-07-04
102 | 0101346682 | JAWURA ENVIROMENTAL SERVICE |  | IKEJA | PTC | PTC | 11-New AlausaINJ-T6-Awolowo |  |  |  | Complete Installation |  |  | 50 |  | Whole current meter |  |  |  |  | 130, AWOLOWO WAY BALOGUN BUS STOP, IKEJA |  | WC meter to be installed | WC meter to be installed | QUINTEC | 60021050797 | METER INSTALLED | 2024-07-16
103 | 0102776194 | LAGOS STATE STREET LIGHT |  | SHOMOLU | OWOROSHONKI MEGA | OWOROSHONKI MEGA | 11-OguduINJ-T3-Soluyi |  |  |  | Complete Installation |  |  | 50 |  | Whole current meter |  |  | 6.5639 | 3.3847 | ESTAPORT AVENUE, SOLUYI ROAD GBAGADA LAGOS |  | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021052779 | METER INSTALLED | 2024-07-16
104 | 0100070739 | ILUPEJU INJECTION STATION |  | SHOMOLU | ILUPEJU | ILUPEJU | 33-IlupejuTCN-ILUPEJU BY-PASS |  | #NAME? | #NAME? | Complete Installation |  |  | 50 | [6 empty] | P H C N OFFICE |  | WC meter to be installed | WC meter to be installed | All solution | 60021051071 | METER INSTALLED | 2024-07-16
105 | 1004048968 | 11-OjoduINJ-T2-River Valley-ABASIAKARA |  | IKEJA | OJODU | OJODU | 11-OjoduINJ-T2-River Valley |  | POLE MOUNTED | METERED | 60020122191 | FUNCTIONAL | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6408 | 3.372 | OJODU ISS, ISHERI ROAD OJODU BERGER |  | WC meter to be installed | WC meter to be installed | DEMOL | 60021052328 | METER INSTALLED | 2024-07-18
106 | 1001888404 | 11-OdogunyanINJ-T2-Odokekere-POLE 351A/351B KENNY JULIUS STR |  | IKORODU | ODOGUNYAN | ODOGUNYAN | 11-OdogunyanINJ-T2-Odokekere |  | POLE MOUNTED | METERED | 60019060777 | FAULTY | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6876 | 3.5222 | OMO ONILE AREA AREA HVDS POLE MOUNTED |  | WC meter to be installed | WC meter to be installed | DEMOL | 60021052670 | METER INSTALLED | 2024-07-22
107 | 1001596985 | 11-IjedeINJ-T1-Gberibe-NIPP HVDS POLE 598 A&B | Band D | IKORODU | IJEDE | IJEDE | 11-IjedeINJ-T1-Gberibe-NIPP HVDS | [6 empty] | 50 |  |  |  |  | 6.594 | 3.5879 | OLUFUNMILAYO FADUGBAGBE STREET, OKE-ELETU IJEDE ROAD IKORODU |  | WC meter to be installed | WC meter to be installed | MAYFAK | 60021051745 | METER INSTALLED | 2024-07-26
108 | 0101698952 | CWAY NIGERIA DRINK WATER SCI & TECH CO. LTD |  | IKEJA | PTC | PTC | 11-PTCINJ-T3-Oba Akinjobi | PUBLIC |  | 4B, REMI FANI KAYODE STR, GRA, IKEJA | Complete Installation | Whole current meter | Batch 1 | demol | 2024-07-11 | [7 empty] | WC meter to be installed | WC meter to be installed | DEMOL | 60021050408 | METER INSTALLED | 2024-08-02
109 | 0101263555 | CHARITY OGUIJE |  | AKOWONJO | GOWON | GOWON | 11-AlimoshoINJ-T4-FHA | PUBLIC | Complete Installation | Whole current meter | Batch 2 | Aderalph | [8 empty] | 32RD,RESTURANT,BESIDE BLUE DEOSOL EVENT CENTRE. |  | WC meter to be installed | WC meter to be installed | aderalph | 60021052239 | METER INSTALLED | 2024-08-07
110 | 0100965665 | EMEKA N. G. O. ., |  | OSHODI | IKOTUN | IKOTUN | 33-EjigboTCN-AGODO | PUBLIC | Complete Installation | Whole current meter | Batch 2 | tee n bee |  | installed | [6 empty] | 28 LIASU ROAD EGBE LAGOS |  | WC meter to be installed | WC meter to be installed | TEE N BEE | 60021051363 | METER INSTALLED
111 | 1003580784 | 11-IjegunINJ-T2-Isheri Oshun-385 & 386 OLUWADAMILARE | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Isheri Oshun | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.4976 | 3.2766 | OLUWADAMILARE |  | WC meter to be installed | WC meter to be installed | MAYFAK | 60021051426 | METER INSTALLED | 2024-08-12
112 | 1003581130 | 11-IjegunINJ-T2-Isheri Oshun-281 & 282 FAGBILE ESTATE ROAD | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Isheri Oshun | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | FAULTY | INACTIVE | 6.5235 | 3.2671 | FAGBILE ESTATE ISHERI OSHUN |  | WC meter to be installed | WC meter to be installed | MAYFAK | 60021050549 | METER INSTALLED | 2024-08-12
113 | 1003580776 | 11-IjegunINJ-T2-Isheri Oshun-IE-0441 PIPELINE ROAD | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Isheri Oshun | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.524 | 3.261 | PIPELINE ROAD IJEGUN |  | WC meter to be installed | WC meter to be installed | MAYFAK | 60021051161 | METER INSTALLED | 2024-08-12
114 | 1003580790 | 11-IjegunINJ-T2-Isheri Oshun-309 & 310 FAGBILE ESTATE ROAD | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Isheri Oshun | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5164 | 3.2658 | FAGBILE ESTATE ISHERI OSHUN |  | WC meter to be installed | WC meter to be installed | MAYFAK | 60021051157 | METER INSTALLED | 2024-08-12
115 | 1003580774 | 11-IjegunINJ-T2-Isheri Oshun-IE-0444 PIPELINE ROAD | Band D | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Isheri Oshun | PUBLIC | POLE MOUNTED | UNMETERED | N/A | N/A | N/A | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5263 | 3.264 | ADEBAYO IGE STREET OFF PIPELINE ROAD IJEGUN |  | WC meter to be installed | WC meter to be installed | MAYFAK | 60021050636 | METER INSTALLED | 2024-08-12
116 | 1000259889 | 11-AgegeINJ-T2-Abule Egba-LABAK EST(SYLVAT AVE) POLE 6 | Band C | AKOWONJO | ORILE-AGEGE | ORILE-AGEGE | 11-AgegeINJ-T2-Abule Egba | PUBLIC | POLE MOUNTED | METERED | 201508004686 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6431 | 3.3093 | PLOT 1 OLUDAYO CLOSE LABAK ESTATE |  |  |  | TEE N BEE | 060021051602 | METER INSTALLED | 2024-08-26
117 | 1000259817 | 11-BeckleyINJ-T1-Beckley-DAVIDS KOLAWOLE HVDS 1 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Beckley | PUBLIC | POLE MOUNTED | METERED | 201508005112 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6584 | 3.3044 | 21 DAVIDS KOLAWOLE |  |  |  | Aderalph | 060021050405 | METER INSTALLED | 2024-08-21
118 | 1000269343 | 11-BeckleyINJ-T1-Agbe road-ILE OGBO HVDS 8 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | METERED | 60020122222 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6599 | 3.3081 | 50A ILE OGBO |  |  |  | Aderalph | 060021052140 | METER INSTALLED | 2024-08-21
119 | 1000280736 | 11-BeckleyINJ-T1-Beckley-MUSBAU ASAFA HVDS 1 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Beckley | PUBLIC | POLE MOUNTED | METERED | 201508006326 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6599 | 3.303 | 28 MUSBAU ASAFA |  |  |  | Aderalph | 060021050498 | METER INSTALLED | 2024-08-21
120 | 1000280282 | 11-BeckleyINJ-T1-Beckley-MUSBAU ASAFA HVDS 3 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Beckley | PUBLIC | POLE MOUNTED | METERED | 60020122286 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6608 | 3.3035 | 16 MUSBAU ASAFA |  |  |  | Aderalph | 060021052910 | METER INSTALLED | 2024-08-21
121 | 1000615902 | 11-BeckleyINJ-T1-Beckley-TAIWO AJALA HVDS 1 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Beckley | PUBLIC | POLE MOUNTED | METERED | 201508005105 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6619 | 3.3038 | 6 TAIWO AJALA |  |  |  | Aderalph | 060021050104 | METER INSTALLED | 2024-08-21
122 | 1001605119 | 11-BeckleyINJ-T1-Beckley-ADEWUNMI ADU HVDS 1 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Beckley | PUBLIC | POLE MOUNTED | METERED | 201508006327 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6636 | 3.3048 | 1 ADEWUNMI ADU |  |  |  | Aderalph | 060021051626 | METER INSTALLED | 2024-08-21
123 | 1001961413 | 11-BeckleyINJ-T1-Beckley-OYE ELEGUNDE HVDS 3 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Beckley | PUBLIC | POLE MOUNTED | METERED | 60019060019 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.665 | 3.3004 | 22, OYE ELEGUNDE |  |  |  | Aderalph | 060021052570 | METER INSTALLED | 2024-08-21
124 | 1000281529 | 11-BeckleyINJ-T1-Agbe road-CHURCH HVDS 1 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | METERED | 60017070064 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6697 | 3.3056 | 2 CHURCH STR OFF FUNSHO OWOYEMI |  |  |  | Aderalph | 060021051143 | METER INSTALLED | 2024-08-21
125 | 1000283045 | 11-Ijaiye OjokoroINJ-T1-Jankara-ADEGUNWA STREET HVDS 2 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-Ijaiye OjokoroINJ-T1-Jankara | PUBLIC | POLE MOUNTED | METERED | 201508007646 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6708 | 3.2951 | 14 DAYO ADEGUNWA |  |  |  | Aderalph | 060021051342 | METER INSTALLED | 2024-08-23
126 | 1000283036 | 11-Ijaiye OjokoroINJ-T1-Jankara-ADIGUN STREET HVDS 2 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-Ijaiye OjokoroINJ-T1-Jankara | PUBLIC | POLE MOUNTED | METERED | 201508006490 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6713 | 3.2957 | 10 ADIGUN |  |  |  | Aderalph | 060021050496 | METER INSTALLED | 2024-08-23
127 | 1000454958 | 11-Ijaiye OjokoroINJ-T1-Jankara-CHURCH STREET HVDS 1 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-Ijaiye OjokoroINJ-T1-Jankara | PUBLIC | POLE MOUNTED | METERED | 201508007213 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6714 | 3.2971 | 5 CHURCH |  |  |  | Aderalph | 060021050084 | METER INSTALLED | 2024-08-23
128 | 1000254352 | 11-Ijaiye OjokoroINJ-T1-Jankara-AKANBI ADENIRAN HVDS 4 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-Ijaiye OjokoroINJ-T1-Jankara | PUBLIC | POLE MOUNTED | METERED | 60020122607 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.672 | 3.3039 | NO 16 AKANBI ADENIRAN |  |  |  | Aderalph | 060021050485 | METER INSTALLED | 2024-08-24
129 | 1000283148 | 11-Ijaiye OjokoroINJ-T1-Jankara-CHURCH STREET HVDS 2 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-Ijaiye OjokoroINJ-T1-Jankara | PUBLIC | POLE MOUNTED | METERED | 201508007207 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.672 | 3.2974 | 17 CHURCH |  |  |  | Aderalph | 060021050551 | METER INSTALLED | 2024-08-23
130 | 1000283164 | 11-Ijaiye OjokoroINJ-T1-Jankara-ADIGUN STREET HVDS 4 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-Ijaiye OjokoroINJ-T1-Jankara | PUBLIC | POLE MOUNTED | METERED | 201508004400 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6725 | 3.2944 | 2A ADIGUN |  |  |  | Aderalph | 060021050028 | METER INSTALLED | 2024-08-23
131 | 1000230571 | 11-Ijaiye OjokoroINJ-T1-Jankara-AJOKE OSHO HVDS 1 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-Ijaiye OjokoroINJ-T1-Jankara | PUBLIC | POLE MOUNTED | METERED | 60017070960 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6726 | 3.3034 | NO 1/2 AJOKE OSHO |  |  |  | Aderalph | 060021051069 | METER INSTALLED | 2024-08-23
132 | 100375840 | W.J. BUSH & COMPANY LTD |  | IKEJA | OGBA | OGBA | 11-OgbaINJ-T3-Oba Akran | 50 | Complete Installation | Whole current meter | Batch 2 | [9 empty] | SHAPARA STREET OLD A/C NO 25/06/02/15519 IKEJA |  |  |  | vicbonny | 60021051084 | METER INSTALLED | 2024-08-12
133 | 0100364128 | COL. STEVE IDEHENRI |  | IKEJA | OBA AKRAN | OBA AKRAN | 11-OjoduINJ-T2-Express | PUBLIC | Complete Installation | Whole current meter | Batch 2 | well done | [8 empty] | PLT 447A OMOTUNDE AKINSOLA LAGOS |  |  |  | vicbonny | 60021052879 | METER INSTALLED | 2024-08-15
134 | 0101666306 | NIGERIA COMPUTER SOCIETY |  | IKEJA | OBA AKRAN | OBA AKRAN | 11-SecretariatINJ-T1-Estate | 50 | Complete Installation | Whole current meter | Batch 2 | well done | [8 empty] | OTUNBA JOBI FELE WAY, IKEJA |  |  |  | MAYFAK | 60021051742 | METER INSTALLED | 2024-10-31 | METER PREVIOUSLY INSTALL WAS 60021052788 ON 15/08/2024 BY VICBONNY BUT WAS HAVING PHASE ISSUE AND NEW WC HAS BEEN INSTALLED 60021051742 BY MAYFAK
135 | 1000255458 | 11-MongoroINJ-T1-Sule-HVDS 2 SEBIOTIMO STREET | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201508004824 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6101 | 3.3277 | SEBIOTIMO STREET, OGBA TYRE, MANGORO |  |  |  | vicbonny | 060021052272 | METER INSTALLED | 2024-09-07
136 | 1000263987 | 11-MongoroINJ-T1-Sule-HVDS 10 IKUOMOLA STREET | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 60019060592 | Faulty | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6082 | 3.3197 | IKUOMOLA STREET, CEMENT |  |  |  | vicbonny | 060021051070 | METER INSTALLED | 2024-09-07
137 | 1000255339 | 11-MongoroINJ-T1-Sule-HVDS 11 SULE STREET | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201505002495 | Faulty | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.609 | 3.324 | SULE STREET MANGORO |  |  |  | vicbonny | 060021051073 | METER INSTALLED | 2024-09-07
138 | 1000265884 | 11-MongoroINJ-T1-Sule-HVDS 2 ALFA YUSUF STREET | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201508004659 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6068 | 3.3149 | YUSUF STREET, OFF UNION RD, DOPEMU |  |  |  | vicbonny | 060021052781 | METER INSTALLED | 2024-09-07
139 | 1000255345 | 11-MongoroINJ-T1-Sule-HVDS 4 TALABI STREET | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201508003633 | Faulty | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6098 | 3.3264 | TALABI STREET, OFF SULE STREET, MANGORO |  |  |  | vicbonny | 060021052913 | METER INSTALLED | 2024-09-07
140 | 1000262236 | 11-MongoroINJ-T1-Sule-HVDS 5 FISHER STREET | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201508006310 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6093 | 3.3197 | FISHER STREET, OFF ADEBISI STREET, MANGORO |  |  |  | vicbonny | 060021052617 | METER INSTALLED | 2024-09-07
141 | 1000255085 | 11-MongoroINJ-T1-Sule-HVDS 3 ALFA NLA ROAD | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 60021051939 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6196 | 3.3203 | ALFA NLA ROAD, AGEGE |  |  |  | TEE N BEE | 060021050024 | METER INSTALLED | 2024-09-07
142 | 1000255240 | 11-MongoroINJ-T1-Sule-HVDS 14 ALFA NLA ROAD | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201508005569 | Faulty | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6196 | 3.3206 | ABUDU OLADEJO STREET, OFF ALFA NLA ROAD, AGEGE |  |  |  | TEE N BEE | 060021051004 | METER INSTALLED | 2024-09-07
143 | 1000280346 | 11-MongoroINJ-T1-Sule-HVDS 2 ALFA NLA ROAD | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201508006285 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6224 | 3.3197 | ALFA NLA ROAD, AGEGE |  |  |  | TEE N BEE | 060021052067 | METER INSTALLED | 2024-09-07
144 | 1002207924 | 11-IsheriINJ-T1-Bankole-30 FELICIA OKE STREET CSP | Band A | SHOMOLU | OLOWORA | MAGODO MEGA | 11-IsheriINJ-T1-Bankole | PUBLIC | POLE MOUNTED | METERED | 60020122341 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6313 | 3.3749 | 30 FELICIA OKE STREET |  |  |  | TEE N BEE | 060021050421 | METER INSTALLED | 2024-09-05
145 | 1000260060 | 11-Oke IraINJ-T2-Kayode-379/380 GEORGE CRESCENT | Band A | IKEJA | OGBA | OGBA | 11-Oke IraINJ-T2-Kayode | PUBLIC | POLE MOUNTED | METERED | 201508006678 | Faulty | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6333 | 3.3501 | PLOT 379, GEORGE CRESCENT |  |  |  | TEE N BEE | 060021050486 | METER INSTALLED | 2024-09-07
146 | 1000258436 | 11-Oke IraINJ-T2-Kayode-BLK 1 BODUNRIN HVDS 25KVA | Band A | IKEJA | OGBA | OGBA | 11-Oke IraINJ-T2-Kayode | PUBLIC | POLE MOUNTED | METERED | 201508003587 | Faulty | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6305 | 3.3395 | DAVID BOURIN CAULCRICK CLOSE, AGUDA, BY CATERPILLAR BUS STOP |  |  |  | TEE N BEE | 060021051146 | METER INSTALLED | 2024-09-07
147 | 1000261260 | 11-AgegeINJ-T2-Abule Egba-LABAK EST(SYLVAT AVE) POLE 4 | Band C | AKOWONJO | ORILE-AGEGE | ORILE-AGEGE | 11-AgegeINJ-T2-Abule Egba | PUBLIC | POLE MOUNTED | METERED | 201508003455 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6441 | 3.3091 | PLOT 21B TREM CHURCH LABAK ESTATE |  |  |  | SYSFIX | 060021052315 | METER INSTALLED | 2024-09-06
148 | 1000260143 | 11-AgegeINJ-T2-Abule Egba-AYOPEJU OLUDAYO CLOSE POLE 3 | Band C | AKOWONJO | ORILE-AGEGE | ORILE-AGEGE | 11-AgegeINJ-T2-Abule Egba | PUBLIC | POLE MOUNTED | METERED | 201508003524 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6442 | 3.3075 | PLOT 6 CONERSTONE CLOSE LABAK ESTATE |  |  |  | SYSFIX | 060021052163 | METER INSTALLED | 2024-09-06
149 | 1000259907 | 11-AgegeINJ-T2-Abule Egba-LABAK EST(TIMOTHY BABATUNDE) POLE 3 | Band C | AKOWONJO | ORILE-AGEGE | ORILE-AGEGE | 11-AgegeINJ-T2-Abule Egba | PUBLIC | POLE MOUNTED | METERED | 201508005606 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.645 | 3.308 | PLOT15 LABAK ESTATE |  |  |  | SYSFIX | 060021050424 | METER INSTALLED | 2024-09-06
150 | 1000260241 | 11-AgegeINJ-T2-Abule Egba-ABIMBOLA AWOLIYI EST(PEACE BOULEVARD) POLE 5 | Band C | AKOWONJO | ORILE-AGEGE | ORILE-AGEGE | 11-AgegeINJ-T2-Abule Egba | PUBLIC | POLE MOUNTED | METERED | 201508007410 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6493 | 3.3132 | PEACE BOULEVARD, ABIMBOLA AWOLIYI ESTATE, OFF OLD OKO OBA RD, OKO OBA |  |  |  | SYSFIX | 060021050121 | METER INSTALLED | 2024-09-06
151 | 1000264717 | 11-AgegeINJ-T2-Abule Egba-DASILVA STREET POLE 4 | Band C | AKOWONJO | ORILE-AGEGE | ORILE-AGEGE | 11-AgegeINJ-T2-Abule Egba | PUBLIC | POLE MOUNTED | METERED | 60020122092 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6524 | 3.3131 | DA SILVA STREET, OFF OLD ABEOKUTA RD, NEW OKO OBA |  |  |  | SYSFIX | 060021051045 | METER INSTALLED | 2024-09-06
152 | 1000261264 | 11-AgegeINJ-T2-Abule Egba-PIPELINE STREET POLE 6 | Band C | AKOWONJO | ORILE-AGEGE | ORILE-AGEGE | 11-AgegeINJ-T2-Abule Egba | PUBLIC | POLE MOUNTED | METERED | 201508005028 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6548 | 3.32 | PIPELINE RD, NEW OKO OBA |  |  |  | SYSFIX | 060021050188 | METER INSTALLED | 2024-09-06
153 | 1000264725 | 11-AgegeINJ-T2-Abule Egba-OLUKAYODE ADEGBOYEGA STR., POLE 4 | Band C | AKOWONJO | ORILE-AGEGE | ORILE-AGEGE | 11-AgegeINJ-T2-Abule Egba | PUBLIC | POLE MOUNTED | METERED | 60019060683 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6558 | 3.317 | OLUKAYODE ADEGBOYEGA STREET, OFF ANJUWON STREET, NEW OKO OBA |  |  |  | SYSFIX | 060021050440 | METER INSTALLED | 2024-09-06
154 | 1000270905 | 11-MongoroINJ-T1-Sule-HVDS 1 DISU AKOGUN STREET | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201508006916 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6158 | 3.3157 | DISU AKOGUN STREET,OFF KADIRI STREET, ONIWAYA ROAD, AGEGE |  |  |  | MAYFAK | 060021050187 | METER INSTALLED | 2024-09-07
155 | 1000270649 | 11-MongoroINJ-T1-Sule-HVDS 12 ONIWAYA ROAD | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201608010927 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6146 | 3.3186 | ONIWAYA ROAD, AGEGE |  |  |  | MAYFAK | 060021052583 | METER INSTALLED | 2024-09-07
156 | 1000270852 | 11-MongoroINJ-T1-Sule-HVDS 14 ONIWAYA ROAD | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201508006468 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6135 | 3.3174 | ONIWAYA ROAD,AGEGE |  |  |  | MAYFAK | 060021050487 | METER INSTALLED | 2024-09-07
157 | 1000270651 | 11-MongoroINJ-T1-Sule-HVDS 3 DISU AKOGUN STREET | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201508006925 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6154 | 3.315 | DISU AKOGUN STREET,OFF KADIRI STREET, ONIWAYA ROAD, AGEGE |  |  |  | MAYFAK | 060021050495 | METER INSTALLED | 2024-09-07
158 | 1000273659 | 11-MongoroINJ-T1-Sule-HVDS 5 ADEBANJO STREET | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201508006044 | Faulty | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6135 | 3.3151 | ADEBANJO STREET, OFF HASSAN OYO STREET,ONIWAYA ROAD,AGEGE |  |  |  | MAYFAK | 060021050425 | METER INSTALLED | 2024-09-07
159 | 1002259406 | 11-Agodo EgbeINJ-T1-Abanishe-215 & 216 OYESILE ST | Band B | OSHODI | IKOTUN | IKOTUN | 11-Agodo EgbeINJ-T1-Abanishe | PUBLIC | POLE MOUNTED | METERED | 60017111657 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5256 | 3.2827 | 29 OYESILE ST, IKOTUN |  |  |  | VICBONNY | 060021050661 | METER INSTALLED | 2024-09-10
160 | 1001802443 | 11-Agodo EgbeINJ-T1-Abanishe-151 & 152 ODEYALE STR | Band B | OSHODI | IKOTUN | IKOTUN | 11-Agodo EgbeINJ-T1-Abanishe | PUBLIC | POLE MOUNTED | METERED | 60017111338 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5291 | 3.2829 | ODEYALE STR. AGODO EGBE |  |  |  | VICBONNY | 060021052560 | METER INSTALLED | 2024-09-10
161 | 1002684956 | 11-Agodo EgbeINJ-T1-Abanishe-73 & 74 OGBEWI STREET | Band B | OSHODI | IKOTUN | IKOTUN | 11-Agodo EgbeINJ-T1-Abanishe | PUBLIC | POLE MOUNTED | METERED | 60019060396 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5312 | 3.2831 | OGBEWI STREET, AGODO EGBE , IKOTUN |  |  |  | VICBONNY | 060021051008 | METER INSTALLED | 2024-09-10
162 | 1002040416 | 11-Agodo EgbeINJ-T1-Abanishe-10 LAWRENCE STREET (POLE 27 & 28) | Band B | OSHODI | IKOTUN | IKOTUN | 11-Agodo EgbeINJ-T1-Abanishe | PUBLIC | POLE MOUNTED | METERED | 60017111112 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5356 | 3.2798 | LAWRENCE STREET, AGODO EGBE. |  |  |  | VICBONNY | 060021052615 | METER INSTALLED | 2024-09-10
163 | 1000295447 | 11-BeckleyINJ-T1-Agbe road-FUNSHO OWOYEMI HVDS 4 | BAND A | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | METERED | 60019060759 | FUNCTIONAL | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6708 | 3.3031 | 23 FUNSHO OWOYEMI |  |  |  | MAYFAK | 060021051888 | METER INSTALLED | 2024-09-10
164 | 1003310554 | 11-Abule TaylorINJ-T1-Bode Williams-38, ASSOCIATION | BAND A | AKOWONJO | ABULE-TAYLOR | ABULE-TAYLOR | 11-Abule TaylorINJ-T1-Bode Williams | PUBLIC | POLE MOUNTED | METERED | 60019060996 | FAULTY | MOJEC | 50 | CONNECTED | NOT COMMISSIONED | HEALTHY | ACTIVE | 6.6535 | 3.2846 | 38, ASSOCIATION |  |  |  | MAYFAK | 060021051111 | METER INSTALLED | 2024-09-10
165 | 1002259914 | 11-Agodo EgbeINJ-T1-Kudaki-133 &134 OLUWASEYI STREET | BAND A | OSHODI | IKOTUN | IKOTUN | 11-Agodo EgbeINJ-T1-Kudaki | PUBLIC | POLE MOUNTED | METERED | 60019060197 | FUNCTIONAL | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5299 | 3.2814 | OLUWASEYI STREET, IKOTUN |  |  |  | MAYFAK | 060021050459 | METER INSTALLED | 2024-09-10
166 | 1000260051 | 11-Oke IraINJ-T2-Kayode-385/386 GEORGE CRESCENT | BAND A | IKEJA | OGBA | OGBA | 11-Oke IraINJ-T2-Kayode | PUBLIC | POLE MOUNTED | METERED | 201508007508 | FUNCTIONAL | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6324 | 3.3501 | 385, GEORGE CRESENT STREET OFF WEMCO ROAD |  |  |  | MAYFAK | 060021051159 | METER INSTALLED | 2024-09-18
167 | 1000273860 | 11-BeckleyINJ-T1-Agbe road-AGBE ROAD HVDS 2 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | METERED | 201508005290 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6563 | 3.3072 | NO 20 AGBE ROAD |  |  |  | SYSFIX | 060021051163 | METER INSTALLED | 2024-09-13
168 | 1000266523 | 11-BeckleyINJ-T1-Agbe road-ALHAJA RAMOTA HVDS 4 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | METERED | 201508004888 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6552 | 3.3089 | 4 ALHAJA RAMOTA |  |  |  | SYSFIX | 060021050924 | METER INSTALLED | 2024-09-13
169 | 1000273753 | 11-BeckleyINJ-T1-Agbe road-OLANIYI HVDS 1 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | METERED | 201508006879 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6549 | 3.3101 | 2 OLANIYI STR |  |  |  | SYSFIX | 060021050666 | METER INSTALLED | 2024-09-13
170 | 1000274105 | 11-BeckleyINJ-T1-Agbe road-SANNI BALOGUN HVDS 2 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | METERED | 201508005284 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6579 | 3.3066 | 11 SANNI BALOGUN |  |  |  | SYSFIX | 060021050339 | METER INSTALLED | 2024-09-13
171 | 1000267083 | 11-Oke IraINJ-T1-Oke Ira-BABATUNDE 4 HVDS | Band A | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Oke Ira | PUBLIC | POLE MOUNTED | METERED | 60020122432 | Faulty | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6405 | 3.3391 | BABATUNDE STREET OFF AINA AJOBO IJAIYE OGBA |  |  |  | TEE N BEE | 060021051270 | METER INSTALLED | 2024-09-13
172 | 1000267095 | 11-Oke IraINJ-T1-Oke Ira-SHODEKE 1 HVDS | Band A | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Oke Ira | PUBLIC | POLE MOUNTED | METERED | 201508004921 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6411 | 3.3398 | 1 SHODEKE STREET, OKE IRA |  |  |  | TEE N BEE | 060021052313 | METER INSTALLED | 2024-09-13
173 | 1000267652 | 11-Oke IraINJ-T1-Oke Ira-OLUWATOYIN 8A HVDS | Band A | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Oke Ira | PUBLIC | POLE MOUNTED | METERED | 201508004913 | Faulty | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6389 | 3.3407 | OLUWATOYIN STREET OFF OLUWASIJIBOMI STREET YAYA ABATAN AREA |  |  |  | TEE N BEE | 060021052179 | METER INSTALLED | 2024-09-13
174 | 1000267561 | 11-Oke IraINJ-T1-Oke Ira-FOLORUNSHO 17 HVDS | Band A | IKEJA | OKE-IRA | OKE-IRA | 11-Oke IraINJ-T1-Oke Ira | PUBLIC | POLE MOUNTED | METERED | 201508004914 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6393 | 3.3418 | FOLORUNSHO STREET OFF OLORUNFUNMI STREET IJAIYE OGBA |  |  |  | TEE N BEE | 060021052083 | METER INSTALLED | 2024-09-13
175 | 1000274134 | 11-BeckleyINJ-T1-Agbe road-KARONWI HVDS 2 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | METERED | 201508003750 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6521 | 3.3043 | 7 KARONWI |  |  |  | SYSFIX | 060021052796 | METER INSTALLED | 2024-09-13
176 | 1000274827 | 11-BeckleyINJ-T1-Agbe road-OWODE HVDS 7 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | METERED | 201508005490 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.654 | 3.309 | 9 SOCIAL CLUB RD OFF OWODE STREET |  |  |  | SYSFIX | 060021051001 | METER INSTALLED | 2024-09-13
177 | 1003952566 | 11-AlajaINJ-T1-Koloba-OSHIN ROAD | Band B | AKOWONJO | AYOBO | AYOBO | 11-AlajaINJ-T1-Koloba | PUBLIC | POLE MOUNTED | METERED | 60012110088 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5834 | 3.2099 | OSHIN ROAD AYOBO |  |  |  | VICBONNY | 060021050080 | METER INSTALLED | 2024-09-13
178 | 1003635902 | 11-ObawoleINJ-T1-Youdeowei-1 ALKAT HVDS | Band A | ABULE EGBA | IJU | IJU | 11-ObawoleINJ-T1-Youdeowei | PUBLIC | POLE MOUNTED | METERED | 201508007292 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.664 | 3.3269 | NO 1, ALKAT WAY IJU ISHAGA. |  |  |  | ADERALPH | 060021051758 | METER INSTALLED | 2024-09-13
179 | 1001604424 | 11-OgbaINJ-T1-Ijaye-HVDS (KEKE)-BLK 78 | BAND A | IKEJA | OGBA | OGBA | 11-OgbaINJ-T1-Ijaye | PUBLIC | POLE MOUNTED | METERED | 60017070264 | FUNCTIONAL | MOJEC | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6323 | 3.3322 | LSDPC PHASE 3 ESTATE GRA ZONE IFAKO |  |  |  | TEE N BEE | 060021051040 | METER INSTALLED | 2024-09-13
180 | 1002527922 | 11-Adeniyi JonesINJ-T1-Anifowoshe-1 OSHIFILA STREET | BAND A | IKEJA | ANIFOWOSHE | ANIFOWOSHE | 11-Adeniyi JonesINJ-T1-Anifowoshe | PUBLIC | POLE MOUNTED | METERED | 60019060883 | FUNCTIONAL | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6001 | 3.3354 | 1,OSHIFILA STR,IKEJA |  |  |  | TEE N BEE | 060021050441 | METER INSTALLED | 2024-09-13
181 | 1000263977 | 11-MongoroINJ-T1-Sule-HVDS 1 AFOLABI LAWAL STR | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201508004360 | Faulty | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6104 | 3.3251 | AFOLABI LAWAL ST. OFF |  |  |  | MAYFAK | 060021050633 | METER INSTALLED | 2024-09-18
182 | 1000265877 | 11-MongoroINJ-T1-Sule-HVDS 2 ADEYOOLA STREET | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201508004853 | Faulty | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6108 | 3.3157 | ADEYOOLA STREET , OFF SUBUOLA STREET , DOPEMU AGEGE |  |  |  | MAYFAK | 060021051445 | METER INSTALLED | 2024-09-18
183 | 1000263998 | 11-MongoroINJ-T1-Sule-HVDS 1 OGABI SQUARE | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201508004668 | Faulty | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6109 | 3.3269 | OGABI SQUARE, OFF SEBIOTIMO STREET, MANGORO |  |  |  | MAYFAK | 060021051813 | METER INSTALLED | 2024-09-18
184 | 1000255678 | 11-MongoroINJ-T1-Sule-HVDS 1 OGUNBAMBI STREET | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201508004690 | Faulty | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6118 | 3.3165 | OGUNBAMBI STREET, OFF SHITA STREET, DOPEMU AGEGE |  |  |  | MAYFAK | 060021050242 | METER INSTALLED | 2024-09-18
185 | 1002988500 | 11-Abule TaylorINJ-T1-Bode Williams-CSP 44 ONA OPEPO STREET | Band B | AKOWONJO | ABULE-TAYLOR | ABULE-TAYLOR | 11-Abule TaylorINJ-T1-Bode Williams | PUBLIC | POLE MOUNTED | METERED | 60019060139 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6525 | 3.2911 | NO. 44 ONA OPEPO STREET. |  |  |  | SYSFIX | 060021052666 | METER INSTALLED | 2024-09-18
186 | 1000270897 | 11-MongoroINJ-T1-Sule-HVDS 5 SARUMI ALAWO STREET | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201508006390 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6168 | 3.3174 | SARUMI ALAWO STREET, OFF ONIWAYA ROAD,AGEGE |  |  |  | TEE N BEE | 060021050714 | METER INSTALLED | 2024-09-18
187 | 1000270027 | 11-MongoroINJ-T1-New Dopemu-HVDS 6 ARIGIDI STREET | Band B | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-New Dopemu | PUBLIC | POLE MOUNTED | METERED | 201508005334 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6088 | 3.3298 | 1, ARIGIDI STREET |  |  |  | VICBONNY | 060021050460 | METER INSTALLED | 2024-09-18
188 | 1000255402 | 11-MongoroINJ-T1-Sule-HVDS 1 ABEOKUTA EXPRESS | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201508005365 | Faulty | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6085 | 3.3254 | ABEOKUTA EXPRESS WAY MANGORO BUS STOP. |  |  |  | VICBONNY | 060021050836 | METER INSTALLED | 2024-09-18
189 | 1002606897 | 11-AlapereINJ-T1-Bakare-NIPP BAlOGUN ILAWE 08 | Band B | SHOMOLU | KETU | ANTHONY MEGA | 11-AlapereINJ-T1-Bakare | PUBLIC | POLE MOUNTED | METERED | 60020122287 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5867 | 3.3944 | BALOGUN ILAWE STREET |  |  |  | VICBONNY | 060021050123 | METER INSTALLED | 2024-09-10
190 | 1002260904 | 11-WasimiINJ-T1-Araromi-50 AGIDI ROAD CSP | Band B | SHOMOLU | KETU | ANTHONY MEGA | 11-WasimiINJ-T1-Araromi | PUBLIC | POLE MOUNTED | METERED | 60019060663 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5911 | 3.4003 | DEMURIN STREET |  |  |  | VICBONNY | 060021051150 | METER INSTALLED | 2024-09-10
191 | 1003072698 | 11-WasimiINJ-T1-Araromi-23 AGIDI ROAD CSP | Band B | SHOMOLU | KETU | ANTHONY MEGA | 11-WasimiINJ-T1-Araromi | PUBLIC | POLE MOUNTED | METERED | 60019060046 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5929 | 3.4004 | 28 DEMURIN STREET, KETU |  |  |  | VICBONNY | 060021052697 | METER INSTALLED | 2024-09-15
192 | 1000259815 | 11-Oke IraINJ-T2-Kayode-9 FADARE STREET | Band A | IKEJA | IFAKO | IFAKO | 11-Oke IraINJ-T2-Kayode | PUBLIC | POLE MOUNTED | METERED | 201508004981 | Faulty | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6353 | 3.3365 | FADARE STREET OFF KAYODE OGBA LAGOS |  |  |  | TEE N BEE | 060021051889 | METER INSTALLED | 2024-09-18
193 | 1000259506 | 11-Oke IraINJ-T2-Kayode-30 ADERINTO STREET | Band A | IKEJA | IFAKO | IFAKO | 11-Oke IraINJ-T2-Kayode | PUBLIC | POLE MOUNTED | METERED | 201508005479 | Faulty | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6336 | 3.3389 | ADERITO STREET OFF ADEFENWA IJAIYE ROAD OGBA |  |  |  | TEE N BEE | 060021051154 | METER INSTALLED | 2024-09-18
194 | 1000273873 | 11-BeckleyINJ-T1-Agbe road-SANTOS HVDS 9 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | POLE MOUNTED | METERED | 60020122263 | Faulty | MOJEC | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6514 | 3.3045 | 11 SANTOS |  |  |  | SYSFIX | 060021051072 | METER INSTALLED | 2024-10-07
195 | 1000274800 | 11-BeckleyINJ-T1-Beckley-AROWOLO HVDS 3 | Band B | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Beckley | PUBLIC | POLE MOUNTED | METERED | 201508006540 | Faulty | CLOU | 50 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6533 | 3.3032 | 53 AROWOLO |  |  |  | SYSFIX | 060021051814 | METER INSTALLED | 2024-09-24
196 | 1001598607 | 11-IgbogboINJ-T2-Agbele-HVDS POLE 54A/54B |  | IKORODU | IGBOGBO | IGBOGBO | 11-IgbogboINJ-T2-Agbele | PUBLIC | POST-PAID | METERED | 60019060655 | FUNCTIONAL | MOJEC | 50 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5805 | 3.5312 | KEJIBO STREET IGBOGBO IKORODU | WC |  | 1001598607 | MAYFAK | 060021051155 | METER INSTALLED | 2024-12-12
197 | 1002527909 | 11-IjegunINJ-T2-Pipeline-397 & 398-KUDEBU ST OFF ISOLO RD |  | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Pipeline | PUBLIC | POLE MOUNTED | CIS | POST-PAID | FAULTY | MOJEC | 50 | WC | CONNECTED | COMMISSIONED | HEALTHY | 6.5137 | 3.264 | KUDEBU ST OFF ISOLO RD | WC | 1002527909 | Faulty Meter Replacement | MAYFAK | 060021052541 | METER INSTALLED | 2024-12-09
198 | 1000255433 | 11-MongoroINJ-T1-Sule-HVDS 1 KAMORU ALIMI STREET | Band C | AKOWONJO | DOPEMU | DOPEMU | 11-MongoroINJ-T1-Sule | PUBLIC | POLE MOUNTED | METERED | 201508004823 | Faulty | CLOU | 25 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6136 | 3.3272 | KAMORU ALIMI STREET, OGBA TYRE, MANGORO |  |  |  | MAYFAK | 060021051431 | METER INSTALLED | 2024-09-07
Note on C38: Energy Management: The feeder is Nathan but the DT feeding EKO is Oke Suna DT 500

## LVMD DATA ANALYSIS (hidden)
Row Labels | Count of METER NO
ADERALPH | 9
All solution | 3
DEMOL | 7
mayfak | 5
TEE N BEE | 3
(blank)
Grand Total | 27

## PROJECT 643 LVMD REPORT
S/N | CIS DT Numbers | New Unique DT Nomenclature | BU | UT | New UT Name | Feeder Name | Ownership | Installation Position | Acc Platform | Acc TYPE (PRE-PAID/POST-PAID) | Metering Status | Meter Number | Meter Functionality Status | Meter Type | Capacity | Meter Ratings | Connection Status | Commissioning Status | Maintenance Status | Disconnection Status | Coordinates (LAT) | Coordinates (LONG) | Addresses | Project | SBC | SBC PHONE NO | METER NO | INSTALLATION STATUS | INSTALLATION DATE | REMARK
1 | 1006025016 | 11-Oke AfaINJ-T2-Ilamose-TUNDE GANIYU | OSHODI | OKE-AFA | OKE-AFA | 11-Oke AfaINJ-T2-Ilamose | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.536318 | 3.310691 | ALH GANIYU STREET OKE AFA | PROJECT 643 | ADERALPH | 8151528316 | 60022033785 | INSTALLED | 2023-11-15
2 | 1006025201 | 11-IgandoINJ-T1-Egan-BENSON ADU 2 | OSHODI | IGANDO | IGANDO | 11-IgandoINJ-T1-Egan | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.546 | 3.2189 | ADEOLA OLAWALE ST. ISUTI RD, IGANDO. | PROJECT 643 | ADERALPH | 8151528316 | 60022032978 | INSTALLED | 2023-11-15
3 | 1006025202 | 33-EjigboTCN-IJEGUN-CHURCH GATE | OSHODI | IJEGUN | IJEGUN | 33-EjigboTCN-IJEGUN | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5022 | 3.2578 | ALONG IJE-ODODO IJEGUN. | PROJECT 643 | ADERALPH | 8151528316 | 60022033350 | INSTALLED | 2023-11-15 | REPLACEMENT OF BURNT METER UNDER PROJECT 843 060022031296
4 | 1003953410 | 33-EgbinTCN-OKE ELETU-ABATA CDA | IKORODU | IJEDE | IJEDE | 33-EgbinTCN-OKE ELETU | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | Gap | 60021080305 | N/A | MOJEC | 500 | 800/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.604 | 3.6395 | OKE ELETU, IJEDE | PROJECT 643 | DEMOL | 09021887242 | 60022033502 | INSTALLED | 2023-11-21
5 | 1006025018 | 11-AgegeINJ-T1-Oko Oba-BAMGBOYE 2 | ABULE EGBA | FAGBA | FAGBA | 11-AgegeINJ--T1-Oko-Oba | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6595 | 3.319836 | AMUSAN JUNCTION, OFF OLABODE STREET, BAMGBOYE AREA | PROJECT 643 | TEE N BEE | 8074952106 | 60022033824 | INSTALLED | 2023-11-26
6 | 1006024201 | 11-EpeINJ-T1-Township-OBA ANIMASHAUN DT | IKORODU | EPE | EPE | MAR | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5848 | 3.9546 | Along Oba Animashaun way, Epe | PROJECT 643 | DEMOL | 09021887242 | 60022031679 | INSTALLED | 2023-11-25
7 | 1006025021 | 33-IkoroduTCN-AGBOWA-HILLTOP NEWTOWN CDA | IKORODU | EPE | EPE | 33-IkoroduTCN-AGBOWA | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6031 | 3.9776 | KULANLA ROAD, OFF ADERIBIGBE STREET, OFF EPE ITOKIN ROAD, EPE | PROJECT 643 | DEMOL | 09021887242 | 60022033712 | INSTALLED | 2023-11-25
8 | 1001605934 | 11-PTCINJ-T2-Medical-OSUNDAIRO | IKEJA | PTC | PTC | 11-PTCINJ-T2-Medical | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5948 | 3.3394 | SOMOYE ST. OFF MEDICAL ROAD ROAD COMPUTER VILLAGE IKEJA | PROJECT 643 | All solution | 9098079569 | 60022033611 | INSTALLED | 2023-12-01
9 | 1006025601 | 11-IgandoINJ-T1-New Igando-IGANDO NEW TOWN CDA | OSHODI | IGANDO | IGANDO | 11-IgandoINJ-T1-New Igando | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | UNMETERED | NA | N/A | N/A | 300 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.57 | 3.2486 | AT ADESOLARIN STREET NEW IGANDO TOWN IGANDO. | PROJECT 643 | All solution | 9098079569 | 60022033396 | INSTALLED | 2023-12-16
10 | 1006025017 | 11-BolorunpeluINJ-T1-Idimu-AGBOGUNLERI 2 | OSHODI | IDIMU | IDIMU | 11-BolorunpeluINJ-T1-Idimu | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5718 | 3.287 | AGBOGUNLERI STREET IDIMU BUS-STOP | PROJECT 643 | All solution | 9098079569 | 60022033501 | INSTALLED | 2023-12-16
11 | 1006026401 | 11-AbesanINJ-T1-Ipaja-IFESOWAPO IKOLA ILUMO | AKOWONJO | IPAJA | IPAJA | 11-AbesanINJ-T1-Ipaja | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6211 | 3.254 | At Ifesowapo community off Ikola Road, Akowonjo | PROJECT 643 | ADERALPH | 8151528316 | 60022031176 | INSTALLED | 2023-12-18
12 | 1006025404 | 33-OdogunyanTCN-AGBEDE-GOD FIRST CDA | IKORODU | ODOGUNYAN | ODOGUNYAN | 33-OdogunyanTCN-AGBEDE | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | UNMETERED | NA | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6975 | 3.4605 | At Elepete, off Agric, Ikorodu | PROJECT 643 | DEMOL | 09021887242 | 60022033622 | INSTALLED | 2023-12-26
13 | 1006025403 | 11-IgbogboINJ-T1-Ofin-AyangaAdeIgbopa CDA | IKORODU | IGBOGBO | IGBOGBO | 11-IgbogboINJ-T1-Ofin | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | UNMETERED | NA | N/A | N/A | 300 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.546 | 3.5206 | At Igbopa Community, off Oreta road, Igbogbo Ikorodu | PROJECT 643 | DEMOL | 09021887242 | 60022032521 | INSTALLED | 2023-12-26
14 | 1006010401 | 33-IkoroduTCN-AGBOWA-GOD IS LOVE CDA | IKORODU | EPE | EPE | 33-IkoroduTCN-AGBOWA | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6636 | 3.6292 | At Majodo Phase II along Emuren, Ikorodu | PROJECT 643 | DEMOL | 09021887242 | 60022032842 | INSTALLED | 2023-12-26
15 | 1006026601 | 11-OgbaINJ-T1-Ijaye-LSDPC CASTLE ESTATE | IKEJA | OGBA | OGBA | 11-OgbaINJ-T1-Ijaye | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6272 | 3.3302 | LSDPC MEDIUM HOUSING ESTATE, PHASE 1, AGEGE STADIUM ROAD. | PROJECT 643 | ADERALPH | 8151528316 | 60022033029 | INSTALLED | 2024-01-19
16 | 1006027001 | 33-IkoroduTCN-IGBOGBO-MUSAMOT ABENI FKC CDA | IKORODU | IJEDE | IJEDE | 33-IkoroduTCN-IGBOGBO | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6081 | 3.5732 | MUSAMOT ABENI STREET, GINTI, FKC, ELEPE, IKORODU | PROJECT 643 | mayfak | 9050329971 | 60022033795 | INSTALLED | 2024-01-23
17 | 1006028401 | 33-IkoroduTCN-IJEDE-PROGRESSIVE CDA 2 | IKORODU | IJEDE | IJEDE | 33-IkoroduTCN-IJEDE | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6299 | 3.5819 | PROGRESSIVE CDA 2 | PROJECT 643 | mayfak | 9050329971 | 60022033238 | INSTALLED | 2024-01-23
18 | 1006025823 | 11-ShashaINJ-T1-Foursquare-IMALA ONA ARA | AKOWONJO | ABULE-ODU | ABULE-ODU | 11-ShashaINJ-T1-Foursquare | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5747 | 3.2906 | Located at 8, Yusuf Adeoye street, Idimu Lagos, | PROJECT 643 | mayfak | 9050329971 | 60022032979 | INSTALLED | 2024-01-24
19 | 1006025824 | 11-EkoroINJ--T2-Agbele-AINA AJAYI PHASE2 | AKOWONJO | ABORU | ABORU | 11-EkoroINJ--T2-Agbele | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6365 | 3.2762 | Located at off Meiran Lagos, Resident Association | PROJECT 643 | mayfak | 9050329971 | 60022033079 | INSTALLED | 2024-01-24
20 | 1000279710 | 11-BolorunpeluINJ-T1-Idimu-MADARIKAN | OSHODI | IDIMU | IDIMU | 11-BolorunpeluINJ-T1-Idimu | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | METERED | 60017112008 | FUNCTIONAL | MOJEC | 500 | 800/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5649 | 3.2719 | MADARIKAN STREET IDIMU IKOTUN | PROJECT 643 | MAYFAK | 9050329971 | 60022031719 | INSTALLED | 2024-01-29
21 | 1002486411 | 11-WasimiINJ-T2-Wasimi-S0HUKURA YAM MARKET | SHOMOLU | IKOSI | MAGODO MEGA | 11-WasimiINJ-T2-Wasimi | PRIVATE | GROUND MOUNTED | CIS | N/A | METERED | N/A | N/A | N/A | 500 | 800/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6088 | 3.3908 | AT MILE 12, KETU, LAGOS | PROJECT 643 | TEE N BEE | 8074952106 | 60022032427 | INSTALLED | 2024-01-25
22 | 1005118902 | 33-OdogunyanTCN-FAKALE MAYA-IFESOWAPO AJEBO | IKORODU | EPE | EPE | 33-OdogunyanTCN-FAKALE MAYA | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.7087 | 3.5651 | AJEBO JUNCTION FAKALE, OGUN STATE | PROJECT 643 | TEE N BEE | 8074952106 | 60022032604 | INSTALLED | 2024-01-28
23 | 1006025822 | 11-New AlausaINJ-T4-Allen-SOJI ADEPEGBA RESIDENCE | IKEJA | PTC | PTC | 11-New AlausaINJ-T4-Allen | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6041 | 3.3504 | NO. 1 SOJI ADEPEGAB CLOSE, OFF ALLEN AVENUE, IKEJA | PROJECT 643 | ADERALPH | 8151528316 | 60022031841 | INSTALLED | 2024-02-12
24 | 1006028601 | 11-PTCNJ-T8-Olowu-SEIDU DT | IKEJA | PTC | PTC | 11-PTCNJ-T8-Olowu | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5975 | 3.3447 | OFF OLOWU STREET 19 SEIDU AJIPOWU ST ALLEN IKEJA | PROJECT 643 | ADERALPH | 8151528316 | 60022033888 | INSTALLED | 2024-02-12
25 | 1006028001 | 11-OjoduINJ-T1-Ojodu-AKIODE CDA | IKEJA | OBA AKRAN | OBA AKRAN | 11-OjoduINJ-T1-Ojodu | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6383 | 3.3561 | 18 OGUNNUSI RD OJODU LAGOS 101233 LAGOS NIGERIA | PROJECT 643 | ADERALPH | 8151528316 | 60022032529 | INSTALLED | 2024-02-12
26 | 1006029001 | 11-AlajaINJ-T1-Fadayomi-IFELODUN OWODINA | AKOWONJO | AYOBO | AYOBO | 11-AlajaINJ-T1-Fadayomi | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5791 | 3.2427 | 16 Lawan Ode st idimu lagos | PROJECT 643 | ADERALPH | 8151528316 | 60022032913 | INSTALLED | 2024-02-12
27 | 1000257534 | 11-OdogunyanINJ-T1-Centex-ODOGUNYAN INJECTION | IKORODU | ODOGUNYAN | ODOGUNYAN | 11-OdogunyanINJ-T1-Centex | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | METERED | 60017111781 | FUNCTIONAL | MOJEC | 500 | 800/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6797 | 3.5248 | AGODO ALARA | PROJECT 643 | DEMOL | 09021887242 | 060022091220 | INSTALLED | 2024-02-07 | N:B METER INITIALLY INSTALLED IS '060022031725 AND WAS REPLACED WHEN IT DEVELOPED FAULTY WITH NEW METER 060022091220
28 | 1006028801 | 33-OdogunyanTCN-FAKALE MAYA-ITAPARA CDA DT | IKORODU | EPE | EPE | 33-OdogunyanTCN-FAKALE MAYA | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.7021 | 3.5638 |  | PROJECT 643 | TEE N BEE | 09021887242 | 60022032483 | INSTALLED | 2024-02-09
29 | 1006025401 | 11-SaboINJ-T2-Eyita-ALHAJA KADIJA MORAYO CDA | IKORODU | LASUNWON | LASUNWON | 11-SaboINJ-T2-Eyita | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | UNMETERED | NA | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.628 | 3.5003 | At Alhaja Morayo street, Olori Powerline CDA, Eyita Powerline, Ikorodu | PROJECT 643 | DEMOL | 09021887242 | 060022033814 | INSTALLED | 2024-02-24
30 | 1000259268 | 11-SaboINJ-T2-Lagos Road-LOWA | IKORODU | AYANGBUREN | AYANGBUREN | 11-SaboINJ-T2-Lagos Road | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | METERED | 201508003507 | FAULTY | CLOU | 500 | 800/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6233 | 3.4941 | LOWA ST | PROJECT 643 | QUINTEC | 07065706955 | 60022032439 | INSTALLED | 2024-05-17 | PREVIOUSLY INSTALLED BY DEMOL WITH PROJECT 843 METER WITH METER NO 60022031297 on 11/03/2024
31 | 1006030001 | 33-IkoroduTCN-AGBOWA-ALEKE PHASE2 ESTATE | IKORODU | EPE | EPE | 33-IkoroduTCN-AGBOWA | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6631 | 3.6067 |  | PROJECT 643 | TEE N BEE | 09021887242 | 60022033476 | INSTALLED | 2024-03-11
32 | 1000237900 | 11-IjegunINJ-T1-Obalagbe-OKERUBE | OSHODI | IKOTUN | IKOTUN | 11-IjegunINJ-T1-Obalagbe | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | Gap | 201505000761 | N/A | CLOU | 500 | 800/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5279 | 3.2363 | OKERUBE BUSTOP, ABARANJE ROAD IKOTUN | PROJECT 643 | TEE N BEE | 09021887242 | 60022032719 | INSTALLED | 2024-03-11
33 | 1006019602 | 33-OtaTCN-AMJE-AYINLA ADAMS 2 | ABULE EGBA | IJAIYE | IJAIYE | 33-OtaTCN-AMJE | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.675 | 3.2822 | Sherifat Banire, off Taibat Banire street, Ojokoro LCDA, Ifako LGA, Abule Egba BU | PROJECT 643 | MAYFAK | 9050329971 | 60022033104 | INSTALLED | 2024-03-11
34 | 1006029401 | 11-IgbogboINJ-T1-Ofin-UPS STAFF COOPERATIVE ESTATE CDA DT | IKORODU | IGBOGBO | IGBOGBO | 11-IgbogboINJ-T1-Ofin | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.564 | 3.5224 |  | PROJECT 643 | QUINTEC | 07065706955 | 60022033894 | INSTALLED | 2024-05-17 | PREVIOUSLY INSTALLED BY DEMOL WITH PROJECT 843 METER WITH METER NO 60022033796 on 14/03/2024
35 | 1003370522 | 33-EgbinTCN-OKE ELETU-IREAKARI CDA | IKORODU | IJEDE | IJEDE | 33-EgbinTCN-OKE ELETU | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6223 | 3.6509 | IMOTA, IKORODU | PROJECT 643 | DEMOL | 09021887242 | 60022033954 | INSTALLED | 2024-03-24
36 | 1006030201 | 11-OdogunyanINJ-T2-Ita Oluwo-Upright CDA | IKORODU | ODOGUNYAN | ODOGUNYAN | 11-OdogunyanINJ-T2-Ita Oluwo | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.683 | 3.4767 |  | PROJECT 643 | DEMOL | 09021887242 | 60022031664 | INSTALLED | 2024-03-15
37 | 1006030401 | 33-IkoroduTCN-IJEDE-Peace CDA | IKORODU | IJEDE | IJEDE | 33-IkoroduTCN-IJEDE | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5676 | 3.5739 |  | PROJECT 643 | DEMOL | 09021887242 | 60022032843 | INSTALLED | 2024-03-15
38 | 1003953406 | 33-EgbinTCN-OKE ELETU-IGBOPA LONDON PHASE 2 | IKORODU | IJEDE | IJEDE | 33-EgbinTCN-OKE ELETU | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5817 | 3.6081 | IGBOPA LONDON PHASE 2, OKE ELETU, IJEDE | PROJECT 643 | DEMOL | 09021887242 | 60022032924 | INSTALLED | 2024-03-14
39 | 1004872022 | 33-Oke-AroTCN-AKUTE-BEACHLAND | SHOMOLU | OLOWORA | MAGODO MEGA | 33-Oke-AroTCN-AKUTE | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.698 | 3.4365 | GBAYIDE SOMUYIWA | PROJECT 643 | TEE N BEE | 09021887242 | 60022033806 | INSTALLED | 2024-03-16
40 | 1006028201 | 11-BolorunpeluINJ-T3-Governor- PEACE EST IV CDA | OSHODI | IDIMU | IDIMU | 11-BolorunpeluINJ-T3-Governor | PUBLIC | GROUND | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.570989 | 3.257583 | SALVATION ARMY STREET, OFF GOVERNOR ROAD , IKOTUN | PROJECT 643 | TEE N BEE | 09021887242 | 60022032610 | INSTALLED | 2024-03-13
41 | 1006027801 | 11-Ago OkotaINJ-T2-Oke Ogbere-OLANREWAJU 2 | OSHODI | AGO | AGO | 11-Ago OkotaINJ-T2-Oke Ogbere | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5015 | 3.2969 | OLANREWAJU STREET DIVINE ESTATE AGO | PROJECT 643 | TEE N BEE | 09021887242 | 60022033176 | INSTALLED | 2024-03-14
42 | 1006025802 | 33-Oke-AroTCN-AKUTE-IBOKO 2 | ABULE EGBA | AKUTE | AKUTE | 33-Oke-AroTCN-AKUTE | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.663 | 3.3807 | SALAMI STREET, IBOKO, OGUN STATE | PROJECT 643 | MAYFAK | 9050329971 | 60022032426 | INSTALLED | 2024-03-13
43 | 1006019603 | 11-MongoroINJ-T1-New Dopemu-OREMEJI RELIEF DT | AKOWONJO | EGBEDA | EGBEDA | 11-MongoroINJ-T1-New Dopemu | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6046 | 3.3255 | Oremeji, off Onipetesi, Idi Mangoro Ikeja LGA | PROJECT 643 | MAYFAK | 9050329971 | 60022032987 | INSTALLED | 2024-03-12
44 | 1006030601 | 33-EgbinTCN-OKE ELETU-OKEAGBO DT | IKORODU | IJEDE | IJEDE | 33-EgbinTCN-OKE ELETU | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6072 | 3.649 | NA | PROJECT 643 | TEE N BEE | 09021887242 | 60022033584 | INSTALLED | 2024-03-25
45 | 1006025402 | 11-BolorunpeluINJ-T1-Isijola-IREPO 3 | OSHODI | IKOTUN | IKOTUN | 11-BolorunpeluINJ-T1-Isijola | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5495 | 3.2539 | AT 62 OSUMBA STREET IKOTUN | PROJECT 643 | MAYFAK | 9050329971 | 60022033906 | INSTALLED | 2024-03-25
46 | 1006030801 | 33-IkoroduTCN-IPAKODO-LAGOON VIEW ESTATE CDA | IKORODU | IGBOGBO | IGBOGBO | 33-IkoroduTCN-IPAKODO | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5855 | 3.4875 | IPAKODO-LAGOON VIEW ESTATE CDA | PROJECT 643 | DEMOL | 09021887242 | 60022033068 | INSTALLED | 2024-04-08
47 | 1001598531 | 33-IkoroduTCN-AGBOWA-ERERUFU | IKORODU | EPE | EPE | 33-IkoroduTCN-AGBOWA | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | FAULTY | INACTIVE | 6.6453 | 3.8481 | ITOIKIN EPE ROAD ERERUFU | PROJECT 643 | TEE N BEE | 09021887242 | 60022031887 | INSTALLED | 2024-03-27
48 | 1000208427 | 11-ObawoleINJ-T1-Youdeowei-MEDOVILLA | ABULE EGBA | IJU | IJU | 11-ObawoleINJ-T1-Youdeowei | PUBLIC | GROUND | CIS | POST-PAID | Gap | 60016110241 | FAULTY | MOJEC | 100 | 200/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6631 | 3.323 | 215/217 IJU ROAD | LIGHT UP LAGOS | MAYFAK | 9050329971 | 60021080958 | INSTALLED | 2024-04-26
49 | 1006032604 | 11-IlupejuINJ-T4-Ikorodu-OLOLADE BENSON CDA | IKEJA | PTC | PTC | 11-IlupejuINJ-T4-Ikorodu | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5695 | 3.3658 | OLADE BENSON ELEKO, ONIGBOGBO, MARYLAND | PROJECT 643 | ADERALPH | 8151528316 | 60022033522 | INSTALLED | 2024-05-10
50 | 1006032801 | 11-OjoduINJ-T1-Ojodu-OJODU CDA | IKEJA | OJODU | OJODU | 11-OjoduINJ-T1-Ojodu | PUBLIC | GROUND | CIS | POST PAID | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6449 | 3.3652 | ZINSOU OFF AINA STREET, OJODU B/STOP, OJODU | PROJECT 643 | ADERALPH | 8151528316 | 60022032517 | INSTALLED | 2024-05-10
51 | 1006032603 | 11-SecretariatINJ-T1-Lateef Jakande-AKIODE 2 CDA | IKEJA | OJODU | OJODU | 11-SecretariatINJ-T1-Lateef Jakande | PUBLIC | GROUND | CIS | POST PAID | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6373 | 3.3553 | OPPOSITE ZENITH BANK OGUNUSI ROAD OJODU | PROJECT 643 | ADERALPH | 8151528316 | 60022033149 | INSTALLED | 2024-05-10
52 | 1006034001 | 33-AlausaTCN-OPIC-PALMS HAVEN CDA | SHOMOLU | MAGODO MEGA | MAGODO MEGA | 33-AlausaTCN-OPIC | PUBLIC | GROUND | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6426 | 3.398 | PALM HAVEN CDA OPIC | PROJECT 643 | ADERALPH | 8151528316 | 60022032761 | INSTALLED | 2024-05-10
53 | 1006032002 | 33-OdogunyanTCN-AGBEDE-Gloryland Omolaiye CDA | IKORODU | IJEDE | IJEDE | 33-OdogunyanTCN-AGBEDE | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6799 | 3.4862 | At Progressive street, Agbede Transformer, Ikorodu Lagos State | PROJECT 643 | TEE N BEE | 09021887242 | 60022033166 | INSTALLED | 2024-05-15
54 | 1006032001 | 33-EgbinTCN-OKELETU-Igbangbe Phase ll CDA | IKORODU | ODOGUNYAN | ODOGUNYAN | 33-EgbinTCN-OKE ELETU | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5899 | 3.6373 | At Agura Gberigbe Road C/P Bus-stop, Agura Ikorodu Lagos State | PROJECT 643 | TEE N BEE | 09021887242 | 60022031901 | INSTALLED | 2024-05-21
55 | 1006032201 | 33-IkoroduTCN-AGBOWA- OKE SABO CDA | IKORODU | EPE | EPE | 33-IkoroduTCN-AGBOWA | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6711 | 3.6632 |  | PROJECT 643 | TEE N BEE | 09021887242 | 60022033662 | INSTALLED | 2024-05-22
56 | 1006032202 | 33-IkoroduTCN-IJEDE-Igbe-Ogunro Joint CDA | IKORODU | IJEDE | IJEDE | 33-IkoroduTCN-IJEDE | PUBLIC | GROUND | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5702 | 3.5725 |  | PROJECT 643 | TEE N BEE | 09021887242 | 60022033548 | INSTALLED | 2024-05-15
57 | 1006032401 | 33-IkoroduTCN-AGBOWA-Sacred Heart Estate | IKORODU | EPE | EPE | 33-IkoroduTCN-AGBOWA | PUBLIC | GROUND | CIS | N/A | UNMETERED | N/A | N/A | N/A | 200 | 300/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6857 | 3.7115 | Odo Onasa Agbowa Ikosi Epe Ikorodu, Lagos | PROJECT 643 | TEE N BEE | 09021887242 | 60022033730 | INSTALLED | 2024-05-22
58 | 1000005002 | 33-Oke-AroTCN-AKUTE-NANSO AKPAN | SHOMOLU | OLOWORA | MAGODO MEGA | 33-Oke-AroTCN-AKUTE | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6375 | 3.4108 | NANSOAKPAN STREET, ISHERI NORTH ESTATE | PROJECT 643 | QUINTEC | 07065706955 | 60022032909 | INSTALLED | 2024-05-17
59 | 1004499976 | 11-OworoINJ-T1-Ifako-ABUBAKAR ODUTAN LASISI | SHOMOLU | OWORO | OWOROSHONKI MEGA | 11-OworoINJ-T1-Ifako | PUBLIC | POLE MOUNTED | CIS | POST-PAID | Gap | 60012064611 | HEALTHY | MOJEC | 100 | 200/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5549 | 3.3913 | 1 BABALOLA STREET, GBAGADA, OWORO | LIGHT UP LAGOS | MAYFAK | 9050329971 | 60020123655 | INSTALLED | 2024-05-14
60 | 1006032601 | 11-IjegunINJ-T2-Pipeline-HARMONY 2 | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T2-Pipeline | PUBLIC | GROUND MOUNTED | CIS | POST PAID | UNMETERED | N/A | N/A | N/A | 300 | 500/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.4984 | 3.2709 | OFF EKENE UDEH ASIWAJU STRT,FAGBILE PHASE 3 IJEGUN | PROJECT 643 | TEE N BEE | 09021887242 | 60022032713 | INSTALLED | 2024-05-29
61 | 1000229080 | 11-IjegunINJ-T1-Ikotun-WILLIAMS SHOTUNDE | OSHODI | IJEGUN | IJEGUN | 11-IjegunINJ-T1-Ikotun | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | Gap | 201505001838 | N/A | CLOU | 500 | 800/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.542 | 3.2633 | IJEGUN IKOTUN ROAD | PROJECT 643 | QUINTEC | 07065706955 | 60022032782 | INSTALLED | 2024-05-28
62 | 1000254484 | 11-Ilupeju BypassINJ-T1-Bypass-TOWN PLANNING III | SHOMOLU | ILUPEJU | ILUPEJU MEGA | 11-Ilupeju BypassINJ-T1-Bypass | PUBLIC | GROUND MOUNTED | CIS | POST-PAID | METERED | 60016111854 | FUNCTIONAL | MOJEC | 300 | 500/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5567 | 3.3573 | 40/42 TOWN PLANNING | PROJECT 643 | ADERALPH | 8151528316 | 60022033812 | INSTALLED | 2024-05-20
63 | 1006036801 | 11-AmuwoINJ-T2-Jakande 2-AGBEDE 2 | OSHODI | AMUWO | AMUWO | 11-AmuwoINJ-T2-Jakande 2 | PUBLIC | GROUND | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.468 | 3.3011 | PLOT 133 AMUWO ODOFIN BY FESTAC LINK BRIDGE, AMUWO | PROJECT 643 | All solution | 9098079569 | 60022033794 | INSTALLED | 2024-06-23
64 | 1000256860 | 11-IgbobiINJ-T3-Railway-IDERA | SHOMOLU | ILUPEJU | ILUPEJU MEGA | 11-IgbobiINJ-T3-Railway | PUBLIC | GROUND | CIS | POST-PAID | METERED | 201508004228 | FUNCTIONAL | CLOU | 500 | 800/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5356 | 3.3606 | IDERA STREET | PROJECT 643 | All solution | 9098079569 | 60022032420 | INSTALLED | 2024-06-28
65 | 1001612442 | 11-Ilupeju BypassINJ-T1-Industrial-BYE-PASS | SHOMOLU | ILUPEJU | ILUPEJU MEGA | 11-Ilupeju BypassINJ-T1-Industrial | PUBLIC | GROUND | CIS | POST-PAID | METERED | 60016111867 | FUNCTIONAL | MOJEC | 500 | 800/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5455 | 3.3592 | CREATIVE HOUSE ILUPEJU BYPASS | PROJECT 643 | All solution | 9098079569 | 60022032812 | INSTALLED | 2024-06-28
66 | 1006034002 | 11-OjoduINJ-T2-Express-MUYIBAT OYEFUSI 2 | IKEJA | OBA AKRAN | OBA AKRAN | 11-OjoduINJ-T2-Express | PUBLIC | GROUND | CIS | POST-PAID | UNMETERED | #N/A | N/A | N/A | 300 | 500/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6355 | 3.3641 | 15, MUYIBAT OYEFUSI STREET, OMOLE ESTATE PHASE 1 | PROJECT 643 | All solution | 9098079569 | 60022031749 | INSTALLED | 2024-07-04
67 | 1006025801 | 11-OdogunyanINJ-T1-Agodo-ANNEX 2 | IKORODU | LASUNWON | LASUNWON | 11-OdogunyanINJ-T1-Agodo | PUBLIC | GROUND MOUNTED | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | FAULTY | INACTIVE | 6.6501 | 3.5162 | OFF ADEOWO STREET, LASUNWON | PROJECT 643 | All solution | 9098079569 | 60022031706 | INSTALLED | 2024-07-04 | Replacement and Retrieval of Old Meter/'060022031897
68 | 1006034801 | 11-IgbogboINJ-T2-Agunfoye-Union Homes Garden Estate CDA | IKORODU | IGBOGBO | IGBOGBO | 11-IgbogboINJ-T2-Agunfoye | PUBLIC | GROUND | CIS | N/A | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5762 | 3.5493 | No. 25, Alhaji Semiu White Okunola Street, Ire 1, Igbogbo Baiyeku LCDA. Lagos | PROJECT 643 | MAYFAK | 9050329971 | 60022031798 | INSTALLED | 2024-07-04
69 | 0101315348 | GEORGE TEMITOPE | IKEJA | IKEJA | IKEJA | 11-Adekunle FajuyiINJ-T1-Oduduwa | PUBLIC | N/A | N/A | N/A | Complete Installation | N/A | N/A | N/A | 100 | 200/5A | N/A | N/A | N/A | N/A |  |  | 29D, REMI FANKAYODE STREET, GRA ,IKEJA | PROJECT 643 | vicbonny | +234 806 797 3395 | 060022033356 | INSTALLED | 2024-07-09
70 | 0100348387 | OGUNDERO MAJOR GENERAL | IKEJA | IKEJA | IKEJA | 11-Adekunle FajuyiINJ-T1-Oduduwa | PUBLIC | N/A | N/A | N/A | Complete Installation | N/A | N/A | N/A | 100 | 200/5A | N/A | N/A | N/A | N/A |  |  | 25 ADEKUNLE FAJUYI C 84/P25/25490 G R A IKEJA | PROJECT 643 | vicbonny | +234 806 797 3395 | 060022033857 | INSTALLED | 2024-07-09
71 | 0100928167 | CHIEF OKORONKWO GEOR | IKEJA | IKEJA | IKEJA | 11-Adekunle FajuyiINJ-T1-Isaac John | 300 | N/A | N/A | N/A | Complete Installation | N/A | N/A | N/A | 300 | 500/5A | N/A | N/A | N/A | N/A | 6.5826 | 3.3487 | 1A LADOKE AKINTOLA STREET GRA IKEJA LAGOS | PROJECT 643 | vicbonny | +234 806 797 3395 | 060022032720 | INSTALLED | 2024-07-09
72 | 0100068892 | SMRIDU HOTEL | IKEJA | IKEJA | IKEJA | 11-Adekunle FajuyiINJ-T1-Oduduwa | 200 | N/A | N/A | N/A | Complete Installation | N/A | N/A | N/A | 200 | 500/5A | N/A | N/A | N/A | N/A | 6.5708 | 3.3487 | 39. ADEKUNLE FAJUYI WAY. IKEJA. | PROJECT 643 | vicbonny | +234 806 797 3395 | 060022031672 | INSTALLED | 2024-07-09
73 | 0100068986 | FIDELIS AYEBAE | IKEJA | IKEJA | IKEJA | 11-IlupejuINJ-T4-Ikorodu | 100 | N/A | N/A | N/A | Complete Installation | N/A | N/A | N/A | 100 | 200/5A | N/A | N/A | N/A | N/A | 6.5678 | 3.3654 | 11 IYA OLOYE CRES. ONIGBONGBO MARYLAND LAGOS | PROJECT 643 | vicbonny | +234 806 797 3395 | 060022033456 | INSTALLED | 2024-07-09
74 | 0100068949 | MESSRS.E.I OJEI HOLDING | IKEJA | IKEJA | IKEJA | 11-Adekunle FajuyiINJ-T1-Oduduwa | 200 | N/A | N/A | N/A | Complete Installation | N/A | N/A | N/A | 200 | 500/5A | N/A | N/A | N/A | N/A | 6.5755 | 3.3564 | 11A+11B SASEGBON STR IKEJA G R A | PROJECT 643 | vicbonny | +234 806 797 3395 | 060022033618 | INSTALLED | 2024-07-10
75 | 0102380538 | SEGUN OJU BRIGHT | IKEJA | PTC | PTC | 11-PTCINJ-T1-Opebi | PUBLIC | N/A | N/A | N/A | Complete Installation | N/A | N/A | N/A | 100 | 200/5A | N/A | N/A | N/A | N/A |  |  | 40 TOYIN STREET IKEJA | PROJECT 643 | QUINTEC | 07065706955 | 060022031142 | INSTALLED | 2024-07-11
76 | 0102649326 | IKEJA ELECTRIC - MAGODO MEGA UNDERTAKING | SHOMOLU | MAGODO MEGA | MAGODO MEGA | 11-MagodoINJ-T2-Bashiru | PUBLIC |  |  | N/A | Complete Installation | N/A | N/A | N/A | 100 | 200/5A | N/A | N/A | N/A | N/A |  |  | PLOT 5B JUBILEE ROAD, CMD ROAD, MAGODO, LAGOS. | PROJECT 643 | ADERALPH | 8151528316 | 060022033263 | INSTALLED | 2024-07-11
77 | 0100070101 | YAKUBU A R ALHAJI | SHOMOLU | MAGODO | MAGODO | 11-MagodoINJ-T1-Shangisha | PUBLIC |  |  |  | Complete Installation | N/A | N/A | N/A | 100 | 200/5A | N/A | N/A | N/A | N/A |  |  | 1 JAIYE OYEDOTUN STR | PROJECT 643 | ADERALPH | 8151528316 | 060022031881 | INSTALLED | 2024-07-11
78 | 0101296742 | CONELE ADEBOLA OGUNSOWO | IKEJA | OREGUN | OREGUN | 11-New AlausaINJ-T5-Alausa | PUBLIC |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | Batch 1 | [5 empty] | 6A, KAFI STREET, ALAUSA,OREGUN. | PROJECT 643 | mayfak | 9050329971 | 060022031878 | INSTALLED | 2024-07-13
79 | 0100346185 | ISMAIL ABIODUN OLALEMI | IKEJA | OREGUN | OREGUN | 11-New AlausaINJ-T5-Alausa | PUBLIC |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | Batch 1 | [5 empty] | ISHOLA BELLO STREET ISHOLA BEL | PROJECT 643 | mayfak | 9050329971 | 060022031689 | INSTALLED | 2024-07-13
80 | 0101309234 | KENETH | IKEJA | OREGUN | OREGUN | 11-New AlausaINJ-T6-Ogundana | PUBLIC |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | Batch 1 | [5 empty] | 23, OGUNDANA STREET OFF ALLEN AVENUE | PROJECT 643 | mayfak | 9050329971 | 060022033355 | INSTALLED | 2024-07-13
81 | 0102796155 | KENSIGNTON & KENSGNTON NIG. LT | IKEJA | OREGUN | OREGUN | 11-New AlausaINJ-T6-Ogundana | 200 |  |  |  | Complete Installation |  |  |  | 300 | 500/5A LVMD | Batch 1 | [5 empty] | 35 OGUNDANA STREET OFF ALLEN AVENUE, IKEJA | PROJECT 643 | mayfak | 9050329971 | 060022033601 | INSTALLED | 2024-07-13
82 | 0100068881 | ADNA HOTEL | IKEJA | PTC | PTC | 11-PTCINJ-T3-General Hospital | 200 |  |  |  | Complete Installation |  |  |  | 300 | 500/5A LVMD | Batch 1 |  |  |  | 6.5761 | 3.3454 | 28. BADIPO BATEYE STREET. G R A - IKEJA. LAGOS. | PROJECT 643 | REALLOCATED vicbonny | +234 806 797 3395 | 60022033314 | INSTALLED | 2024-07-13
83 | 0100069019 | VIRGIN ATLANTIC | IKEJA | PTC | PTC | 11-PTCINJ-T3-General Hospital | 500 |  |  |  | Complete Installation |  |  |  | 500 | 800/5A LVMD | Batch 1 |  |  |  | 6.5799 | 3.3426 | 10. MOBOLAJI BANK ANTHONY WAY. IKEJA. LAGOS. | PROJECT 643 | REALLOCATED vicbonny | +234 806 797 3395 | 060022032946 | INSTALLED | 2024-07-13
84 | 0100348793 | EKITI STATE LIASON OFFICE | IKEJA | PTC | PTC | 11-PTCINJ-T3-General Hospital | 100 |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | Batch 1 |  |  |  | 6.5754 | 3.3469 | 81A ODUDUWA CRESCENT GRA IKEJA LAGOS. | PROJECT 643 | REALLOCATED vicbonny | +234 806 797 3395 | 060022031844 | INSTALLED | 2024-07-13
85 | 0101536732 | ADEMIDUN FEMI-MAPADERUN | IKEJA | PTC | PTC | 11-PTCINJ-T3-General Hospital | PUBLIC |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | Batch 1 | [5 empty] | 45,ODUDUWA CRESCENT,IKEJA GRA | PROJECT 643 | REALLOCATED vicbonny | +234 806 797 3395 | 060022033430 | INSTALLED | 2024-07-13
86 | 0102261457 | FEDERAL MIN INTERNAL AFFAI | IKEJA | PTC | PTC | 11-PTCINJ-T3-General Hospital | PUBLIC |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | Batch 1 | [5 empty] | IMMIGRATION DEPT 68/51777 IKEJA | PROJECT 643 | REALLOCATED vicbonny | +234 806 797 3395 | 060022033369 | INSTALLED | 2024-07-13
87 | 0100925854 | BEIJ INN AND SUITES | SHOMOLU | OGUDU | OGUDU | 11-OguduINJ-T1-CAC | 200 |  |  |  | Complete Installation |  |  |  | 300 | 500/5A LVMD | Batch 1 |  |  |  | 6.5787 | 3.3808 | 26 EMMANUEL HIGH STREET | PROJECT 643 | ADERALPH | 8151528316 | 060022033597 | INSTALLED | 2024-07-16
88 | 0101028661 | CHIEF ADEKUNLE ABDUL | SHOMOLU | OGUDU | OGUDU | 11-OguduINJ-T1-Express | 300 |  |  |  | Complete Installation |  |  |  | 300 | 500/5A LVMD | Batch 1 |  |  |  | 6.5755 | 3.3898 | PLT 3 BLK M OGUDU GRA LAGOS | PROJECT 643 | ADERALPH | 8151528316 | 060022032747 | INSTALLED | 2024-07-16
89 | 0100070508 | U A C FOOD (MR BIGGS) | SHOMOLU | OGUDU | OGUDU | 11-OguduINJ-T1-Express | 200 |  |  |  | Complete Installation |  |  |  | 300 | 500/5A LVMD | Batch 1 |  |  |  | 6.577 | 3.3895 | 117 OGUDU ROAD | PROJECT 643 | ADERALPH | 8151528316 | 060022032450 | INSTALLED | 2024-07-16
90 | 0100350372 | JUDE EKWUNIFE | IKEJA | PTC | PTC | 11-New AlausaINJ-T6-Awolowo | 200 |  |  |  | Complete Installation |  |  |  | 300 | 500/5A LVMD | Batch 1 |  |  |  | 6.6023 | 3.3457 | 4. FADEYI ALADURA STREET. OFF ORISHE STREET. IKEJA. | PROJECT 643 | QUINTEC | 07065706955 | 060022032817 | INSTALLED | 2024-07-16
91 | 0100068771 | DOWN TOWN ROYAL HOTEL | IKEJA | PTC | PTC | 11-New AlausaINJ-T6-Awolowo | 100 |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | Batch 1 |  |  |  | 6.605 | 3.3493 | 22. DIPEOLU ST. OFF AWOLOWO WA AIRPORT HOTEL. IKEJA LAGOS. | PROJECT 643 | QUINTEC | 07065706955 | 060020123679 | INSTALLED | 2024-07-16
92 | 0100068953 | DR ABAYOMI FINNIH OLUYO | IKEJA | PTC | PUBLIC | 11-PTCINJ-T3-General Hospital | 100 |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | [6 empty] | 34 ODUDUWA CRESCENT M/NO 80/P200/5/196 G R A IKEJA | PROJECT 643 | welldone |  | 060022032582 | INSTALLED | 2024-07-16
93 | 0100348273 | DANIEL KEHINDE OLABISI | IKEJA | PTC | PUBLIC | 11-PTCINJ-T3-General Hospital | 100 |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | [6 empty] | 91 ODUDUWA CRESCENT 98/P50/000039 GRA | PROJECT 643 | welldone |  | 060022033180 | INSTALLED | 2024-07-16 | after installation and payment made to sbc meter was reported as faulty and was replaced with a new meter by another sbc (reason for acct no duplicate)
94 | 1003442556 | 11-OguduINJ-T3-Soluyi-ESTAPORT | SHOMOLU | OWORO | OWOROSHONKI MEGA | 11-OguduINJ-T3-Soluyi | PUBLIC | GROUND | CIS | POST-PAID |  | 60020120209 | FUNCTIONAL | MOJEC | 200 | 300/5a |  |  |  |  | 6.56 | 3.3862 | DOGO MAJEKODUNMI STREET, SOLUYI | PROJECT 643 | mayfak/demol | 09021887242 | 060022031760 | INSTALLED | 2024-07-17
95 | 1000240761 | 11-Adekunle FajuyiINJ-T1-Oduduwa-ODUDUWA WAY III | IKEJA | PTC | PTC | 11-Adekunle FajuyiINJ-T1-Oduduwa | PUBLIC | GROUND | CIS | POST-PAID |  | 201505001066 | FUNCTIONAL | CLOU | 500 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE |  | 6.5714 | 3.3531 | ODUDUWA WAY, IKEJA GRA | PROJECT 643 | All solution | 9098079569 | 60022031661 | INSTALLED | 2024-07-16
96 | 0100702082 | Z FATOKU ESQ | SHOMOLU | ILUPEJU MEGA | ILUPEJU MEGA | 11-IlupejuINJ-T3-Coker | PUBLIC |  |  |  | Complete Installation |  |  |  | 100 | 200/5A LVMD | [6 empty] | 1 SERE ST | PROJECT 643 | All solution | 9098079569 | 60022033955 | INSTALLED | 2024-07-17
97 | 1003970428 | 11-New GowonINJ-T1-Olorunadaba-MOBOLAJI AKINSHILO | AKOWONJO | EGBEDA | EGBEDA | 11-New GowonINJ-T1-Olorunadaba | PUBLIC | POLE MOUNTED | CIS | POST-PAID | METERED | 60020120127 | FAULTY | MOJEC | 100 | 200/5 | COMMISSIONED | HEALTHY | ACTIVE |  | 6.6081 | 3.2962 | 2 ONIYIDE CLOSE RANTI ALABI RAJI OBA ALIMOSHO LAGOS STATE | PROJECT 643 | mayfak/demol |  | 060022032670 | INSTALLED | 2024-07-13
98 | 1000163154 | 11-New GowonINJ-T1-Olorunadaba-ADEBUNMI EDUN | AKOWONJO | EGBEDA | EGBEDA | 11-New GowonINJ-T1-Olorunadaba | PUBLIC | GROUND | CIS | POST-PAID | METERED | 60017052599 | FUNCTIONAL | MOJEC | 500 | 800/5 | COMMISSIONED | HEALTHY | ACTIVE |  | 6.6084 | 3.2998 | ADEBUNMI STREET ALIMOSHO LAGOS STATE | PROJECT 643 | mayfak/demol |  | 060022032766 | INSTALLED | 2024-07-13
99 | 1006038005 | 33-OdogunyanTCN-FAKALE MAYA-PROMISED LAND CDA 2 | IKORODU | ODOGUNYAN | ODOGUNYAN | 33-OdogunyanTCN-FAKALE MAYA | PUBLIC | GROUND | CIS | POST-PAID | UNMETERED | N/A | N/A | N/A | 500 | 800/5 | NOT COMMISSIONED | HEALTHY | INACTIVE |  | 6.7237 | 3.5393 | EVERLASTING AREA CDC, OGIJO SAGAMU SOUTH, OGUN STATE | PROJECT 643 | DEMOL |  | 60022032409 | INSTALLED | 2024-07-16
100 | 1006038004 | 33-IkoroduTCN-IPAKODO- ELEPE ROYAL ESTATE CDA | IKORODU | IGBOGBO | IGBOGBO | 33-IkoroduTCN-IPAKODO | PUBLIC | GROUND | CIS | POST-PAID | UNMETERED | N/A | N/A | N/A | 500 | 800/5 | NOT COMMISSIONED | HEALTHY | INACTIVE |  | 6.6061 | 3.4998 | NO. 1, SHIFAD SHITTA STREET, ELEPE ROYAL ESTATE, AGA, IKORODU, LAGOS STATE | PROJECT 643 | DEMOL |  | 60022032945 | INSTALLED | 2024-07-16
101 | 0100346373 | BOLA OGUNSANWO | IKEJA | OREGUN | OREGUN | 11-New AlausaINJ-T5-Alausa | PUBLIC |  |  |  | Complete Installation | N/A | Batch 1 | mayfak | 100 | 200/5A LVMD | [6 empty] | 6 KAFFI STR | PROJECT 643 | mayfak |  | 060022032669 | INSTALLED | 2024-07-17
102 | 1000238330 | 11-ShashaINJ-T1-Coker Estate-KINGS COURT 2 | AKOWONJO | ABULE-ODU | ABULE-ODU | 11-ShashaINJ-T1-Coker Estate | PUBLIC | GROUND | CIS | POST-PAID | METERED | 201505001278 | FUNCTIONAL | CLOU | 500 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE |  | 6.5822 | 3.3076 | KINGS COURT OFF JAIYE OBA ROAD SHASHA LAGOS STATE | PROJECT 643 | mayfak/demol |  | 060022033161 | INSTALLED | 2024-07-17 | meter was collected from aderalph / meter installed
103 | 1002050818 | 11-PTCINJ-T3-Oba Akinjobi-BCI GLOBAL PROPERTIE | IKEJA | PTC | PTC | 11-PTCINJ-T3-Oba Akinjobi | PUBLIC | GROUND | CIS | POST-PAID | METERED | 60017111280 | FUNCTIONAL | MOJEC | 200 | 300/5 | COMMISSIONED | HEALTHY | ACTIVE |  | 6.5809 | 3.3543 | OBA DOSUNMU STREET GRA IKEJA | PROJECT 643 | All solution |  | 60022032523 | INSTALLED | 2024-07-19
104 | 1000189155 | 11-New AlausaINJ-T6-Awolowo-OBOKUN | IKEJA | PTC | PTC | 11-New AlausaINJ-T6-Awolowo | PUBLIC | GROUND | CIS | POST-PAID | METERED | 201505000842 | FUNCTIONAL | CLOU | 300 | 500/5 | COMMISSIONED | HEALTHY | ACTIVE |  | 6.6055 | 3.3485 | OBOKUN CLOSE IKEJA | PROJECT 643 | All solution |  | 60022033240 | INSTALLED | 2024-07-19
105 | 1000975518 | 11-OjoduINJ-T1-Ojodu-OJODU ESTATE 1 | IKEJA | OJODU | OJODU | 11-OjoduINJ-T1-Ojodu | PUBLIC | GROUND | CIS | POST-PAID | METERED | 201505000850 | FUNCTIONAL | CLOU | 500 | 800/5 | COMMISSIONED | HEALTHY | ACTIVE |  | 6.646 | 3.365 | SOFOLA STREET OFF OGUNLUSI ROAD OJODU BERGER | PROJECT 643 | All solution |  | 60022032636 | INSTALLED | 2024-07-19
106 | 1000247282 | 11-New AlausaINJ-T6-Ogundana-OLARIBIRO | IKEJA | OREGUN | OREGUN | 11-New AlausaINJ-T6-Ogundana | PUBLIC | GROUND | CIS | POST-PAID | METERED | 60019030581 | FUNCTIONAL | MOJEC | 500 | 800/5 | COMMISSIONED | HEALTHY | ACTIVE |  | 6.6046 | 3.3531 | ALLEN AVENUE IKEJA LAGOS OFF ADEBOYE SOLANKE STREET | PROJECT 643 | All solution |  | 60022032434 | INSTALLED | 2024-07-19
107 | 0100070680 | INTERIOR OPTION LIMITED | SHOMOLU | ILUPEJU | ILUPEJU | 11-Ilupeju BypassINJ-T1-Industrial |  |  |  |  | Complete Installation |  | Batch 1 |  | 100 | 200/5A LVMD | [6 empty] | BURNUN IND LTD | PROJECT 643 | All solution |  | 60022033327 | INSTALLED | 2024-07-19
108 | 0100709356 | CITY HALL - OJOTA | SHOMOLU | ANTHONY MEGA | ANTHONY MEGA | 11-OguduINJ-T1-CAC |  |  |  |  | Complete Installation |  | Batch 1 |  | 100 | 200/5A LVMD |  |  |  |  | 6.5807 | 3.3822 | EMMANUEL HIGH STR OGUDU LAGOS | PROJECT 643 | All solution |  | 60020123623 | INSTALLED | 2024-07-22
109 | 0100070167 | OMOTAYO OJO CAB CONST WK L | SHOMOLU | IKOSI | IKOSI | 11-MarylandINJ-T3-Demurin |  |  |  |  | Complete Installation |  | Batch 1 |  | 300 | 500/5A LVMD |  |  |  |  | 6.607 | 3.3817 | 23 LOVEALL ST | PROJECT 643 | All solution |  | 60022033816 | INSTALLED | 2024-07-22
110 | 0100070771 | KAMSON KEHINDE | SHOMOLU | OLOWORA | OLOWORA | 11-MagodoINJ-T2-Bashiru | PUBLIC |  |  |  | Complete Installation |  | Batch 1 | tee n bee | 100 | 200/5A LVMD | [6 empty] | P.793 SOMIDE ODUNJIR | PROJECT 643 | TEE N BEE |  | 60022033311 | INSTALLED | 2024-07-18
111 | 0100070132 | RAPEEAT TEMITAYO LAWAL | SHOMOLU | OLOWORA | OLOWORA | 33-AlausaTCN-OPIC | 100 | #NAME? | #NAME? |  | Complete Installation |  | Batch 1 | tee n bee | 100 | 200/5A LVMD | [6 empty] | PLT 10 ISHERI NORTH OPIC | PROJECT 643 | TEE N BEE |  | 60022033272 | INSTALLED | 2024-07-18
112 | 0100070502 | EHKAY CORRUGATED CARTONS LTD | SHOMOLU | OGUDU | OGUDU | 11-OguduINJ-T1-Ogudu | 500 | #NAME? | #NAME? |  | Complete Installation |  | Batch 1 | aderalph | 300 | 500/5A LVMD |  |  |  |  | 6.5877 | 3.3836 | 2-10 TAIWO STREET | PROJECT 643 | ADERALPH |  | 060022033013 | INSTALLED | 2024-07-18
113 | 1002049767 | 33-OgbaTCN-IJU WATER WORKS-GENERAL HOSPITAL | IKEJA | IFAKO | IFAKO | 33-OgbaTCN-IJU WATER WORKS-GENERAL HOSPITAL |  |  |  |  | Complete Installation | 800/5A LVMD |  | aderalph | 500 | 800/5A LVMD |  |  |  |  | 6.6439 | 3.3255 | COLLEGE ROAD, AGEGE | PROJECT 643 | ADERALPH |  | 060022033026 | INSTALLED | 2024-07-19
114 | 0100069024 | G L O B A C O M OFFICE | IKEJA | PTC | PTC | 11-PTCINJ-T1-Opebi | 200 |  |  |  | Complete Installation | 500/5A LVMD | Batch 1 | quintec | 1900-07-18 | 500/5A LVMD | INSTALLED |  |  |  | 6.5957 | 3.3549 | 2. OPEBI ROAD. IKEJA. | PROJECT 643 | QUINTEC |  | 060022032662 | INSTALLED | 2024-07-18
115 | 0100922296 | OLUMIRIN VENTURES LIMITED | IKEJA | OGBA | OGBA | 11-OgbaINJ-T2-Mangoro | 3NP07304 |  |  |  | Complete Installation | 500/5A LVMD | [10 empty] | 1, OGBA ROAD | PROJECT 643 | vicbonny |  | 060022032771 | INSTALLED | 2024-07-18
116 | 0100068353 | POWER LINE NIGERIA LTD | IKEJA | OGBA | OGBA | 11-OgbaINJ-T3-Oba Akran | 0 |  |  |  | Complete Installation | 200/5A LVMD | [10 empty] | SAPARA STR MD/IKEJA/1/2/29 M/N 65/23457 IKEJA | PROJECT 643 | vicbonny |  | 060022033330 | INSTALLED | 2024-07-18
117 | 1003016404 | 11-MagodoINJ-T1-Owulade-AUSTIN AGBOLAHAN | SHOMOLU | MAGODO | MAGODO MEGA | 11-MagodoINJ-T1-Owulade | PUBLIC | GROUND | CIS | POST-PAID | METERED | 60011010673 | FUNCTIONAL | MOJEC | 100 | 200/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6188 | 3.3847 | AUSTIN AGBONLAHOR CLOSE, OFF ADETORO ADELAJA STREET, MAGODO PHASE 2, LAGOS | PROJECT 643 | mayfak |  | 60022033273 | INSTALLED | 2024-07-24
118 | 0100068144 | GS MICROFINANCE BANK | IKEJA | OREGUN | OREGUN | 11-New AlausaINJ-T5-Alausa |  |  |  |  | Complete Installation | 500/5A LVMD | Batch 1 | mayfak | [6 empty] | 6.6096 | 3.3535 | 1. KUDIRAT ABIOLA WAY. OREGUN LAGOS. | PROJECT 643 | mayfak |  | 060022033567 | INSTALLED | 2024-07-23
119 | 1006038401 | 11-Ipakodo (Ebute)INJ-T1-WAEC-OLU ODO II | IKORODU | IGBOGBO | IGBOGBO | 11-Ipakodo (Ebute)INJ-T1-WAEC | PUBLIC | GROUND | CIS | POST-PAID | UNMETERED | N/A | N/A | 500 | NOT CONNECTED | NOT COMMISSIONED |  | HEALTHY |  |  | 6.5908 | 3.5004 | OLU ODO , EBUTE, IGBOGBO, IKORODU | PROJECT 643 | mayfak |  | 60022033747 | INSTALLED | 2024-07-25
120 | 1006038201 | 11-SaboINJ-T2-Erunwen-Awofusi CDA | IKORODU | AYANGBUREN | AYANGBUREN | 11-SaboINJ-T2-Erunwen |  | GROUND MOUNTED | UNMETERED | 500 | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | NOT CONNECTED | NOT COMMISSIONED |  |  |  |  | 6.6121 | 3.544 | Awofusi Community Area. Ikorodu Lagos State | PROJECT 643 | mayfak |  | 60022033474 | INSTALLED | 2024-07-26
121 | 1000253993 | 11-OgbaINJ-T1-Isokoko-ADEYEMI 500KVA | IKEJA | OGBA | OGBA | 11-OgbaINJ-T1-Isokoko | PUBLIC | GROUND | CIS | POST-PAID | METERED | 201508004053 | FUNCTIONAL | CLOU | 500 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE |  | 6.6202 | 3.328 | ADEYEMI STREET OGBA | PROJECT 643 | All solution |  | 60022032443 | INSTALLED | 2024-07-30
122 | 1003212906 | 11-AlimoshoINJ-T8-Alimosho-OBICHERE UGOCHUKWU | AKOWONJO | EGBEDA | EGBEDA | 11-AlimoshoINJ-T8-Alimosho | PUBLIC | POLE MOUNTED | CIS | POST-PAID | METERED | 60013090435 | FUNCTIONAL | MOJEC | 100 | 200/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6066 | 3.307 | ADISA OGUNWEMIMO STREET | PROJECT 643 | TEE N BEE |  | 060022031880 | INSTALLED | 2024-07-30
123 | 1000535965 | 33-AyoboTCN-ABULE TAYLOR-OPEYEMI 1 | AKOWONJO | ABULE-TAYLOR | ABULE-TAYLOR | 33-AyoboTCN-ABULE TAYLOR | PUBLIC | GROUND | CIS | POST-PAID | METERED | 201508005684 | FUNCTIONAL | CLOU | 500 | 800/5 | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6621 | 3.2868 | OPEYEMI STREET, OBADEYI. | PROJECT 643 | DEMOL/TEE N BEE |  | 060022033792 | INSTALLED | 2024-07-29
124 | 1006038402 | 33-Oke-AroTCN-AKUTE-FEYSDAM RESIDENTIAL ESTATE | SHOMOLU | MAGODO MEGA | MAGODO MEGA | 33-Oke-AroTCN-AKUTE | PUBLIC | GROUND MOUNTED |  |  | UNMETERED |  |  |  | 500 |  | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.686832 | 3.432806 | AT BLOCK E-F, PLOT 2, VOERA ESTATE, AREPO, OFF LAGOS IBADAN EXPRESSWAY | PROJECT 643 | mayfak |  | 060022032792 | INSTALLED | 2024-07-29
125 | 1005118908 | 11-AbesanINJ-T1-Ipaja-GLORYFIELD | AKOWONJO | IPAJA | IPAJA | 11-AbesanINJ-T1-Ipaja | GROUND MOUNTED | UNMETERED | [6 empty] | 500 | NOT CONNECTED | NOT COMMISSIONED |  | HEALTHY | INACTIVE | 6.6278 | 3.2509 | peace estate road off command road,ipaja Akowonjo | PROJECT 643 | mayfak |  | 60022032406 | INSTALLED | 2024-07-30
126 | 0100068665 | MAZIN ENGINEERING CO LTD | IKEJA | OREGUN | OREGUN | 11-SecretariatINJ-T2-UAC |  |  |  |  | Complete Installation | 800/5A LVMD | Batch 1 | mayfak | 500 | [5 empty] | 6.6046 | 3.3645 | PLT 20 OLAYIWOLA STR M/NO 85/56 OREGUN | PROJECT 643 | mayfak |  | 060022032476 | INSTALLED | 2024-07-29
127 | 1002050712 | 11-OgbaINJ-T3-Oba Akran-DEMILLER GENERAL SERVICES | IKEJA | ANIFOWOSHE | ANIFOWOSHE | 11-OgbaINJ-T3-Oba Akran | PUBLIC | POLE MOUNTED | CIS | POST-PAID | METERED | 201606010644 | FAULTY | CLOU | 100 | CONNECTED | COMMISSIONED |  | HEALTHY | ACTIVE | 6.598 | 3.3406 | 6,OBA AKRAN AVENUE | PROJECT 643 | mayfak/demol |  | 060022033851 | INSTALLED | 2024-07-29
128 | 0100068632 | CHRIST EMBASSY CHURCH | IKEJA | OREGUN | OREGUN | 11-New AlausaINJ-T5-Alausa |  |  |  |  | Complete Installation | 800/5A LVMD | Batch 1 | mayfak | 500 | [5 empty] | 6.6067 | 3.3628 | BILLINGS WAY ALAUSA IKEJA. LAGOS. | PROJECT 643 | mayfak |  | 060022032425 | INSTALLED | 2024-07-23 | IKEJA REQUEST METER BE REMOVED FROM THIS LOCATION BECAUSE METER IS NOT BEEN UTILIZED
129 | 1001603434 | 11-New GowonINJ-T1-Olorunadaba-I.E. DISTRICT OFFICE EGBEDA | AKOWONJO | EGBEDA | EGBEDA | 11-New GowonINJ-T1-Olorunadaba | PUBLIC | 60013090645 | [12 empty] | * | 3.2937 | AKOWONJO BU OFFICE | PROJECT 643 | mayfak/demol | FUNCTIONAL | 060022032908 | INSTALLED | 3107/2024
130 | 1006037201 | 11-BolorunpeluINJ-T3-Liasu-MEMUDU BADA | OSHODI | AMUWO | AMUWO | 11-BolorunpeluINJ-T3-Liasu | PUBLIC | GROUND | [6 empty] | 500 | NOT CONNECTED | NOT COMMISSIONED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.568 | 3.2689 | MEMUDU BABA STREET, IDIMU. | PROJECT 643 | mayfak | FUNCTIONAL | 60022033805 | INSTALLED | 2024-08-10
131 | 0101546110 | BEATRICE OGOR | IKORODU | ODOGUNYAN | ODOGUNYAN | 11-OdogunyanINJ-T1-Centex | PUBLIC | 060017112226 |  | Special |  |  |  |  | 500 | 800/5A | Complete Installation | NOT COMMISSIONED | HEALTHY | INACTIVE |  |  | 30 OMOLAFE STREET, AGODO ALARA, IKORODU, LAGOS | PROJECT 643 | mayfak | FUNCTIONAL | 60022033686 | INSTALLED | 2024-08-10
132 | 1006038801 | 11-IgbogboINJ-T2-Agunfoye-TEMIDIRE CDA | IKORODU | IGBOGBO | IGBOGBO | 11-IgbogboINJ-T2-Agunfoye | 500 | NOT CONNECTED | [6 empty] | 500 | 800/5a | NOT COMMISSIONED | NOT COMMISSIONED | HEALTHY | INACTIVE |  |  | TEMIDIRE CDA | PROJECT 643 | mayfak | FUNCTIONAL | 60022032859 | INSTALLED | 2024-08-10
133 | 0100068893 | THE ROZIZZIO | IKEJA | PTC | PTC | 11-Adekunle FajuyiINJ-T1-Isaac John | #NAME? |  |  |  | Complete Installation |  |  | vicbonny | 100 | 200/5A LVMD | [6 empty] | 29 ISAAC JOHN GRA. IKEJA LAGOS. | PROJECT 643 | Vicbonny |  | 060022033346 | INSTALLED | 2024-08-10
134 | 0100927676 | FIFINE HOTEL | OSHODI | IKOTUN | IKOTUN | 33-EjigboTCN-AGODO | PUBLIC | 0 | Complete Installation |  | Batch 2 |  |  |  | 100 | 200/5A LVMD | [6 empty] | 44 OPELOYERU STREET OFF LIASU ROAD IKOTUN-EGBE | PROJECT 643 | TEE N BEE |  | 060022033331 | INSTALLED | 2024-08-10
135 | 0102728774 | OLI VITALIS OGBONNA | OSHODI | IKOTUN | IKOTUN | 33-EjigboTCN-AGODO | PUBLIC | 0 | Complete Installation |  | Batch 2 |  |  |  | 100 | 200/5A LVMD | [6 empty] | 2, RASHEED BELLO STREET, EGBE | PROJECT 643 | TEE N BEE |  | 60022033343 | INSTALLED | 2024-08-10
136 | 0101666369 | NORTHWEST PETROLEUM RETAIL | ABULE-EGBA | FAGBA | FAGBA | 33-OgbaTCN-ABEOKUTA EXP. | PUBLIC | #N/A | Complete Installation |  | Batch 2 |  |  | installed | 100 | 200/5A LVMD | [6 empty] | KLM 17,ABEOKUTA EXPRESSWAY,FAGBA | PROJECT 643 | QUINTEC |  | 060022033175 | INSTALLED | 2024-08-10
137 | 0100397218 | MR BENJAMIN | ABULE-EGBA | IJAIYE | IJAIYE | 33-OtaTCN-AMJE | PUBLIC | 201709001217 | Complete Installation |  | Batch 2 |  |  | installed | 100 | 200/5A LVMD | [6 empty] | 18/20 BAALE ANIMASHAUN LAGOS | PROJECT 643 | QUINTEC |  | 060022032109 | INSTALLED | 2024-08-10
138 | 0100300459 | CHIEF FRANCIS AJAYI | OSHODI | IDIMU | IDIMU | 33-EjigboTCN-AGODO | PUBLIC | 0 | Complete Installation |  | Batch 2 |  |  |  | 100 | 200/5A LVMD | [6 empty] | 3 LEONA AJAYI CLOSE EGBE LAGOS | PROJECT 643 | Aderalph |  | 060020123715 | INSTALLED | 2024-08-10
139 | 0101841820 | GROCERY BAZAAR | AKOWONJO | IPAJA | IPAJA | 33-AyoboTCN-ABULE TAYLOR | 100 | 201803011582 | Complete Installation |  | Batch 2 |  |  |  | 100 | 200/5A LVMD | [6 empty] | PLOT G, BLOCK 33, UNITY BUS STOP, COMMAND ROAD ,IPAJA, LAGOS STATE. | PROJECT 643 | Aderalph |  | 060022033583 | INSTALLED | 2024-08-10
140 | 0101851121 | ADEDEJI OLUWASAYO REBECCA | OSHODI | IKOTUN | IKOTUN | 33-EjigboTCN-EGBE | PUBLIC | 0 | Complete Installation |  | Batch 2 |  |  | METER TO COLLECT FROM ADERALPH | 100 | 200/5A LVMD | [6 empty] | 9 OKESALU STREET IKOTUN | PROJECT 643 | TEE N BEE |  | 060022031814 | INSTALLED | 2024-08-10 | this is meter no was initially installed 60022033333 but was having phase supply issues and was replaced with 060022031814
141 | 101813259 | BOLAMUS GLOBAL RESOURCES | AKOWONJO | EGBEDA | EGBEDA | 11-ALIMOSHOINJ-T8-AlimoshoINJ-T8-OKUNOLA | PUBLIC | 1 | Complete Installation |  | Batch 3 |  |  | METER TO COLLECT FROM ADERALPH | 100 | 200/5A LVMD | [6 empty] | 8 FASHOLA STREET,OKUNOLA ROAD | PROJECT 643 | mayfak | FUNCTIONAL | 60022033722 | INSTALLED | 2024-08-12
142 | 0100955615 | EDOBOR | AKOWONJO | EGBEDA | EGBEDA | 11-AlimoshoINJ-T8-Alimosho | 60010015829 |  | Complete Installation | 200/5A LVMD | Batch 2 |  | TO BE ASSIGN A METER |  | 100 | 200/5A LVMD | [6 empty] | 21 OYINLOLA STR LAGOS | PROJECT 643 | mayfak |  | 060022032407 | INSTALLED | 2024-08-13
143 | 0100067675 | ZENITH BANK | AKOWONJO | EGBEDA | EGBEDA | 11-AlimoshoINJ-T8-Alimosho | 0 |  | Complete Installation | 500/5A LVMD | Batch 2 | mayfak |  |  | 100 | 200/5A LVMD | [6 empty] | ABEOKUTA EXPRESS WAY DOPEMU LAGOS STATE | PROJECT 643 | mayfak |  | 60022033727 | INSTALLED | 2024-08-15
144 | 100622328 | ALHAJI LATEEF SHITTU ADE | AKOWONJO | AIT | AIT | 11-ILAPOINJ-T1-ILAPO | 1 |  | Complete Installation | 200/5A LVMD | Batch 3 | mayfak |  |  | 100 | 200/5A LVMD | [6 empty] | 7 JA OLIVE STREET ALAGBADO | PROJECT 643 | mayfak |  | 60022031870 | INSTALLED | 2024-08-15
145 | 0100067565 | PETER ESANGHEDO | AKOWONJO | AIT | AIT | 33-AyoboTCN-AMIKANLE | 201803012321 |  | Complete Installation | 500/5A LVMD | Batch 2 | mayfak |  |  | 300 | [7 empty] | 47 AIT ROAD OFF LAGOS/ABEOKUTA EXPRESS ALAGBADO LAGOS | PROJECT 643 | mayfak |  | 060022033729 | INSTALLED | 2024-08-15
147 | 1006035001 | 11-Ago OkotaINJ-T2-Lake View-STARTIMES ESTATE II | OSHODI | AGO | AGO | 11-Ago OkotaINJ-T2-Lake View | PUBLIC | GROUND | CIS | N/A | UNMETERED | #N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.484356 | 3.2927 | NO 39 VINCENT OGAMBA CRESCENT STARTIMES ESTATE AGO PALACE WAY. | PROJECT 643 | TEE N BEE |  | 60022031733 | INSTALLED | 2024-08-13
148 | 0100333621 | EKENE JACOBS ., | OSHODI | IKOTUN | IKOTUN | 33-EjigboTCN-AGODO | 0 | 33-EjigboTCN-AGODO | Complete Installation | 200/5A LVMD | Batch 2 | tee n bee | [10 empty] | 7, MOBOLOWA DURO STR | PROJECT 643 | TEE N BEE |  | 060022031843 | INSTALLED | 2024-08-15
149 | 0100069515 | AMION STEEL LTD | OSHODI | IKOTUN | IKOTUN | 33-EjigboTCN-AGODO | 0 | 33-EjigboTCN-AGODO | Complete Installation | 800/5A LVMD | Batch 2 | tee n bee | [10 empty] | 7 SEGUN IREFIN STR EGBE LAGOS | PROJECT 643 | TEE N BEE |  | 060022032428 | INSTALLED | 2024-08-16
150 | 0100300308 | LEMIKAN AKINOLA SAMUEL | OSHODI | IKOTUN | IKOTUN | 33-EjigboTCN-AGODO | 0 | 0 | Complete Installation | 200/5A LVMD | Batch 2 | tee n bee | [10 empty] | 1 BAKINSON STR. OFF LIASU RD EGBE LAGOS | PROJECT 643 | TEE N BEE |  | 060022033264 | INSTALLED | 2024-08-18
151 | 0101366631 | EKULO GROUP | OSHODI | AMUWO | AMUWO | 33-ItireTCN-AGO II | 0 | 33-ItireTCN-AGO II | Complete Installation | 800/5A LVMD | Batch 2 | tee n bee | [10 empty] | C33, BABANGIDA ROAD, AMUWO ODOFIN IND | PROJECT 643 | TEE N BEE |  | 60022033001 | INSTALLED | 2024-08-18 | faulty yellow phase after installation and retrieved 060022032849 and new installation of 60022033001
152 | 0100098734 | ELIZADE NIGERIA LIMITED | IKEJA | PTC | PTC | 11-MarylandINJ-T2-GRA | 11-MarylandINJ-T2-GRA | 6.5793 | 3.3607 |  | Complete Installation | 800/5A LVMD | Batch 1 | quintec | 500 | 800/5A | 500 | #NAME? |  |  |  |  | 14 MOBOLAJI BANK ANTHONY WAY IKEJA LAGOS | PROJECT 643 | QUINTEC |  | 060022032413 | INSTALLED | 2024-08-19
153 | 0100068235 | FOREVER LIVING PRODUCT | IKEJA | ANIFOWOSHE | ANIFOWOSHE | 11-Adeniyi JonesINJ-T1-Adeniyi Jones | No meter |  | Complete Installation | 500/5A LVMD | Batch 2 | [11 empty] | AROMIRE AVENUE IKEJA | PROJECT 643 | Aderalph |  | 060022033171 | INSTALLED | 2024-08-12
154 | 0100068161 | UNITED BANK FOR AFRICA | IKEJA | ANIFOWOSHE | ANIFOWOSHE | 11-OgbaINJ-T3-Oba Akran | No meter |  | Complete Installation | 500/5A LVMD | Batch 2 | [11 empty] | OBA AKRAN AVENUE. IKEJA. LAGOS STATE | PROJECT 643 | Aderalph |  | 60022033714 | INSTALLED | 2024-08-12
155 | 0100068182 | LASACO ASSURANCE PLC | IKEJA | ANIFOWOSHE | ANIFOWOSHE | 11-OgbaINJ-T2-Ifako | 13090003 |  | Complete Installation | 500/5A LVMD | Batch 2 | Aderalph | [10 empty] | 16 ACME ROAD OGBA OGBA B/UNIT LAGOS STATE | PROJECT 643 | Aderalph |  | 060022033763 | INSTALLED | 2024-08-13
156 | 0100068249 | NATIONAL BANK NIGERIA LTD | IKEJA | OGBA | OGBA | 11-OgbaINJ-T3-Oba Akran | 0 |  | Complete Installation | 800/5A LVMD | Batch 2 | [12 empty] | PROJECT 643 | vicbonny |  | 060022033782 | INSTALLED | 2024-08-12
157 | 0100067981 | ADEITE SANYA OLAYINKA | IKEJA | OBA AKRAN | OBA AKRAN | 11-OjoduINJ-T2-Express | #N/A |  | Faulty Electronic component | 200/5A LVMD | Batch 2 | [11 empty] | 10 AGINDINGBI ROAD. OJODU | PROJECT 643 | vicbonny |  | 60020123084 | INSTALLED | 2024-08-14
158 | 0100068480 | P L A T I N U M BANK NIG | IKEJA | OBA AKRAN | OBA AKRAN | 11-OjoduINJ-T1-Ojodu | 201903012516 |  | Complete Installation | 200/5A LVMD | Batch 2 | well done | [10 empty] | OBADINA OJODU | PROJECT 643 | vicbonny |  | 60022033716 | INSTALLED | 2024-08-15
159 | 0100068450 | N A C B LTD | IKEJA | OBA AKRAN | OBA AKRAN | 11-SecretariatINJ-T1-Estate | 0 |  | Complete Installation | 500/5A LVMD | Batch 2 | well done | [10 empty] | BUSINESS DISTRICT IKEJA | PROJECT 643 | vicbonny |  | 60022033095 | INSTALLED | 2024-08-15
160 | 0100068455 | R. M. S. INVESTMENT TRUST, | IKEJA | OBA AKRAN | OBA AKRAN | 11-SecretariatINJ-T1-Omole | 201512007876 | 11-SecretariatINJ-T1-Omole | Complete Installation | 800/5A LVMD | Batch 2 | well done |  | Awaiting Installations | [8 empty] | 1 IPM RD..OPP LAGOS STATE ALAUSA. IKEJA | PROJECT 643 | vicbonny |  | 60022033130 | INSTALLED | 2024-08-16
161 | 0100069608 | FEDELITY BANK PLC | OSHODI | AGO | AGO | 11-ItireINJ-T2-Canal | 0 | 11-ItireINJ-T2-Canal | Complete Installation | 500/5A LVMD | Batch 2 | vicbonny | [10 empty] | 99 AGO-PALACE WAY AGO LAGOS | PROJECT 643 | vicbonny |  | 060022031695 | INSTALLED | 2024-08-16
162 | 0101201120 | EAT AND GO | OSHODI | AGO | AGO | 11-ItireINJ-T2-Canal | 0 | 11-ItireINJ-T2-Canal | Complete Installation | 500/5A LVMD | Batch 2 | vicbonny | [10 empty] | AGO PALACE WAY | PROJECT 643 | vicbonny |  | 060022033811 | INSTALLED | 2024-08-16
163 | 0100069840 | COMPLETE COMMUNICATIONS LTD | OSHODI | OKOTA | OKOTA | 11-ItireINJ-T1-Okota | 0 | 11-ItireINJ-T1-Okota | Complete Installation | 500/5A LVMD | Batch 2 | all solution | [10 empty] | 3 ALH. ADENEKAN STREET OKOTA LAGOS | PROJECT 643 | Allsolution |  | 60022032745 | INSTALLED | 2024-08-26
164 | 0100069821 | ZENITH BANK PLC | OSHODI | OKOTA | 100 | 11-ItireINJ-T1-Okota | 0 | 11-ItireINJ-T1-Okota | Complete Installation | 200/5A LVMD | Batch 2 | all solution | [10 empty] | 103.OKOTA ROAD OKOTA LAGOS | PROJECT 643 | Allsolution |  | 60022033363 | INSTALLED | 2024-08-12
165 | 0101484365 | ALEX SUNDAY NWOYE | OSHODI | OKE-AFA | PUBLIC | 33-EjigboTCN-OKEAFA 2 | 0 | 33-EjigboTCN-OKEAFA 2 | Complete Installation | 200/5A LVMD | Batch 2 | all solution | [10 empty] | 4 ABIODUN ALIMI STREET OKE AFA LAGOS | PROJECT 643 | Allsolution |  | 60020123697 | INSTALLED | 2024-08-12
166 | 0100069378 | HI-POINT HOTEL & SUIT | OSHODI | OKE-AFA | PUBLIC | 33-EjigboTCN-OKEAFA 2 | 0 | 33-EjigboTCN-OKEAFA 2 | Complete Installation | 200/5A LVMD | Batch 2 | all solution | [10 empty] | ISOLO EGBE ROAD OKE-AFA LAGOS | PROJECT 643 | Allsolution |  | 60022031744 | INSTALLED | 2024-08-12
167 | 0100069859 | MABATKO HOTELS | OSHODI | OSHODI | OSHODI | PUBLIC | 0 | 33-IsoloTCN-PTC INTERFACE | Faulty Electronic component | 500/5A LVMD | Batch 2 | all solution | [10 empty] | 41/43,OYEGUNWA STREET SHOGUNLE,Oshodi-Isolo,Lagos | PROJECT 643 | Allsolution |  | 60022033445 | INSTALLED | 2024-08-28
168 | 102001601 | Collins Adebowale Edward (W HOTEL) | IKEJA | PTC | PTC | 11-Adekunle FajuyiINJ-T1-Oduduwa-ODUDUWA CRESCENT IV |  |  |  | 200/5A | Mr. Collins Adebowale 08035686223 | [12 empty] | PROJECT 643 | Aderalph |  | 060022031685 | INSTALLED | 2024-09-03
169 | 0100348273 | DANIEL KEHINDE OLABISI | IKEJA | PTC | PTC | 11-PTCINJ-T3-General Hospital |  |  |  | 200/5A | [12 empty] | 91 ODUDUWA CRESCENT 98/P50/000039 GRA | PROJECT 643 | Aderalph |  | 060022033206 | INSTALLED | 2024-09-03 | 60022033180 this is meter no was initially installed 60022033180 but was having phase supply issues and was replaced with 060022033206
170 | 102441541 | ADEJUMO FAM NIG. LTD | IKEJA | PTC | PTC | 11-IlupejuINJ-T1-ATM-ADEYEMI BERO | 200/5A | [15 empty] | PLT8, BLKIV ILUPEJU SCHEME ILUPEJU | PROJECT 643 | Aderalph |  | 60022033172 | INSTALLED | 2024-09-09 | this is meter no was initially installed 60022033207 but was having phase supply issues and was replaced with 060022033452 and it also had issue and finally we replaced with 60022033172
171 | 101212592 | Tip Top Hotel | AKOWONJO | ORILE-AGEGE | ORILE-AGEGE | 33-AlimoshoTCN-TOWER IPAJA | 201709001262 | 33-AlimoshoTCN-TOWER IPAJA | Faulty Electronic component | 500/5A LVMD | Batch 2 | [11 empty] | 198 Abeokuta Express | PROJECT 643 | Aderalph |  | 60022032581 | INSTALLED | 2024-09-03
172 | 0100888219 | KENNY JULIUS | IKORODU | ODOGUNYAN | ODOGUNYAN | 11-OdogunyanINJ-T2-Odokekere | 0 | 11-OdogunyanINJ-T2-Odokekere | Complete Installation | 200/5A LVMD | Batch 2 | [11 empty] | KENNY JULIUS STREET ALARA AGBODO IKD. LAG. | PROJECT 643 | vicbonny |  | 060022033847 | INSTALLED | 2024-09-07
173 | 100067470 | CORPORATE BODY/JEDAZ EVENT CEN | AKOWONJO | ABORU | ABORU | 33-AlimoshoTCN-AGEGE | #N/A | 33-AlimoshoTCN-AGEGE | Complete Installation | 200/5A LVMD | Batch 2 | mayfak | [10 empty] | 1 AJAGUNA STREET OFF IGE ROAD ABORU LAGOS | PROJECT 643 | mayfak |  | 60022033491 | INSTALLED | 2024-08-27
174 | 1006039601 | 11-AyetoroINJ-T1-Bada - Props Cooperative | AKOWONJO | AYOBO | AYOBO | 11-AyetoroINJ-T1-Bada | PUBLIC | GROUND | CIS | N/A | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 3.2184 | 6.5879 |  | PROJECT 643 | mayfak |  | 60022032862 | INSTALLED | 2024-09-03
175 | 0101334569 | 33-EjigboTCN-AGODO-DE-ONE LODGE | OSHODI | IKOTUN | IKOTUN | 33-EjigboTCN-AGODO | 60014120200 | [7 empty] | 300 | 500/5A |  |  |  |  | 6.5451 | 3.2716 | 18 ADANO STREET, SYNAGOGE BUS STOP BOLORUNPLELU | PROJECT 643 | mayfak |  | 60022031786 | INSTALLED | 2024-09-08 | 60022033457 PREVIOUSLY INSTALLED BUT WAS FAULTY HAVING PHASE ISSUE AFTER INSTALLATION.060022031786 REDEPLOYED AND INSTALLED
176 | 1006039201 | 33-ItireTCN-AGO I-EGBUHUZOR ONYEBUCHI 1 | OSHODI | AMUWO | AMUWO | 33-ItireTCN-AGO I | PUBLIC | GROUND | CIS | N/A | METERED |  | FUNCTIONAL | MOJEC | 500 |  | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.4843 | 3.3112 | FIDELIS EDOKA STREET AMUWO ODOFIN ESTATE, AMUWO-ODOFIN. | PROJECT 643 | mayfak |  | 60022032793 | INSTALLED | 2024-08-13
177 | 1006039001 | 33-ItireTCN-AGO I-PRAYER ESTATE 3 | OSHODI | AMUWO | AMUWO | 33-ItireTCN-AGO I | PUBLIC | GROUND | CIS | N/A | METERED |  | FUNCTIONAL | MOJEC | 500 |  | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.4869 | 3.3139 | CHIEF O. A. MOYINATUMBA AMUWO ODOFIN ESTATE, AMUWO-ODOFIN. | PROJECT 643 | mayfak |  | 60022032717 | INSTALLED | 2024-08-13
178 | 0100067711 | NEXT LEVEL SHOPPING PLAZA | AKOWONJO | EGBEDA | EGBEDA | 11-AlimoshoINJ-T8-Alimosho | 219857397 | 11-AlimoshoINJ-T8-Alimosho | Faulty Electronic component | 500/5A LVMD | Batch 2 | mayfak | [10 empty] | 42 AKOWONJO RD LAGOS | PROJECT 643 | mayfak |  | 60022032808 | INSTALLED | 2024-09-05
179 | 0100300821 | SAVNIER GLOBAL SERVICES | OSHODI | IKOTUN | IKOTUN | 33-EjigboTCN-AGODO-SAMUEL SODE | IKOTUN | 33-EjigboTCN-AGODO | 60019060917 | 200/5A | [12 empty] | 100 ISOLO ROAD EGBE LAGOS | PROJECT 643 | QUINTEC |  | 060020123680 | INSTALLED | 2024-08-31
180 | 0100330459 | ESATER ALADE | OSHODI | IKOTUN | IKOTUN | 33-EjigboTCN-AGODO-ILEWE | IKOTUN | 33-EjigboTCN-AGODO | No meter | 200/5A | [12 empty] | 8.PALMER STREET IKOTUN LAGOS | PROJECT 643 | QUINTEC |  | 060022031743 | INSTALLED | 2024-08-31
181 | 0102609651 | HAMEED OLANREWAJU OMOTOSHO | OSHODI | IKOTUN | IKOTUN | 33-EjigboTCN-AGODO-OLOJO II | IKOTUN | 33-EjigboTCN-AGODO | 60020121278 | 500/5A |  |  | 0 | [10 empty] | PROJECT 643 | QUINTEC |  | 060022033570 | INSTALLED | 2024-08-31
182 | 0102799287 | ASIMIYU AZEEZ OLORUNSOGO | OSHODI | IKOTUN | IKOTUN | 33-EjigboTCN-AGODO-TEMIADARA | IKOTUN | 33-EjigboTCN-AGODO | 0 | 500/5A | [12 empty] | 1 Ambali Street, off Liasu Road, Egbe, Lagos | PROJECT 643 | QUINTEC |  | 060022033659 | INSTALLED | 2024-09-02
183 | 1006038601 | 11-AkuteINJ-T1-Ishashi-ZION | PUBLIC | ABULE EGBA | AKUTE | 11-AkuteINJ-T1-Ishashi | AKUTE | GROUND | 300 | 500/5A | [12 empty] | LOCATED AT ZION STREET VALLEY ESTATE ISHASHI AKUTE, OGUN STATE, ABULE EGBA BU. | PROJECT 643 | QUINTEC |  | 060022032418 | INSTALLED | 2024-09-02
184 | 0101306330 | MR TAIWO AND OLAWOYE | IKEJA | PTC | 200 | #NAME? | 11-PTCINJ-T3-Oba Akinjobi | 6.5793 | 3.3449 |  | Complete Installation | 500/5A LVMD | Batch 1 | demol | 2024-07-11 | [7 empty] | 4, OLUTOYE CLOSE, GRA, IKEJA | PROJECT 643 | DEMOL |  | 060022033599 | INSTALLED | 2024-09-03
185 | 0101269643 | M.SHOAGA OIL & GAS | AKOWONJO | AIT | AIT | PUBLIC | #N/A | 33-OtaTCN-AMJE | Complete Installation | 200/5A LVMD | [12 empty] | TOLL GATE ALONG LAGOS ABEOKUTA EXPRESSWAY | PROJECT 643 | mayfak |  | 60022032494 | INSTALLED | 2024-09-03
186 | 0102627483 | OLAITAN MOSES | ABULE-EGBA | IJAIYE | IJAIYE | PUBLIC | 60013090937 | 33-OtaTCN-AMJE | Complete Installation | 200/5A LVMD | Batch 2 | [11 empty] | FAGBEMI STREET | PROJECT 643 | QUINTEC |  | 060022033344 | INSTALLED | 2024-09-10
187 | 0101294615 | MR OLORUNTOLA JOHN(O K WATER) | PLT 2 O K CLOSE OFF GBELEYI STREET ALAKUKO. | ABULE-EGBA | IJAIYE | 200 | 201803012287 | 33-OtaTCN-AMJE | Complete Installation | 500/5A LVMD | Batch 2 |  |  | awaiting installations | [9 empty] | PROJECT 643 | QUINTEC |  | 060022033170 | INSTALLED | 2024-09-10
188 | 0102403987 | BAPTIST COMPOUND | SHOMOLU | OWOROSHONKI MEGA | PUBLIC | #NAME? | 11-Ilupeju BypassINJ-T1-Obanikoro |  |  | BAPTIST ACADEMY OBANIKORO LAGOS | Complete Installation | 500/5A LVMD | Batch 1 | tee n bee | [9 empty] | PROJECT 643 | TEE N BEE |  | 60022032714 | INSTALLED | 2024-09-20
189 | 0100346807 | IKEJA | PTC | OREGUN | 11-New AlausaINJ-T4-Allen | 11-New AlausaINJ-T4-Allen-DURO SHOLEYE | MD ON PUBLIC | MGBECHURIKE | 60021052634 |  | 200/5A |  |  | 19B ALLEN AVENUE IKEJA LAGOS | [9 empty] | PROJECT 643 | QUINTEC |  | 60022033334 | INSTALLED
190 | 1006040001 | 11-IgbogboINJ-T1-Ofin- Lajo CDA | IKORODU | IGBOGBO | IGBOGBO | 11-IgbogboINJ-T1-Ofin | PUBLIC | GROUND | CIS | POST-PAID | UNMETERED | N/A | N/A | N/A | 300 | 500/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5635 | 3.5028 | At Lajo Community, off Offin | PROJECT 643 | mayfak |  | 60022032423 | INSTALLED
191 | 1000244675 | 11-IjuINJ-T1-Ajuwon-ONI | ABULE EGBA | AKUTE | AKUTE | 11-IjuINJ-T1-Ajuwon | PUBLIC | GROUND | CIS | POST-PAID | Metered | 60019021349 | HEALTHY | MOJEC | 500 | 800/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6705 | 3.3453 | ONI JUNCTION AJUWON | PROJECT 643 | QUINTEC |  | 60022032421 | INSTALLED
192 | 1006039801 | 11-AmuwoINJ-T1-Ijesha Express-OKOEFO II | OSHODI | AMUWO | AMUWO | 11-AmuwoINJ-T1-Ijesha Express | PUBLIC | GROUND | CIS | NIL | UNMETERED | NIL | N/A | NIL | 300 | 500/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.4696 | 3.3199 | AMUWO ODOFIN LOW COST HOSUING MILE 2, AMUWO | PROJECT 643 | QUINTEC |  | 60022032811 | INSTALLED
193 | 1000240848 | 11-BeckleyINJ-T1-Beckley-BECKLEY | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Beckley | PUBLIC | GROUND | CIS | POST-PAID | METERED EST. | 201508004330 | FAULTY | CLOU | 500 | 800/5A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6602 | 3.2988 | BECKLEY JUNCTION | PROJECT 643 | QUINTEC |  | 60022033865 | INSTALLED
194 | 0101272892 | 11-OpebiINJ-T1-Salvation-GAFARI BALOGUN | IKEJA | OREGUN | OREGUN | 11-OpebiINJ-T1-Salvation | MD ON PUBLIC | NJOY HOTEL | [6 empty] | 300 | 500/5A | [6 empty] | 6,GAFARI BALOGUN STREET OFF SAMUEL AWONIYI STREET, IKEJA | PROJECT 643 | QUINTEC |  | 60022031668 | INSTALLED
195 | 100395751 |  | ABULE-EGBA | IJAIYE | IJAIYE | 33-OtaTCN-AMJE |  | EJIKE EARNEST | [6 empty] | 300 | 500/5A | [6 empty] | 2 LAWAL STR. LAGOS | PROJECT 643 | QUINTEC |  | 60022032508 | INSTALLED
196 | 1006024801 | 11-IjuINJ-T1-Galilee-OLOWOLAJUOGBON 2 | ABULE EGBA | IJU | IJU | 11-IjuINJ-T1-Galilee | PUBLIC | GROUND | CIS | NIL | UNMETERED | NIL | NIL | NIL | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6635 | 3.3342 | 9, OLOWOLAJUOGBON STREET, OBAWOLE | PROJECT 643 | QUINTEC |  | 60022032531 | INSTALLED
197 | 1006042401 | 11-IgbogboINJ-T1-Bayeku-Greenland CDA | IKORODU | Igbogbo | Igbogbo | 11-IgbogboINJ-T1-Bayeku | PUBLIC | GROUND | CIS | POST-PAID | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5654 | 3.5294 | Located at Igbogbo baiyeku road, ikorodu lagos. | PROJECT 643 | aderalph |  | 60022033751 | INSTALLED
198 | 1006042403 | 11-OdogunyanINJ-Ita Oluwo-Charity | IKORODU | Odogunyan | Odogunyan | 11-OdogunyanINJ-Ita Oluwo | PUBLIC | GROUND | CIS | POST-PAID | UNMETERED | N/A | N/A | N/A | 300 | 500/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6932 | 3.4742 | Located at Agbede road, vis Ita Oluwo, Ikorodu Lagos. | PROJECT 643 | aderalph |  | 60022032920 | INSTALLED
199 | 1006042402 | 11-OwutuINJ-T2-Isawo-Mawere Akorede | IKORODU | Owutu | Owutu | 11-OwutuINJ-T2-Isawo | PUBLIC | GROUND | CIS | POST-PAID | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6481 | 3.4411 | Located at Mawere Street, Isawo Ikorodu Lagos. | PROJECT 643 | aderalph |  | 60022032424 | INSTALLED
200 | 1006042201 | 33-OdogunyanTCN-Fakale Maya-Eyita III | IKORODU | Odogunyan | Odogunyan | 33-OdogunyanTCN-Fakale Maya | PUBLIC | GROUND | CIS | POST-PAID | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6956 | 3.5234 | Located at Fakale Village, Ikorodu Lagos. | PROJECT 643 | aderalph |  | 60022033624 | INSTALLED
201 | 1006042202 | 33-OdogunyanTCN-Fakale Maya-Oke Agbodo II | IKORODU | Epe | Epe | 33-OdogunyanTCN-Fakale Maya | PUBLIC | GROUND | CIS | POST-PAID | UNMETERED | N/A | N/A | N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.685 | 3.5918 | Located at Maya Road, Aiyetoro Ikorodu Lagos. | PROJECT 643 | aderalph |  | 60022032605 | INSTALLED
202 | 1006040801 | 11-IjuINJ-Asore-OJUKO | ABULE EGBA | AKUTE | AKUTE | 11-IjuINJ-T1-Asore | PUBLIC | GROUND | CIS | NIL | UNMETERED | NIL | #N/A | #N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6621 | 3.3618 | Ojuko street, Old soldier Bus stop, Abule Ojo, Alagbole, Akute, Ogun state | PROJECT 643 | DEMOL |  | 60022032412 | INSTALLED
203 | 1006041001 | 11-BeckleyINJ-T1-Agbe road-FUNSHO OWOYEMI | ABULE EGBA | FAGBA | FAGBA | 11-BeckleyINJ-T1-Agbe road | PUBLIC | GROUND | CIS | NIL | UNMETERED | NIL | #N/A | #N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6704 | 3.3014 | Akinwande Ogundipe Cl, Ifako-Ijaiye, Lagos 101232, Lagos | PROJECT 643 | DEMOL |  | 60022033739 | INSTALLED
204 | 1006041002 | 11-LambeINJ-T1-Jolasco-ONIBUDO 3 | ABULE EGBA | AKUTE | AKUTE | 11-LambeINJ-T1-Jolasco | PUBLIC | GROUND | CIS | NIL | UNMETERED | NIL | #N/A | #N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.7009 | 3.3607 | Phase 2, Onibudo Estate, Onibudo, Along Akute-Ijoko Rd, Ogun State | PROJECT 643 | DEMOL |  | 60022033540 | INSTALLED
205 | 1006041003 | 11-LambeINJ-T1-Matogun-PROGRESSIVE CDA (BEULAH) | ABULE EGBA | LAMBE | LAMBE | 11-LambeINJ-T1-Matogun | PUBLIC | GROUND | CIS | NIL | UNMETERED | NIL | #N/A | #N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6984 | 3.3253 | 3 Joseph Ediku Street, Matogun Rd, Oke Aro | PROJECT 643 | DEMOL |  | 60022033776 | INSTALLED
206 | 1006040802 | 11-AkuteINJ-T1-Oyeyemi-ARIFANLA 2 | ABULE EGBA | AKUTE | AKUTE | 11-AkuteINJ-T1-Oyeyemi | PUBLIC | GROUND | CIS | NIL | UNMETERED | NIL | #N/A | #N/A | 500 | 800/5A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.6833 | 3.3676 | Jimoh and Tairu street, Arifanla junction, Akute, Ogun state | PROJECT 643 | DEMOL |  | 60022032795 | INSTALLED
207 | 102641619 | TOMOTHY NNANNA | ABULE-EGBA | IJAIYE | IJAIYE | PUBLIC | 217217134 | 33-OtaTCN-AMJE | Complete Installation | 200/5A LVMD | Batch 2 |  |  |  | 100 | 200/5A LVMD | NOT CONNECTED | NOT COMMISSIONED | HEALTHY |  |  |  | 8/12 IDOWU,OYA STREET, AGBADO, LAGOS. | PROJECT 643 | QUINTEC |  | 060022033335 | INSTALLED
208 | 100700815 | ATOLAGBE OLAMILEKAN | SHOMOLU | ILUPEJU | ILUPEJU |  |  |  |  | 200/5A LVMD |  |  |  |  | 100 | 200/5A LVMD | NOT CONNECTED | NOT COMMISSIONED | HEALTHY |  |  |  | 14 ARIKEWUYO STREET | PROJECT 643 | mayfak |  | 060022033202 | INSTALLED
209 | 101631503 | KORDXY NIGERIA LIMITED | IKEJA | OREGUN | OREGUN |  |  |  |  | 300/5A |  |  |  |  | 200 | 300/5A LVMD | [6 empty] | 14B ONDO CLOSE, ALLEN AVENUE | PROJECT 643 | mayfak |  | 60022032820 | INSTALLED
210 | ASK JOHN FOR THE ADDRESS | ASK JOHN FOR THE ADDRESS | SHOMOLU | IGBOBI | IGBOBI | NA |  |  |  | 200/5A |  |  |  |  | 100 | 200/5A LVMD | NOT CONNECTED | [5 empty] | 17 ,JIBOWU ST | PROJECT 643 | mayfak |  | 60021080524 | INSTALLED
211 | 101173244 | 11-PTCINJ-T3-Oba Akinjobi | IKEJA | PTC | PTC | 11-PTCINJ-T3-Oba Akinjobi | 201803011861 |  |  | 500/5A |  |  |  |  | 300 | 500/ 5 A | [6 empty] | 4,AYOOLA COKER STREET GRA IKEJA | PROJECT 643 | DEMOL |  | 60022032819 | INSTALLED
212 | 0100068412 | R . C . C. G | IKEJA | OGBA | OGBA | 300 | 11092234 | 11-OgbaINJ-T1-Ijaye | Complete Installation | 500/5A LVMD | Batch 2 |  | 60022033093 |  | 300 | 500/ 5 A | [6 empty] | PLT3 OBA OGUNJI ROAD AGEGE LAGOS. | PROJECT 643 | vicbonny |  | 60022033093 | INSTALLED
213 | 1012352071 | 11-OgbaNJ-T1-Ijaye | IKEJA | OGBA | OGBA |  | MD ON PUBLIC | Sariatu Oladimeji |  |  | 200/5A | [11 empty] | 15 Adepegba Street Keke, Agege | PROJECT 643 | mayfak |  | 60022033669 | INSTALLED
214 | 0100068021 | TECO HOUSE |  | IKEJA | OBA AKRAN | 100 | 201903012579 | 33-OgbaTCN-NEW OJODU | Complete Installation | 200/5A LVMD | Batch 2 | well done | [10 empty] | CBD BEHINDE OSTRA HOTEL ALAUSA -IKEJA LAGOS | PROJECT 643 | vicbonny |  | 060022033707 | INSTALLED
215 | 100363451 | ST JUDE ANGLICAN CHURCH | IKEJA | OBA AKRAN | OBA AKRAN | 200 - 300/5Amps | [16 empty] | PLOT 5, ADEMOLA AJASA OMOLE PHASE 1 , IKEJA , LAGOS | PROJECT 643 | TEE N BEE |  | 060022032482 | INSTALLED
216 | 102844586 | MICHAEL OLUSHOLA ADEROGBA |  | IKEJA | OREGUN | 200/ 5 A | [9 empty] | 200/5A LVMD | [6 empty] | 7, Olufunke atitebi street, julie estate, oregun | PROJECT 643 | mayfak |  | 60022033328 | INSTALLED | 2024-11-08
217 | 1001605926 | Madam Winifse Adunola | IKEJA | PTC | PTC | 11-PTCINJ-T2-Medical | PRIVATE | GROUND MOUNTED | CIS | Postpaid | METERED | NIL | NIL | NIL | MD on Public | 200/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | N/A | N/A | 10 Oremeji Str Ikeja 85/S25/110779 Old A/C No 25/05/02/2431 | LVCT | vicbonny | 0102445392 | 060022033823 | INSTALLED | 2024-11-12
218 | 1001605924 | Owie James I. | IKEJA | PTC | PTC | 11-PTCINJ-T2-Medical | PRIVATE | GROUND MOUNTED | CIS | Postpaid | METERED | NIL | NIL | NIL | MD on Public | 200/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | N/A | N/A | 12 .Adepele Str.Off Simbiat Abiola Way.Ikeja Lagos. | LVCT | QUINTEC | 0100350146 | 60022033808 | INSTALLED | 2024-11-12
219 | 1001605924 | Adeniranye Oladapo A | IKEJA | PTC | PTC | 11-PTCINJ-T2-Medical | PRIVATE | GROUND MOUNTED | CIS | Postpaid | METERED | NIL | NIL | NIL | MD on Public | 200/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | N/A | N/A | 2 Adepele Str 90/P50/00804 Ikeja | LVCT | QUINTEC | 0100348076 | 60022032048 | INSTALLED | 2024-11-12
220 | 1001605916 | Oluwasanya Yinka Olusesan | IKEJA | PTC | PTC | 11-PTCINJ-T2-Medical | PRIVATE | GROUND MOUNTED | CIS | Postpaid | METERED | NIL | NIL | NIL | MD on Public | 200/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | N/A | N/A | 2.Oriyomi Street Ikeja Lagos. | LVCT | mayfak | 0100349049 | 60022033247 | INSTALLED | 2024-11-12
221 | 1001605916 | Step-Up Saloon | IKEJA | PTC | PTC | 11-PTCINJ-T2-Medical | PRIVATE | GROUND MOUNTED | CIS | Postpaid | METERED | NIL | NIL | NIL | MD on Public | 200/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | N/A | N/A | 3. Oriyomi Street Ikeja. Lagos | LVCT | mayfak | 0101006017 | 60022033566 | INSTALLED | 2024-11-12
222 | 1000204557 | 0102167044 | OCHAD SCHOOL'S | SHOMOLU | OWOROSHONKI MEGA | 11-OworoINJ-T3-Anthony | 11-OworoINJ-T3-Anthony | PRIVATE | GROUND MOUNTED | CIS | POST-PAID | NIL | NIL | NIL | MD on Public | 200/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.5545 | 3.386 | TUNDE BAKARE ST | LVCT | aderalph |  | 60022031687 | INSTALLED | 2024-11-21
223 | 1001212432 | Dorcas Olubanke Olatokun | IKEJA | PTC | PTC | 11-PTCINJ-T2-Medical | PRIVATE | GROUND MOUNTED | CIS | Postpaid | METERED | NIL | NIL | NIL | MD on Public | 200/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | N/A | N/A | 4 Otigba Street Ikeja Lagos | LVCT | DEMOL | 0101918507 | 60022031868 | INSTALLED | 2024-11-19
224 | 1004563996 | Eunice Odunubi | IKEJA | PTC | PTC | 11-PTCINJ-T2-Medical | PRIVATE | GROUND MOUNTED | CIS | Postpaid | METERED | NIL | NIL | NIL | MD on Public | 200/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | N/A | N/A | 11 Otigba Str Ikeja Old Account 25/05/01/03611 | LVCT | DEMOL | 0100347987 | 60022033563 | INSTALLED | 2024-11-26
225 | 1006042203 | 11-Ijaiye OjokoroINJ-T1-Abeokuta Express - BEN BLUE ROOF ESTATE | AKOWONJO | AIT | AIT | 11-Ijaiye OjokoroINJ-T1-Abeokuta Express | PUBLIC | GROUND | CIS | NIL | UNMETERED | NIL | NIL | NIL | NIL | 300 | 500/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | 6.652 | 3.2612 | AT KOLAPO SALAKO STREET, OPPOSITE BEN BLUE ROOF CRESCENT, ALAGBADO, AMIKANLE, LAGOS | LVCT | mayfak |  | 060022032454 | INSTALLED | 2024-12-06
226 | 0100069410 | ADEBISI W | OSHODI | OKE-AFA | OKE-AFA | 11-Oke AfaINJ-T2-Ilamoshe | PRIVATE | GROUND MOUNTED | CIS | POST-PAID | NIL | NIL | NIL | NIL | NIL | 300 | 500/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | NA | NA | 40 NNPC ROAD EJIGBO LAGOS | LVCT | mayfak |  | 060022032525 | INSTALLED | 2024-12-09
227 | 0100327331 | ADEKUNLE OSHIN ., | OSHODI | OKE-AFA | OKE-AFA | 11-Oke AfaINJ-T1-Bucknor | PRIVATE | GROUND MOUNTED | CIS | POST-PAID | NIL | NIL | NIL | NIL | NIL | MD on Public | 200/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | NA | 67 ISHERI ROAD BUCKNOR LAGOS | LVCT | mayfak |  | 60022033365 | INSTALLED | 2024-12-12
228 | 0102504145 | MARY OLAYINKA ADELAJA | SHOMOLU | ILUPEJU MEGA | ILUPEJU MEGA | 11-IlupejuINJ-T3-Coker | PRIVATE | GROUND MOUNTED | CIS | POST-PAID | NIL | NIL | NIL | NIL | NIL | MD on Public | 300/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | NA | 16, AINA GEORGE STREET, COKER R/ABOUT B/STOP, ILUPEJU, LAGOS | LVCT | DEMOL | 07010826286 | 060022032453 | INSTALLED | 2024-12-16
229 | 1006044401 | 11-AbesanINJ-T1-Baruwa-ALHAJI WASIU | AKOWONJO | IPAJA | IPAJA | 11-AbesanINJ-T1-Baruwa | PUBLIC | GROUND | CIS | NIL | UNMETERED | NIL | NIL | NIL | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5879 | 3.2672 | Ipaja, Lagos State | LVCT | mayfak | New Approvals | 60022031653 | INSTALLED | 2024-12-18
230 | 1006044402 | 11-New GowonINJ-T1-Unity-ODUWOLE III | AKOWONJO | ABULE ODU | ABULE ODU | 11-New GowonINJ-T1-Unity | PUBLIC | GROUND | CIS | NIL | UNMETERED | NIL | NIL | NIL | 500 | 800/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5891 | 3.2828 | Abule Odu, Lagos State | LVCT | mayfak | New Approvals | 60022031889 | INSTALLED | 2024-12-18
231 | 1006044403 | 11-AyetoroINJ-T1-Itele- OLORUNSOGO 2 | AKOWONJO | AYOBO | AYOBO | 11-AyetoroINJ-T1-Itele | PUBLIC | GROUND | CIS | NIL | UNMETERED | NIL | NIL | NIL | 300 | 500/ 5 A | NOT CONNECTED | NOT COMMISSIONED | HEALTHY | INACTIVE | 6.5853 | 3.1901 | Ayobo, Lagos State | LVCT | mayfak | New Approvals | 60022033231 | INSTALLED | 2024-12-16
232 | 1000255229 (Checkmeter) | 33-IkoroduTCN-FAKALE Source-ADEITE (Additional check metering) | IKORODU | ODOGUNYAN | ODOGUNYAN | 33-IkoroduTCN-FAKALE Source | PUBLIC | GROUND | CIS | POST-PAID | METERED | 60017112400 | FUNCTIONAL | MOJEC | 100/500 | 200/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | 6.6849 | 3.4864 | ADEITE STREET | LVCT | DEMOL |  | 60022033354 | INSTALLED | 2024-12-18
233 | 1000240876 | SEWEDO DAVID GANTHONU | ABULE-EGBA | IJU | IJU | 11-YidiINJ-T1-Osoba | PRIVATE | GROUND MOUNTED | CIS | POST-PAID | NIL | NIL | NIL | NIL | MD on Public | 300/ 5 A | CONNECTED | COMMISSIONED | HEALTHY | ACTIVE | NA | NA | 13, OKE ARO ROAD IJU ISHAGA | LVCT | mayfak | 0101496598 | 60022032655 | INSTALLED | 2024-01-04

## 172 METERS ALLOCATED
S/N | METER NO | RATING | SBC | STATUS
1 | 060022033272 | 200/5A | TEE N BEE | INSTALLED
2 | 060022033311 | 200/5A | TEE N BEE | INSTALLED
3 | 060022033264 | 200/5A | TEE N BEE | INSTALLED
4 | 060022033331 | 200/5A | TEE N BEE | INSTALLED
5 | 060022031843 | 200/5A | TEE N BEE | INSTALLED
6 | 060022033343 | 200/5A | TEE N BEE | INSTALLED
7 | 060022031880 | 200/5A | TEE N BEE | INSTALLED
8 | 060022032581 | 500/5A | TEE N BEE | INSTALLED
9 | 060022032714 | 500/5A | TEE N BEE | INSTALLED
10 | 060022033445 | 500/5A | TEE N BEE | INSTALLED
11 | 060022032745 | 500/5A | TEE N BEE | INSTALLED
12 | 060022032862 | 500/5A | TEE N BEE | INSTALLED
13 | 060022031733 | 500/5A | TEE N BEE | INSTALLED
14 | 060022032428 | 800/5A | TEE N BEE | INSTALLED
15 | 60022033001 | 800/5A | TEE N BEE | INSTALLED
16 | 060022033792 | 800/5A | TEE N BEE | INSTALLED
17 | 60021051363 | WC | TEE N BEE | INSTALLED
18 | 60021052779 | WC | TEE N BEE | INSTALLED
19 | 060022031881 | 200/5A | ADERALPH | INSTALLED
20 | 060022033263 | 200/5A | ADERALPH | INSTALLED
21 | 060022033714 | 500/5A | ADERALPH | INSTALLED
22 | 060022033597 | 500/5A | ADERALPH | INSTALLED
23 | 060022032747 | 500/5A | ADERALPH | INSTALLED
24 | 060022032450 | 500/5A | ADERALPH | INSTALLED
25 | 060022033583 | 500/5A | ADERALPH | INSTALLED
26 | 060022033171 | 500/5A | ADERALPH | INSTALLED
27 | 060022033013 | 500/5A | ADERALPH | INSTALLED
28 | 060022033161 | 800/5A | ADERALPH | INSTALLED
29 | 060022033026 | 800/5A | ADERALPH | INSTALLED
30 | 060022033763 | 800/5A | ADERALPH | INSTALLED
31 | 060022032717 | 800/5A | ADERALPH | INSTALLED
32 | 060022031685 | 200/5A | ADERALPH | INSTALLED
33 | 060022033206 | 200/5A | ADERALPH | INSTALLED
34 | 060020123715 | 200/5A | ADERALPH | INSTALLED
35 | 060022031814 | 200/5A | ADERALPH | installed
36 | 60022033172 | 200/5A | ADERALPH | installed
37 | 60021051745 | WC | MAYFAK | INSTALLED
38 | 060022033865 | 800/5A | ADERALPH | installed
39 | 60020123623 | 200/5A | ALL SOLUTION | INSTALLED
40 | 60022033327 | 200/5A | ALL SOLUTION | INSTALLED
41 | 60022033955 | 200/5A | ALL SOLUTION | INSTALLED
42 | 60022032523 | 500/5A | ALL SOLUTION | INSTALLED
43 | 60022033816 | 500/5A | ALL SOLUTION | INSTALLED
44 | 60022033240 | 500/5A | ALL SOLUTION | INSTALLED
45 | 60022031661 | 800/5A | ALL SOLUTION | INSTALLED
46 | 60022032636 | 500/5A | ALL SOLUTION | INSTALLED
47 | 60022032434 | 800/5A | ALL SOLUTION | INSTALLED
48 | 60022032443 | 800/5A | ALL SOLUTION | INSTALLED
49 | 60020123697 | 200/5A | ALL SOLUTION | INSTALLED
50 | 60022031744 | 200/5A | ALL SOLUTION | INSTALLED
51 | 60022033363 | 200/5A | ALL SOLUTION | INSTALLED
52 | 60021052788 | WC | DEMOL | INSTALLED
53 | 60021050408 | WC | DEMOL | INSTALLED
54 | 60021052328 | WC | DEMOL | INSTALLED
55 | 60021052670 | WC | DEMOL | INSTALLED
56 | 060022032670 | 200/5A | DEMOL | INSTALLED
57 | 060022033851 | 200/5A | DEMOL | INSTALLED
58 | 060022033273 | 200/5A | DEMOL | INSTALLED
59 | 060022032766 | 800/5A | DEMOL | INSTALLED
60 | 060022032945 | 800/5A | DEMOL | INSTALLED
61 | 060022032409 | 800/5A | DEMOL | INSTALLED
62 | 060022033599 | 500/5A | DEMOL | INSTALLED
63 | 060022033729 | 500/5A | DEMOL | INSTALLED
64 | 060021051071 | WC | ALL SOLUTION | INSTALLED
65 | 060022031786 | 300/5A | DEMOL | INSTALLED
66 | 060022032808 | 500/5A | DEMOL | INSTALLED
67 | 060022032820 | 300/5A | DEMOL | installed
68 | 060022032819 | 500/5A | DEMOL | installed
69 | 060022032669 | 200/5A | MAYFAK | INSTALLED
70 | 060022031878 | 200/5A | MAYFAK | INSTALLED
71 | 060022031689 | 200/5A | MAYFAK | INSTALLED
72 | 60021052239 | WC | ADERALPH | INSTALLED
73 | 060022033355 | 200/5A | MAYFAK | INSTALLED
74 | 060022033567 | 500/5A | MAYFAK | INSTALLED
75 | 060022033601 | 500/5A | MAYFAK | INSTALLED
76 | 060022031760 | 500/5A | MAYFAK | INSTALLED
77 | 060022033747 | 800/5A | MAYFAK | INSTALLED
78 | 060022033474 | 800/5A | MAYFAK | INSTALLED
79 | 060022032476 | 800/5A | MAYFAK | INSTALLED
80 | 060022032406 | 800/5A | MAYFAK | INSTALLED
81 | 060022032908 | 800/5A | MAYFAK | INSTALLED
82 | 060022033722 | 200/5A | MAYFAK | INSTALLED
83 | 060022031870 | 200/5A | MAYFAK | INSTALLED
84 | 060022032494 | 200/5A | MAYFAK | INSTALLED
85 | 060022033491 | 200/5A | MAYFAK | INSTALLED
86 | 060022032407 | 200/5A | MAYFAK | INSTALLED
87 | 060022033727 | 500/5A | MAYFAK | INSTALLED
88 | 60021080524 | 200/5A | MAYFAK | LIGHT UP LAGOS METER WITH MAYFAK installed for project 643
89 | 60022033202 | 200/5A | MAYFAK | installed
90 | 60022033669 | 200/5A | MAYFAK | installed
91 | 060022033328 | 200/5A | MAYFAK | Meter installed
92 | 060020123679 | 200/5A | QUINTEC | INSTALLED
93 | 060022033175 | 200/5A | QUINTEC | INSTALLED
94 | 060021051084 | WC | ALL SOLUTION | INSTALLED BY VICBONNY
95 | 60021052879 | WC | ADERALPH | INSTALLED BY VICBONNY
96 | 060022032817 | 500/5A | QUINTEC | INSTALLED
97 | 060022032662 | 500/5A | QUINTEC | INSTALLED
98 | 060022032413 | 800/5A | QUINTEC | INSTALLED
99 | 060022031142 | 200/5A | QUINTEC | INSTALLED
100 | 060022032792 | 800/5A | QUINTEC | INSTALLED
101 | 060020123680 | 200/5A | QUINTEC | INSTALLED
102 | 060022031743 | 200/5A | QUINTEC | INSTALLED
103 | 060022033344 | 200/5A | QUINTEC | INSTALLED
104 | 060022032109 | 200/5A | QUINTEC | INSTALLED
105 | 060022033659 | 500/5A | QUINTEC | INSTALLED
106 | 060022033170 | 500/5A | QUINTEC | INSTALLED
107 | 060022032418 | 500/5A | QUINTEC | INSTALLED
108 | 060022033570 | 500/5A | QUINTEC | INSTALLED
109 | 060022033334 | 200/5A | QUINTEC | installed
110 | 060022031668 | 200/5A | QUINTEC | installed
111 | 060022032421 | 800/5A | QUINTEC | installed
112 | 060022033335 | 200/5A | QUINTEC | installed
113 | 060022031672 | 500/5A | VICBONNY | INSTALLED
114 | 060022032720 | 500/5A | VICBONNY | INSTALLED
115 | 060022033857 | 200/5A | VICBONNY | INSTALLED
116 | 060022033356 | 200/5A | VICBONNY | INSTALLED
117 | 060022033456 | 200/5A | VICBONNY | INSTALLED
118 | 060022033782 | 800/5A | VICBONNY | INSTALLED
119 | 060022033618 | 500/5A | VICBONNY | INSTALLED
120 | 060022032771 | 500/5A | VICBONNY | INSTALLED
121 | 060022033811 | 500/5A | VICBONNY | INSTALLED
122 | 060022031695 | 500/5A | VICBONNY | INSTALLED
123 | 060022033330 | 200/5A | VICBONNY | INSTALLED
124 | 060022033847 | 200/5A | VICBONNY | INSTALLED
125 | 060022033346 | 200/5A | VICBONNY | INSTALLED
126 | 060022033686 | 800/5A | VICBONNY | INSTALLED
127 | 060022033707 | 200/5A | VICBONNY | INSTALLED
128 | 060022032582 | 200/5A | WELLDONE/VICBONNY | INSTALLED
129 | 60020123084 | 200/5A | WELLDONE/VICBONNY | INSTALLED
130 | 60022032946 | 800/5A | WELLDONE/VICBONNY | INSTALLED
131 | 60022033095 | 500/5A | WELLDONE/VICBONNY | INSTALLED
132 | 60022033130 | 800/5A | WELLDONE/VICBONNY | INSTALLED
133 | 60022033314 | 500/5A | WELLDONE/VICBONNY | INSTALLED
134 | 60022033369 | 200/5A | WELLDONE/VICBONNY | INSTALLED
135 | 60022033716 | 200/5A | WELLDONE/VICBONNY | INSTALLED
136 | 060022031844 | 200/5A | WELLDONE/VICBONNY | INSTALLED
137 | 060022033430 | 200/5A | WELLDONE/VICBONNY | INSTALLED
138 | 60022032859 | 800/5A | WELLDONE/VICBONNY | INSTALLED
139 | 60022033805 | 800/5A | WELLDONE/VICBONNY | INSTALLED
140 | 60022033093 | 500/5A | WELLDONE/VICBONNY | INSTALLED
141 | 60022033808 | 200/5A | quintec | INSTALLED
142 | 60022032048 | 200/5A | quintec | INSTALLED
143 | 060022033823 | 200/5A | VICBONNY | INSTALLED
144 | 60022033247 | 200/5A | mayfak | INSTALLED
145 | 60022033566 | 200/5A | mayfak | INSTALLED
146 | 060022031687 | 200/5A | ADERALPH | INSTALLED
147 | 060022033563 | 200/5A | DEMOL | INSTALLED
148 | 060022031868 | 200/5A | DEMOL | INSTALLED
149 | 060022032425 | 800/5A | MAYFAK | INSTALLED
150 | 060022032454 | 500/5A | DEMOL | INSTALLED
151 | 060022032525 | 500/5A | VICBONNY | INSTALLED
152 | 060022033365 | 200/5A | VICBONNY | INSTALLED
153 | 060021051155 | WC | MAYFAK | INSTALLED
154 | 060021052541 | WC | MAYFAK | INSTALLED
155 | 060022032453 | 500/5A | DEMOL | INSTALLED
156 | 060022033354 | 200/5A | DEMOL | INSTALLED
157 | 060022032655 | 300/5A | MAYFAK | INSTALLED
158 | 060022033209 | 200/5A | ADERALPH | CONFIRMED WITH SBC
142 | 60022031677 | 200/5A | ALL SOLUTION | CONFIRMED WITH SBC
160 | 60022032732 | 800/5A | ALL SOLUTION | CONFIRMED WITH SBC
161 | 60022032417 | 1200/5A | ALL SOLUTION | CONFIRMED WITH SBC
162 | 60022031757 | 200/5A | ALL SOLUTION | CONFIRMED WITH SBC
163 | 60022031688 | 200/5A | ALL SOLUTION | CONFIRMED WITH SBC
164 | 60020123577 | 200/5A | ALL SOLUTION | CONFIRMED WITH SBC
165 | 60022033157 | 800/5A | ALL SOLUTION | CONFIRMED WITH SBC
166 | 060022031858 | 500/5A | ALL SOLUTION | CONFIRMED WITH SBC
167 | 060022033000 | 500/5A | DEMOL | CONFIRMED WITH SBC/Meter at PTC undertaking
168 | 060022032667 | 200/5A | DEMOL | CONFIRMED WITH SBC/Meter at PTC undertaking
169 | 60022031653 | 800/5A | MAYFAK | CONFIRMED WITH SBC
170 | 060022032408 | 800/5A | QUINTEC | CONFIRMED WITH SBC
164 | 60022032419 | 1200/5A | VICBONNY | CONFIRMED WITH SBC
172 | 060020123711 | 200/5A | VICBONNY | CONFIRMED WITH SBC
173 | 060022033362 | 200/5A | VICBONNY | CONFIRMED WITH SBC
174 | 060022032818 | 800/5A | VICBONNY | CONFIRMED WITH SBC
175 | 060022033248 | 200/5A | VICBONNY | CONFIRMED WITH SBC
176 | 060022033364 | 200/5A | VICBONNY | CONFIRMED WITH SBC
177 | 60022032479 | 500/5A | VICBONNY | CONFIRMED WITH SBC
178 | 60022033231 | 500/5A | VICBONNY | CONFIRMED WITH SBC
179 | 060022033205 | 200/5A | VICBONNY | CONFIRMED WITH SBC
180 | 060021051533 | WC | MAYFAK | CONFIRMED WITH SBC
181 | 060022033333 | 200/5A | TEE N BEE | FAULTY METER RETURNED TO IE
182 | 60022033207 | 200/5A | ADERALPH | FAULTY METER RETURNED TO IE
183 | 60022033452 | 200/5A | ADERALPH | FAULTY METER RETURNED TO IE
184 | 060022033180 | 200/5A | ADERALPH | FAULTY METER RETURNED TO IE
185 | 060022033457 | 500/5A | MAYFAK | Faulty METER INSTALLED BUT HAVE CT ISSUE AND HAS BEEN RETRIEVED BY MAYFAK TO INSTALL ANOTHER METER/meter returned to ikeja
186 | 60020120127 |  | mayfak | FAULTY YELLOW PHASE RETURNED TO IE
187 | 60022031296 |  | mayfak | Faulty METER INSTALLED BUT HAVE CT ISSUE AND HAS BEEN RETRIEVED BY MAYFAK TO INSTALL ANOTHER METER/meter returned to ikeja
188 | 060022032849 | 800/5A | TEE N BEE | FAULTY YELLOW PHASE RETURNED TO IE

## 40 ALLOCATED
CORRECT METER WITH VICBONNY |  |  |  | CORRECT METER WITH ADERALPH
S/N | METER NUMBER | RATING | Status | S/N | METER NUMBER | RATING | Status | ANALYSIS
1 | 060022032415 | 500/5A | METER WITH VICBONY | 1 | 060022033540 | 800/5A | INSTALLED | BY DEMOL
2 | 060022033227 | 500/5A | METER WITH VICBONY | 2 | 060022032424 | 800/5A | INSTALLED
3 | 060022033724 | 500/5A | METER WITH VICBONY | 3 | 060022032531 | 800/5A | INSTALLED
4 | 060022033819 | 500/5A | METER WITH VICBONY | 4 | 060022032412 | 800/5A | INSTALLED | BY DEMOL
5 | 060022033135 | 800/5A | METER WITH VICBONY | 5 | 060022033776 | 800/5A | INSTALLED | BY DEMOL
6 | 060022032734 | 800/5A | METER WITH VICBONY | 6 | 060022032795 | 800/5A | INSTALLED | BY DEMOL
7 | 060022032435 | 800/5A | METER WITH VICBONY | 7 | 060022033739 | 800/5A | INSTALLED | BY DEMOL
8 | 060022033072 | 800/5A | METER WITH VICBONY | 8 | 060022033751 | 800/5A | INSTALLED
9 | 060022033536 | 800/5A | METER WITH VICBONY | 9 | 060022032605 | 800/5A | INSTALLED
10 | 060022033838 | 800/5A | METER WITH VICBONY | 10 | 060022033624 | 800/5A | INSTALLED
11 | 060022033898 | 800/5A | METER WITH VICBONY | 11 | 060022032920 | 500/5A | INSTALLED
12 | 060022031808 | 800/5A | METER WITH VICBONY | 12 | 060022032508 | 500/5A | INSTALLED
13 | 060022031837 | 800/5A | METER WITH VICBONY | 13 | 060022032811 | 500/5A | INSTALLED
14 | 060022032809 | 800/5A | METER WITH VICBONY | 14 | 060022032423 | 500/5A | INSTALLED
15 | 060022032757 | 800/5A | METER WITH VICBONY | 15 | 060022033001 | 800/5A | INSTALLED | METER GIVEN TO TEE N BEE
19 | 060022032991 | 800/5A | METER WITH VICBONY | 16 | 060022032482 | 500/5A | INSTALLED | METER GIVEN TO TEE N BEE
16 | 060022033750 | 800/5A | METER WITH VICBONY | 17 | 060022033002 | 800/5A | AWAITING INSTALLATION | METER WITH ADERALF
17 | 060022033173 | 800/5A | METER WITH VICBONY | 18 | 060022031653 | 800/5A | AWAITING INSTALLATION | METER GIVING TO MOSES AND WITH MAYFAK
18 | 060022033150 | 800/5A | METER WITH VICBONY | 19 | 060022031889 | 800/5A | AWAITING INSTALLATION | METER WITH MOSES MAYFAK
20 | 60022032451 | 500/5A | METER WITH VICBONY | 20 | 060022033818 | 800/5A | AWAITING INSTALLATION | METER WITH ADERALF

## Probe (hidden)
S/N | METER NO | RATING | SBC | STATUS
| 60022031897 |  | ALL SOLUTION | retrieved from OFF ADEOWO STREET, LASUNWON (INSTALLER TO EXPLAIN METER WHEREABOUT)
| 60022031725 |  | DEMOL | retrieved from Agodo alara (INSTALLER TO EXPLAIN METER WHEREABOUT)
| 60022031297 |  | quintec | retrieved from lowa street (INSTALLER TO EXPLAIN METER WHEREABOUT)
| 60022033796 |  | quintec | retrieved from cooperative estate (INSTALLER TO EXPLAIN METER WHEREABOUT)

## issue (hidden)
S/N | CIS Account No. | NAME | BU | UT | Transformer Capacity | Meter No | Feeder | Coordinates (LAT) | Coordinates (LONG) | ADDRESS | Meter current condition | Requirement | Remark | Installer | METER NO ASSIGNED FOR LOCATION | INSTALLATION STATUS/ISSUES | DAY OUTAGE WAS SCHEDULE
1 | 0101846534 | O'SHEY | IKEJA | PTC | PUBLIC | #NAME? | 11-Adekunle FajuyiINJ-T1-Isaac John |  |  | 29 ISAAC JOHN GRA. IKEJA LAGOS. | Complete Installation | 200/5A LVMD | Batch 1 | vicbonny | 060022033205 | ALREADY METERED/AWAIT NEW LOCATION FROM IE | 2024-07-09
2 | 0100349046 | YOUNG TITILOLA | IKEJA | PTC | PUBLIC | #NAME? | 11-Adekunle FajuyiINJ-T1-Isaac John |  |  | 58A, ISAAC JOHN STREET, GRA , IKEJA , LAGOS | Complete Installation | 500/5A LVMD | Batch 1 | vicbonny | 060022032818 | ALREADY METERED/AWAIT NEW LOCATION FROM IE | 2024-07-09
3 | 0100070089 | LAGOS STATE HOUSE ANNEX | SHOMOLU | MAGODO | 200 | #NAME? | 11-MagodoINJ-T1-Shangisha | 6.614 | 3.3678 | 1 SHANGISHA | Complete Installation | 500/5A LVMD | Batch 1 | aderalph | 060022033714 | FACILITY STAKEHOLDERS DELAYING INSTALLATION
4 | 0102229993 | SIMON PETER OPARA | SHOMOLU | MAGODO MEGA | PUBLIC | #NAME? | 11-MagodoINJ-T1-Shangisha |  |  | 2, EMMANUEL KESHI STR, MAGODO PHASE II LAGOS | Complete Installation | 200/5A LVMD | Batch 1 | aderalph | 060022031687 | ALREADY METERED
5 | 0102071186 | AMBIENCE HOTEL & RESORT | SHOMOLU | MAGODO MEGA | PUBLIC | #NAME? | 11-MagodoINJ-T1-Shangisha |  |  | 23 ADEKUNLE BANJO AVENUE | Complete Installation | 200/5A LVMD | Batch 1 | aderalph | 060022031685 | ALREADY PAID FOR NEW METER AND EXPECTING IT
6 | 0102173664 | SADELA SAMUEL | SHOMOLU | OWOROSHONKI MEGA | PUBLIC | #NAME? | 11-OguduINJ-T3-Soluyi |  |  | SHOLUYI VILL OFF AMOELE | Complete Installation | 500/5A LVMD | Batch 1 | tee n bee | 060022032745 | ALREADY METERED
7 | 0102403987 | BAPTIST COMPOUND | SHOMOLU | OWOROSHONKI MEGA | PUBLIC | #NAME? | 11-Ilupeju BypassINJ-T1-Obanikoro |  |  | BAPTIST ACADEMY OBANIKORO LAGOS | Complete Installation | 500/5A LVMD | Batch 1 | tee n bee | 060022033445 | ALREADY METERED
8 | 0100098726 | POWER HOLDING COMPANY OF NIG., | IKEJA | PTC | 300 | #NAME? | 33-OgbaTCN-PTC EXP. | #NAME? | #NAME? | 1. GENERAL HOSPITAL ROAD. IKEJ PTC UNDERTAKING OFFICE LAGOS STATE | Complete Installation | 500/5A LVMD | Batch 1 | demol | 060022033729 | VOLTAGE CABLE CASTED /UNDERGROUND | 2024-07-11
9 | 0100069057 | GOODISS SUPERSTORES LTD | IKEJA | PTC | 300 | #NAME? | 11-PTCINJ-T2-Awuse | 6.587 | 3.3576 | 21/22, MOBOLAJI BANK ANTHONY WAY, MARYLAND , IKEJA , LAGOS | Complete Installation | 500/5A LVMD | Batch 1 | demol | 060022033000 | SHORT CABLE AT SITE | 2024-07-10
10 | 0101477190 | NPF MICROFINANCCE BANK PLC | IKEJA | PTC | PUBLIC | #NAME? | 11-PTCINJ-T2-Awuse |  |  | OBA AKINJOBI WAY, GRA, IKEJA | Complete Installation | 200/5A LVMD | Batch 1 | demol | 060022033563 | CUSTOMER DOESN’T WANT METER TO BE CHANGE | 2024-07-10
11 | 0101394974 | DR ADEBOLA SULAIMON | IKEJA | PTC | PTC |  | 11-PTCINJ-T3-General Hospital | 6.575 | 3.347 | 90 ODUDUWA CRESCENT | Faulty Electronic component | 200/5A LVMD | Faulty meter | welldone/meter with vicbonny | 060022033364 | Requires 2m cable of 150mm X 4 core
12 | 0100068948 | AYOOLA ABIDOYE | IKEJA | PTC | PTC |  | 11-PTCINJ-T3-General Hospital | 6.5804 | 3.3437 | 54 OLADIPO BATEYE ST IKEJA G R A | Complete Installation | 200/5A LVMD | Faulty meter | welldone/meter with vicbonny | 060022033365 | customer refused access to location
13 | NEW ACCOUNT | ARAROMI COMMUNITY | IKEJA | OJODU | PUBLIC |  | 11-OjoduINJ-T1-Ojodu |  |  | ADENIYI OKE STREET | Complete Installation | 500/5A LVMD | Batch 1 | tee n bee | 60022031858 | require 1 concrete po;e and 150mmx 4core
14 | 0100062889 | THE APOSTOLIC FAITH MISSION | SHOMOLU | MENDE | MENDE | #NAME? | 11-MarylandINJ-T3-Sylvia | 6.5626 | 3.3772 | 1, APOSTOLIC FAITH COMP | Complete Installation | 800/5A LVMD | Batch 1 | aderalph | 060022033161 | need cable/ short cable
15 | 0100098717 | ALHAJI KAREEM YUSUF | IKEJA | PTC | PTC | #NAME? | 11-PTCINJ-T1-Opebi | 6.5941 | 3.3516 | 7A ABIODUN CLOSE OFF TOYIN STREET LAGOS | Complete Installation | 500/5A LVMD | Batch 1 | quintec | 060022033659 | customer doesn’t want meter said they have case with IE IN COURT
16 | 0101451596 | GLOBACOM LTD - LAG 309 | IKEJA | PTC | PTC | #NAME? | 11-MarylandINJ-T2-GRA |  |  | BEHIND BRISCOE MOTORS OFF MOBOLAJI BANK ANTHONY WAY, IKEJA | Complete Installation | 200/5A LVMD | Batch 1 | quintec | 060020123680 | NEED CABLE
17 | 100070201 | REX CHARLES AND PATRICK LTD | SHOMOLU | OLATEJU | OLATEJU | #NAME? | 11-Ilupeju BypassINJ-T1-Industrial | 6.5417 | 3.3571 | AGEGE MOTOR RD | Complete Installation | 500/5A LVMD | Batch 1 | tee n bee | 60022032581 | ALREADY METERED
18 | 0102290575 | MEGAVONS C.P.E.D | SHOMOLU | IGBOBI MEGA | IGBOBI MEGA | #NAME? | 11-IgbobiINJ-T2-Market |  |  | 134 IKORODU ROAD ONIPANU | Complete Installation | 200/5A LVMD | Batch 1 | All solution | 60022301677 | ALREADY METERED
19 | 0102726053 | ATC WILESS 403132 LG0778 | SHOMOLU | ILUPEJU MEGA | ILUPEJU MEGA | #NAME? | 11-Ilupeju BypassINJ-T1-Industrial |  |  | 15 TAIWO KOYA STREET OFF MOGAJI STREET ILUPEJU, LAGOS | Complete Installation | Whole current meter | Batch 1 | All solution | 060021051084 | ALREADY METERED
20 | 0102122637 | JIDE AGABE | IKEJA | OREGUN | OREGUN | #NAME? | 11-New AlausaINJ-T4-Oregun |  |  | 3B,OLUFUNKE ATITEBI JULI ESTATE,IKEJA,LAGOS | Complete Installation | 200/5A LVMD | Batch 1 | mayfak | 060022033722 | short cable
21 | 0102731129 | PIUS KOLAWOLE EDDO | IKEJA | OREGUN | OREGUN | #NAME? | 11-New AlausaINJ-T5-Alausa |  |  | 24 IYALLA STREET OFF KAFFI ALAUSA IKEJA | Complete Installation | 200/5A LVMD | Batch 1 | mayfak | 060022031870 | short cable
22 | 0101309240 | KUNLE | IKEJA | OREGUN | OREGUN | #NAME? | 11-New AlausaINJ-T6-Ogundana |  |  | 31B, OGUNDANA STREET OFF ALLEN AVENUE | Complete Installation | 200/5A LVMD | Batch 1 | mayfak | 060022032494 | short cable
21 | 0101823509 | ENIOLA OLUFEMI SAMUEL | 2/4, AMBALI STREET, OFF LIASU ROAD, EGBE | OSHODI | IKOTUN | PUBLIC | 0 | 33-EjigboTCN-AGODO | Complete Installation | 200/5A LVMD | Batch 2 | tee n bee | 060022031880 | utm ikotun said that meter is working
22 | 0101358418 | ANYIRA EBUNOLUWA TITILOPE | 38,OPELOYERU STR. OFF LIASU RD. IKOTUN | OSHODI | IKOTUN | PUBLIC | 0 | 33-EjigboTCN-AGODO | Complete Installation | 200/5A LVMD | Batch 2 | tee n bee |  | customrer pack out/meter installed at another customer site
23 | 0100069573 | ILOANYA EARNEST | 23 BAYO STREET OFF LIASU ROAD IKOTUN LAGOS | OSHODI | IKOTUN | 300 | 0 | 33-EjigboTCN-AGODO | Complete Installation | 500/5A LVMD | Batch 2 | tee n bee | 060022032862 | utm ikotun said that meter is working
24 | 0101553276 | OMIDIYA OLUGBENGA | GEORGE STREET, EKINMOGUN, LAGOS | AKOWONJO | GOWON | 300 | 201508007287 | 11-AlimoshoINJ-T4-FHA | Complete Installation | 500/5A LVMD | Batch 2 | Aderalph |  |  | meter assigned to location 500/5a (060022033583) but has been installed in another location/n;b omc said not to install the meter
25 | 0101005660 | CHUKWUDI NWOSU MR & MRS | 29 ADENIYI JONES AVENUE IKEJA LAGOS | IKEJA | ANIFOWOSHE | PUBLIC | 250709288 | 11-Adeniyi JonesINJ-T1-Adeniyi Jones | Complete Installation | Whole current meter | Batch 2 | Aderalph | 60021052879 |  | customer doesn’t want meter

## OUTSTANDING WC LVMD (hidden)
S/N | CIS DT Number | New Unique DT Nomenclature | BAND | BU | UT | New UT Name | Feeder Name | Ownership | Installation Position | Metering Status | OLD Meter Number | Meter Functionality Status | Meter Type | Capacity | Connection Status | Commissioning Status | Maintenance Status | Disconnection Status | Coordinates (LAT) | Coordinates (LONG) | Addresses | Identified Issue(s) | Required Materials | Remark by EM Engineer | SBC SCHEDULED FOR INSTALLATION | NEW METER INSTALLED AT DT | STATUS | DATE OF INSTALLATION

## OUTSTANDING WC (2) (hidden)
S/N | CIS DT Number | New Unique DT Nomenclature | BAND | BU | UT | New UT Name | Feeder Name | Ownership | Installation Position | Metering Status | OLD Meter Number | Meter Functionality Status | Meter Type | Capacity | Connection Status | Commissioning Status | Maintenance Status | Disconnection Status | Coordinates (LAT) | Coordinates (LONG) | Addresses | Identified Issue(s) | Required Materials | Remark by EM Engineer | SBC SCHEDULED FOR INSTALLATION | NEW METER INSTALLED AT DT | STATUS | DATE OF INSTALLATION

## WC TO DEPLOY (hidden)
S/N | CIS DT Number | New Unique DT Nomenclature | BAND | BU | UT | New UT Name | Feeder Name | Ownership | Installation Position | Metering Status | OLD Meter Number | Meter Functionality Status | Meter Type | Capacity | Connection Status | Commissioning Status | Maintenance Status | Disconnection Status | Coordinates (LAT) | Coordinates (LONG) | Addresses | STATUS | DATE OF INSTALLATION